Brook Trout WG 2021 SRS Cycle

**SRS Check in**: Yet to be scheduled, should be scheduled for **some time in late May.**

* Highlight our current logic and action plan
* Write Narrative analysis
* Meet with SRS team to discuss documents and common requests with other work groups

**STAR Materials Due: July 15th**

* DRAFT 2022-2023 logic and action plan
* DRAFT QPM Presentation
* DRAFT Management Strategy
* Narrative analysis

**STAR Dry Runs: July 22nd**

* Receive feedback from STAR on presentation and documents

**QPM Materials Due: July 26th**

* FINAL 2022-2023 Logic and Action Plan
* FINAL Presentation
* FINAL Narrative Analysis
* FINAL Management Strategy

**QPM: August 12th**

* Deliver presentation

**Near Final SRS Materials Due: November 10th**

* Near Final Presentation
* Near Final Logic and Action Plan
* Near Final Narrative Analysis
* Near Final Management Strategy

**Signatory Review begins: November 11th**

**Signatory Review Ends: November 29th**

**Final Materials Due: December 8th**

* Final Presentation
* Final Logic and Action Plan
* Final Narrative analysis
* Final Management Strategy

**Final Materials Presented to MB: December 9th**