## Slide 1: Draft Expectations for Watershed Implementation Plans
Jon Capacasa and Katherine Antos
U.S. EPA Region III Water Protection Division
and Chesapeake Bay Program Office
Principals’ Staff Committee
October 23, 2009
Attachment F
Subject to Change

## Slide 2: Watershed Implementation Plan Overview
Plans + Milestones + “Consequences” = New Accountability Framework
Major recommendation of draft Executive Order 202(a) report
Identify nutrient and sediment reductions by sector and area over time
Fulfill Short-Term Needs:
  Support and inform establishment of Bay TMDL
  Provide assurance that TMDL can and will be achieved and maintained
Fulfill Long-Term Need: Set targets for assessing accountability over time
Considered WQGIT feedback, but expectations do not represent WQGIT recommendations or decisions

## Slide 3: Response to Concerns with Short Timeframe to Develop Plans
Defer some planning elements to a later date
Phase I Plan: Target loads by source sector and segment drainage area to inform Bay TMDL WLAs and LAs
  Preliminary: June 1, 2010
  Draft: August 1, 2010
  Final: November 1, 2010
Phase II Plan: Include local area target loads and identify specific controls to be implemented by 2017
  Draft: June 1, 2011
  Final: No later than November 1, 2011
2-year Milestones: Near-term, specific commitments and actions
  Iterative: 2012 – 2013; 2014 – 2015; etc.
Phase III Plan: Update 2018 - 2025 implementation efforts
  Final: No later than January 1, 2017

## Slide 4: Role in TMDL Process
Subject to Change
Major basin
jurisdiction
loading
targets
Plan details into draft WLAs & LAs
Final
TMDL
Established
Nov. 2009 – August 2010
December 2010
EPA
sends
Expect-
ations letter to
PSC
EPA
sends
Conse-
quences letter to PSC
Fall
2009
2012 – 2025
2-year
milestones, reporting, modeling, monitoring
Develop Ph. I WIP
Ph II
WIP
with
local
targets
and controls
No later than November 2011

## Slide 5: Watershed Implementation Plan Includes:
Interim and Final Target Loads by Major Basin and Sector
Current Program Capacity and Gap Analysis
Policies, Rules, Dates for Key Actions to Fill Gaps
Mechanisms to Account for Growth
Contingencies for Failed or Delayed Implementation
Appendix with:
  Loads divided by 303(d) segment drainage and source sector
  2-year milestone loads by jurisdiction – EPA will use to assess milestones
  No later than November 2011: Update to include loads divided by local area and controls to meet 2017 interim target load
Chesapeake Bay Program will provide scenario outputs and technical support to assist jurisdictions with Plan development

## Slide 6: Scale of WIP Target Loads
Bay TMDL: WLAs and LAs for 92 303(d) segments
WIPs: Subdivide by source sector, NPDES, segment drainage, and, by no later than Nov. 2011, local area
Local area based on:
  Engaging local partners
  Scale that programs are administered
Progress first assessed at jurisdiction scale

## Slide 7: Interim Target Load
States and District must have controls in place to meet interim target by 2017
  Demonstrates on track to meet final target load by 2025
  EPA assesses if 2-year milestones on schedule to meet interim and final target loads and imposes consequences as necessary
60% between 2008 loads and target loads
  Basinwide: 233 mil lbs/yr N and 15.5 mil lbs/yr P
  Represents ~18% decrease of N and ~5% decrease of P compared to 2008 loads
  Corresponds to modeled water quality improvements
  With greater justification, EPA may accept interim target of no less than 50% between current and target loads

## Slide 8
1985 – 2008 loads based on Chesapeake Bay Program Phase 5.2 Watershed Model Scenarios. 2017 and 2025 targets are loads that would result from controls in place in 2017 and 2025.

## Slide 9
Basinwide Interim Target Load
EPA Will Assess if
Milestone
Reductions are on Schedule to Meet Target Loads
Assumes Upfront Program-Building and Future Reductions
Assumes Constant Reduction Over Time
Assumes Upfront Low-Hanging Fruit and More Difficult Future Reductions
< Interim Target
233
284
200

## Slide 10: Dissolved Oxygen Violations
Breakpoint in # Segments with D.O. Violations
Total Nitrogen Loads Delivered to Bay from Watershed (mil lbs/year)
Number of Segments with D.O. Violations

## Slide 11: Staged Implementation
Stage 1: Current Loads – Interim Target
  2011 – 2017
Stage 2: Interim – Final Target
  2018 – no later than 2025
Less details on Stage 2 if States and District commit to update Plans by 2017
  Potential actions that will result in final target loads to provide assurance that final TMDL will be achieved
  Recognize 2018 – 2025 milestones may change
Specific implementation efforts adapted and assessed through 2-year milestones

## Slide 12
Example: Projected Nitrogen Delivery from
Major Basin in Each Jurisdiction by Source Sector
Also divide jurisdiction load by 303(d) segment drainage area and, by November 2011, local area
Attain jurisdiction-wide load reductions by the interim target, or justify why can still meet final target
Jurisdiction would determine desired 2-year schedule to meet interim and final target loads
EPA first evaluates milestones based on consistency with jurisdiction target load. EPA accepts shifts among source sectors, basins, segment drainages, and local areas if jurisdiction target load is met and local and Bay water quality goals are achieved
Propose increased budget to legislature
Increased program budget
Increased controls
Propose new legislative authorities
Rulemaking
Implement regulatory controls
Examples of Some Planned Controls
Load Reduction
Schedule
Interim
Targets
Final
Targets
35
26
20
Stage 1 Implementation
Stage 2 Implementation
Milestones for Assessing Progress

## Slide 13: Jon Capacasa, Director Water Protection Division U.S. EPA Region III capacasa.jon@epa.gov (215) 814-5422 Katherine Antos, Coordinator Water Quality Goal Implementation Team U.S. EPA Chesapeake Bay Program Office antos.katherine@epa.gov (410) 295-1358