## ControlsPublished2009
Pollution Control Practices Included in 2009-2011 Milestone Commitments |  | DC | DC | DC | DC | DC | DC | DE | DE | DE | DE | DE | DE | MD | MD | MD | MD | MD | MD | MD | MD | NY | NY | NY | NY | NY | NY | PA | PA | PA | PA | PA | PA | VA | VA | VA | VA | VA | VA | WV | WV | WV | WV | WV | WV | ALL | ALL | ALL | ALL | ALL | ALL | Notes
Info from this worksheet will be used to update the "Pollution Control Practices Included in 2009-2011 Milestone Commitments" table in the fact sheets from the 2011 EC mtg. Blue-highlighted cells require data. CBPO will pre-populate "credited practices" using 2011 progress run data submitted via NEIEN. Jurisdictions are responsible for providing 2011 data for "non-credited practices". Values in "Progress (7/1/08-6/30/11)" and "% Achieved (7/1/08-6/30/11)" columns will re-calculate automatically. Please refer to notes (at far right) regarding yellow highlighted cells. |  | DC: Values in this column will re-calculate after blue cells in column F are populated; DC: Values in this column will re-calculate after blue cells in column F are populated; DE: Values in this column will re-calculate after blue cells in column L are populated; DE: Values in this column will re-calculate after blue cells in column L are populated; MD: Values in this column will re-calculate after blue cells in column R are populated; MD: Values in this column will re-calculate after blue cells in column R are populated; MD: Values in this column will re-calculate after blue cells in column R are populated; NY: Values in this column will re-calculate after blue cells in column Z are populated; NY: Values in this column will re-calculate after blue cells in column Z are populated; PA: Values in this column will re-calculate after blue cells in column AF are populated; PA: Values in this column will re-calculate after blue cells in column AF are populated; VA: Values in this column will re-calculate after blue cells in column AL are populated; VA: Values in this column will re-calculate after blue cells in column AL are populated; WV: Values in this column will re-calculate after blue cells in column AR are populated; WV: Values in this column will re-calculate after blue cells in column AR are populated; ALL: Values in this column will re-calculate after blue cells in columns F, L, R, Z, AF, AL, AR are populated; ALL: Values in this column will re-calculate after values in column AX re-calculate; ALL: Values in this column will re-calculate after values in column AY re-caluclate
Agriculture: | Units | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | Original 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | Adapted* 2009-2011 Commitment | % Adapted* Commitment Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | MD's table contains two additional columns (compared to other jurisdictions) since this more current information is documented and available to the public on Bay Stat
Animal Waste Management Systems, All Types | animal units | NY: 43500; NY: 14848; NY: 34.13%; NY: 14848; NY: 34.13%; ALL: 43500; ALL: 14848; ALL: 34.13%; ALL: 0; ALL: 14848; ALL: 34.13%
Animal Waste Management Systems, All Types | structures | MD: 198; MD: 116; MD: 58.59%; MD: 116; MD: 58.59%; MD: 130; MD: 89.23%; ALL: 198; ALL: 116; ALL: 58.59%; ALL: 0; ALL: 116; ALL: 58.59%
Animal Waste Management Systems, All Types | systems | MD: 75; MD: 135; MD: 180%; MD: 135; MD: 180%; MD: 175; MD: 77.14%; PA: 275; PA: 274; PA: 99.64%; PA: 274; PA: 99.64%; VA: 273; VA: 264; VA: 96.7%; VA: 264; VA: 96.7%; WV: 11; WV: 38; WV: 345.5%; WV: 38; WV: 345.5%; ALL: 634; ALL: 711; ALL: 112.1%; ALL: 0; ALL: 711; ALL: 112.1%
Carbon Sequestration/Alternative Crops | acres | PA: 25740; PA: 4533; PA: 17.61%; PA: 4533; PA: 17.61%; ALL: 25740; ALL: 4533; ALL: 17.61%; ALL: 0; ALL: 4533; ALL: 17.61%
Conservation Plans/SCWQP | acres | MD: 257049; MD: 35849; MD: 13.95%; MD: 35849; MD: 13.95%; MD: 257049; MD: 13.95%; PA: 327599; PA: 158610; PA: 48.42%; PA: 158610; PA: 48.42%; ALL: 584648; ALL: 194459; ALL: 33.26%; ALL: 0; ALL: 194459; ALL: 33.26%
Conservation Tillage, All Types | acres/yr | NY: 3000; NY: 1513; NY: 50.43%; NY: 1513; NY: 50.43%; PA: 175491; PA: 101470; PA: 57.82%; PA: 101470; PA: 57.82%; VA: 128500; VA: 135186; VA: 105.2%; VA: 135186; VA: 105.2%; ALL: 306991; ALL: 238169; ALL: 77.58%; ALL: 0; ALL: 238169; ALL: 77.58%
Cover Crop Planting, All Types | acres/yr | [6 empty] | 37200 | 18322 | 49.25% |  | 18322 | 49.25% | 460000 | 25347 | 5.51% |  | 25347 | 5.51% | 325000 | 7.799% | 1000 | 717 | 71.7% |  | 717 | 71.7% | 174818 | 201653 | 115.4% |  | 201653 | 115.4% | 157000 | 119018 | 75.81% |  | 119018 | 75.81% | 1500 | 3157 | 210.5% |  | 3157 | 210.5% | 831518 | 368214 | 44.28% | 0 | 368214 | 44.28%
Dairy & Poultry Manure Incorporation Technology | acres | MD: 5000; MD: 892; MD: 17.84%; MD: 892; MD: 17.84%; MD: 2500; MD: 35.68%; ALL: 5000; ALL: 892; ALL: 17.84%; ALL: 0; ALL: 892; ALL: 17.84%
Forest Buffers | acres | [6 empty] | 2700 | 2236 | 82.81% |  | 2236 | 82.81% | 5100 | 563 | 11.04% |  | 563 | 11.04% | 895 | 62.91% | 2051 | 408 | 19.89% |  | 408 | 19.89% | 19059 | 35709 | 187.4% |  | 35709 | 187.4% | 10000 | 7823 | 78.23% |  | 7823 | 78.23% | 200 | 898 | 449% |  | 898 | 449% | 39110 | 47637 | 121.8% | 0 | 47637 | 121.8%
Forest Harvesting Practices | acres | PA: 125; PA: 4758; PA: 3806%; PA: 4758; PA: 3806%; ALL: 125; ALL: 4758; ALL: 3806%; ALL: 0; ALL: 4758; ALL: 3806%
Grass Buffers | acres | [12 empty] | 8000 | 1607 | 20.09% |  | 1607 | 20.09% | 2319 | 69.3% | 3549 | 599 | 16.88% |  | 599 | 16.88% | 1161 | 3082 | 265.5% |  | 3082 | 265.5% | 2000 | 2859 | 142.9% |  | 2859 | 142.9% | 200 | 0 | 0% |  | 0 | 0% | 14910 | 8147 | 54.64% | 0 | 8147 | 54.64%
Heavy Use Poultry Areas Concrete Pads | farms | MD: 400; MD: 290; MD: 72.5%; MD: 290; MD: 72.5%; MD: N/A; MD: N/A; ALL: 400; ALL: 290; ALL: 72.5%; ALL: 0; ALL: 290; ALL: 72.5%
Horse Pasture Management | acres | NY: 300; NY: 77; NY: 25.67%; NY: 77; NY: 25.67%; ALL: 300; ALL: 77; ALL: 25.67%; ALL: 0; ALL: 77; ALL: 25.67%
Land Retirement | acres | MD: 3800; MD: 1470; MD: 38.68%; MD: 1470; MD: 38.68%; MD: 2500; MD: 58.8%; NY: 2000; NY: 75; NY: 3.75%; NY: 75; NY: 3.75%; PA: 58876; PA: 142377; PA: 241.8%; PA: 142377; PA: 241.8%; VA: 19000; VA: 17465; VA: 91.92%; VA: 17465; VA: 91.92%; ALL: 83676; ALL: 161387; ALL: 192.9%; ALL: 0; ALL: 161387; ALL: 192.9%
Manure Transport | net tons reduced | DE: 55100; DE: 49844; DE: 90.46%; DE: 49844; DE: 90.46%; MD: 10000; MD: 8213; MD: 82.13%; MD: 8213; MD: 82.13%; MD: 10000; MD: 82.13%; PA: 58915; PA: 279392; PA: 474.2%; PA: 279392; PA: 474.2%; WV: 14000; WV: 13109; WV: 93.64%; WV: 13109; WV: 93.64%; ALL: 138015; ALL: 350558; ALL: 254%; ALL: 0; ALL: 350558; ALL: 254%
Mortality Composters | units | MD: 100000; MD: 0%; PA: 22; PA: 18; PA: 81.82%; PA: 18; PA: 81.82%; ALL: 22; ALL: 18; ALL: 81.82%; ALL: 0; ALL: 18; ALL: 81.82%
Nutrient Management, All Types | acres/yr | [6 empty] | 177000 | 177000 | 100% |  | 177000 | 100% | 100000 | 95709 | 95.71% |  | 95709 | 95.71% | 198 | 48338% | 38000 | 13622 | 35.85% |  | 13622 | 35.85% | 129250 | 69491 | 53.76% |  | 69491 | 53.76% | 258000 | 122021 | 47.29% |  | 122021 | 47.29% | [6 empty] | 702250 | 477843 | 68.04% | 0 | 477843 | 68.04%
Pasture Grazing Best Management Practices, All Types | feet | NY: 608000; NY: 410378; NY: 67.5%; NY: 410378; NY: 67.5%; ALL: 608000; ALL: 410378; ALL: 67.5%; ALL: 0; ALL: 410378; ALL: 67.5%
Pasture Grazing Best Management Practices, All Types | acres | [12 empty] | 6000 | 5612 | 93.53% |  | 5612 | 93.53% | 7400 | 75.84% | 18700 | 6291 | 33.64% |  | 6291 | 33.64% | 34727 | 13294 | 38.28% |  | 13294 | 38.28% | 89500 | 61083 | 68.25% |  | 61083 | 68.25% | 14000 | 10214 | 72.96% |  | 10214 | 72.96% | 162927 | 96494 | 59.23% | 0 | 96494 | 59.23%
Poultry Phytase | P lbs reduced | PA: 19626; PA: 13084; PA: 66.67%; PA: 13084; PA: 66.67%; ALL: 19626; ALL: 13084; ALL: 66.67%; ALL: 0; ALL: 13084; ALL: 66.67%
Precision Feeding and/or Forage Mgmt. | animal units | NY: 7600; NY: 3160; NY: 41.58%; NY: 3160; NY: 41.58%; ALL: 7600; ALL: 3160; ALL: 41.58%; ALL: 0; ALL: 3160; ALL: 41.58%
Stream Restoration | linear feet | PA: 215088; PA: 197123; PA: 91.65%; PA: 197123; PA: 91.65%; VA: 13000; VA: 8060; VA: 62%; VA: 8060; VA: 62%; WV: 4000; WV: 9082; WV: 227.1%; WV: 9082; WV: 227.1%; ALL: 246344; ALL: 217829; ALL: 88.42%; ALL: 0; ALL: 217829; ALL: 88.42%
Tree Planting | acres | DE: 200; DE: 11; DE: 5.5%; DE: 11; DE: 5.5%; NY: 200; NY: 13; NY: 6.5%; NY: 13; NY: 6.5%; PA: 15065; PA: 3191; PA: 21.18%; PA: 3191; PA: 21.18%; VA: 12500; VA: 10040; VA: 80.32%; VA: 10040; VA: 80.32%; ALL: 27965; ALL: 13255; ALL: 47.4%; ALL: 0; ALL: 13255; ALL: 47.4%
Water Control Structures, Ag. | structures | MD: 200; MD: 66; MD: 33%; MD: 66; MD: 33%; MD: 125; MD: 52.8%; ALL: 200; ALL: 66; ALL: 33%; ALL: 0; ALL: 66; ALL: 33%
Wetland Restoration, ag land | acres | DE: 420; DE: 436; DE: 103.8%; DE: 436; DE: 103.8%; MD: 1700; MD: 797; MD: 46.88%; MD: 797; MD: 46.88%; MD: 1155; MD: 69%; NY: 100; NY: 130; NY: 130%; NY: 130; NY: 130%; PA: 1548; PA: 802; PA: 51.81%; PA: 802; PA: 51.81%; ALL: 3768; ALL: 2165; ALL: 57.46%; ALL: 0; ALL: 2165; ALL: 57.46%
Wetland Restoration, other land | acres | NY: 350; NY: 350; NY: 100%; NY: 350; NY: 100%; VA: 36; VA: 39.72; VA: 110.3%; VA: 39.72; VA: 110.3%; WV: 5; WV: 0.2; WV: 4%; WV: 0.2; WV: 4%; ALL: 391; ALL: 389.92; ALL: 99.72%; ALL: 0; ALL: 389.92; ALL: 99.72%
Urban/Suburban: | Units | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | Original 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | Adapted* 2009-2011 Commitment | % Adapted* Commitment Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | MD's table contains two additional columns (compared to other jurisdictions) since this more current information is documented and available to the public on Bay Stat
Abandoned Mine Reclamation | acres | PA: 2219; PA: 1616; PA: 72.83%; PA: 1616; PA: 72.83%; ALL: 2219; ALL: 1616; ALL: 72.83%; ALL: 0; ALL: 1616; ALL: 72.83%
Dirt & Gravel Road Erosion & Sediment Control | feet | PA: 124913; PA: 509522; PA: 407.9%; PA: 509522; PA: 407.9%; ALL: 124913; ALL: 509522; ALL: 407.9%; ALL: 0; ALL: 509522; ALL: 407.9%
Downspout Connections | downspouts | DC: 300; DC: 975; DC: 325%; DC: 975; DC: 325%; ALL: 300; ALL: 975; ALL: 325%; ALL: 0; ALL: 975; ALL: 325%
Erosion & Sediment Control | acres | NY: 150; NY: 1880.3; NY: 1254%; NY: 1880.3; NY: 1254%; PA: 7000; PA: 8173; PA: 116.8%; PA: 8173; PA: 116.8%; VA: 61000; VA: 54984; VA: 90.14%; VA: 54984; VA: 90.14%; WV: 1400; WV: 3501; WV: 250.1%; WV: 3501; WV: 250.1%; ALL: 69550; ALL: 68538.3; ALL: 98.55%; ALL: 0; ALL: 68538.3; ALL: 98.55%
Green Roofs | square feet | DC: 2500000; DC: 1300000; DC: 52%; DC: 1300000; DC: 52%; ALL: 2500000; ALL: 1300000; ALL: 52%; ALL: 0; ALL: 1300000; ALL: 52%
Litter Trap Installation Demo Projects | pounds trash diverted | DC: 6800; DC: 6800; DC: 100%; DC: 6800; DC: 100%; ALL: 6800; ALL: 6800; ALL: 100%; ALL: 0; ALL: 6800; ALL: 100%
Rain Barrels | barrels | DC: 250; DC: 975; DC: 390%; DC: 975; DC: 390%; ALL: 250; ALL: 975; ALL: 390%; ALL: 0; ALL: 975; ALL: 390%
Rain Gardens | gardens | DC: 100; DC: 92; DC: 92%; DC: 92; DC: 92%; ALL: 100; ALL: 92; ALL: 92%; ALL: 0; ALL: 92; ALL: 92%
Retrofit Catch Basins for Trash Control | catch basins | DC: 100; DC: 200; DC: 200%; DC: 200; DC: 200%; ALL: 100; ALL: 200; ALL: 200%; ALL: 0; ALL: 200; ALL: 200%
Sanitary Sewer Replacement | miles | DC: 1.5; DC: 0.38; DC: 25.33%; DC: 0.38; DC: 25.33%; ALL: 1.5; ALL: 0.38; ALL: 25.33%; ALL: 0; ALL: 0.38; ALL: 25.33%
Septic Improvements, All Types | systems | [6 empty] | 8800 | 387 | 4.398% |  | 387 | 4.398% | 3000 | 1916 | 63.87% |  | 1916 | 63.87% | 3139 | 61.04% | [6 empty] | 7353.2 | 42022 | 571.5% |  | 42022 | 571.5% | 806 | 28109 | 3487% |  | 28109 | 3487% | 7166 | 7857 | 109.6% |  | 7857 | 109.6% | 27125.2 | 80291 | 296% | 0 | 80291 | 296%
Storm Drain Marker Installation | markers/yr | DC: 1000; DC: 1000; DC: 100%; DC: 1000; DC: 100%; ALL: 1000; ALL: 1000; ALL: 100%; ALL: 0; ALL: 1000; ALL: 100%
Stormwater Management, All Types (including urb. nut. man.) | acres | MD: 90000; MD: 15423; MD: 17.14%; MD: 15423; MD: 17.14%; MD: 90000; MD: 17.14%; PA: 8690; PA: 48; PA: 0.5524%; PA: 48; PA: 0.5524%; VA: 182000; VA: 77226; VA: 42.43%; VA: 77226; VA: 42.43%; WV: 1050; WV: 1230; WV: 117.1%; WV: 1230; WV: 117.1%; ALL: 281740; ALL: 93927; ALL: 33.34%; ALL: 0; ALL: 93927; ALL: 33.34%
Stream Restoration | linear feet | DC: 14256; DC: 3564; DC: 25%; DC: 3564; DC: 25%; PA: 4400; PA: 0; PA: 0%; PA: 0; PA: 0%; ALL: 18656; ALL: 3564; ALL: 19.1%; ALL: 0; ALL: 3564; ALL: 19.1%
Tree Canopy Expansion | trees | DC: 21500; DC: 9620; DC: 44.74%; DC: 9620; DC: 44.74%; ALL: 21500; ALL: 9620; ALL: 44.74%; ALL: 0; ALL: 9620; ALL: 44.74%; Notes: DC's tree canopy expansion commitment was 5% in 25 years, therefore 0.5% in 2.5 years for this milestone. Commit: 0.5% or 21,500 trees; progress, 9,620 trees
Tree Planting | acres | DC: 30; DC: 30; DC: 100%; DC: 30; DC: 100%; ALL: 30; ALL: 30; ALL: 100%; ALL: 0; ALL: 30; ALL: 100%
Wastewater: | Units | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | Original 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | Adapted* 2009-2011 Commitment | % Adapted* Commitment Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | MD's table contains two additional columns (compared to other jurisdictions) since this more current information is documented and available to the public on Bay Stat
Wastewater Nitrogen | N lbs reduced | 159000 | 962274.6227 | 605.2% |  | 962274.6227 | 605.2% | [6 empty] | 930000 | 1916279.5875 | 206.1% |  | 1916279.5875 | 206.1% | 930000 | 206.1% | 348200 | 278052.2657 | 79.85% |  | 278052.2657 | 79.85% | 1679000 | 1396581.0464 | 83.18% |  | 1396581.0464 | 83.18% | 233000 | -523187.8996 | -224.5% |  | -523187.8996 | -224.5% | [6 empty] | 3349200 | 4029999.6228 | 120.3% | 0 | 4029999.6228 | 120.3%
Wastewater Phosphorus | P lbs reduced | MD: 39000; MD: 119357.8212; MD: 306%; MD: 119357.8212; MD: 306%; MD: 39000; MD: 306%; NY: 36414; NY: 18068.5485; NY: 49.62%; NY: 18068.5485; NY: 49.62%; PA: 49500; PA: 121468.4601; PA: 245.4%; PA: 121468.4601; PA: 245.4%; VA: 126000; VA: 282865.3963; VA: 224.5%; VA: 282865.3963; VA: 224.5%; ALL: 250914; ALL: 541760.2261; ALL: 215.9%; ALL: 0; ALL: 541760.2261; ALL: 215.9%
Air: | Units | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | Original 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) |  |  | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | 2009-2011 Commitment | Progress (7/1/08-6/30/10) | % Achieved (7/1/08-6/30/10) | Progress 7/1/10-6/30/11 | Progress (7/1/08-6/30/11) | % Achieved (7/1/08-6/30/11) | MD's table contains two additional columns (compared to other jurisdictions) since this more current information is documented and available to the public on Bay Stat
Heavy Truck Anti-Idling Rule | hours reduced | PA: 9780000; PA: 9780000; PA: 100%; PA: 9780000; PA: 100%; ALL: 9780000; ALL: 9780000; ALL: 100%; ALL: 0; ALL: 9780000; ALL: 100%
Maryland Healthy Air Act, Air | N lbs reduced | MD: 305882; MD: 305882; MD: 100%; MD: 305882; MD: 100%; MD: 305882; MD: 100%; ALL: 305882; ALL: 305882; ALL: 100%; ALL: 0; ALL: 305882; ALL: 100%

## ControlsNotPublished2009
Pollution Control Practices Subsituted for Original 2009-2011 Milestone Commitments |  | DC | DC | DC | DE | DE | DE | MD | MD | MD | NY | NY | NY | PA | PA | PA | VA | VA | VA | WV | WV | WV | ALL | ALL | ALL
Info from this worksheet will be used to update the "Pollution Control Practices Jurisdiction x Subsituted for Original 2009-2011 Milestone Commitments" table in the fact sheets from the 2011 EC mtg. Blue-highlighted cells require data. CBPO will pre-populate "credited practices" using 2011 progress run data submitted via NEIEN. Jurisdictions are responsible for providing 2011 data for "non-credited practices". Values in "Amount Completed (7/1/08-6/30/11)" columns will re-calculate automatically. |  | DC: Values in this column will re-calculate after blue cells in column D are populated; DE: Values in this column will re-calculate after blue cells in column G are populated; MD: Values in this column will re-calculate after blue cells in column J are populated; NY: Values in this column will re-calculate after blue cells in column M are populated; PA: Values in this column will re-calculate after blue cells in column P are populated; VA: Values in this column will re-calculate after blue cells in column S are populated; WV: Values in this column will re-calculate after blue cells in column V are populated; ALL: Values in this column will re-calculate after blue cells in columns F, L, R, Z, AF, AL, AR are populated; ALL: Values in this column will re-calculate after values in column Y re-calculate
Agriculture: | Units | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11)
Animal Waste Management Systems, All Types | structures | DE: 654; DE: 654; ALL: 654; ALL: 0; ALL: 654
Animal Waste Management Systems, All Types | systems | PA: 19; PA: 19; ALL: 19; ALL: 0; ALL: 19
Conservation Plans/SCWQP | acres | DE: 194666; DE: 194666; NY: 2872; NY: 2872; WV: 65280; WV: 65280; ALL: 262818; ALL: 0; ALL: 262818
Conservation Tillage, All Types | acres/yr | DE: 197799; DE: 197799; MD: 150000; MD: 150000; WV: 431; WV: 431; ALL: 348230; ALL: 0; ALL: 348230
Cropland Irrigation Management | acres | DE: 68442; DE: 68442; ALL: 68442; ALL: 0; ALL: 68442
Forest Harvesting Practices | acres | DE: 3838; DE: 3838; WV: 26508; WV: 26508; ALL: 30346; ALL: 0; ALL: 30346
Grass Buffers | acres | DE: 711; DE: 711; ALL: 711; ALL: 0; ALL: 711
Heavy Use Poultry Areas Concrete Pads | farms | DE: 866; DE: 866; ALL: 866; ALL: 0; ALL: 866
Horse Pasture Management | acres | PA: 1; PA: 1; ALL: 1; ALL: 0; ALL: 1
Land Retirement | acres | WV: 80.6; WV: 80.6; ALL: 80.6; ALL: 0; ALL: 80.6
Mortality Composters | units | DE: 549; DE: 549; ALL: 549; ALL: 0; ALL: 549
Nutrient Management, All Types | acres/yr | WV: 16322; WV: 16322; ALL: 16322; ALL: 0; ALL: 16322
Pasture Grazing Best Management Practices, All Types | acres | DE: 310; DE: 310; ALL: 310; ALL: 0; ALL: 310
Stream Restoration | linear feet | DE: 17700; DE: 17700; ALL: 17700; ALL: 0; ALL: 17700
Tree Planting | acres | MD: 1104; MD: 1104; WV: 556; WV: 556; ALL: 1660; ALL: 0; ALL: 1660
Water Control Structures, Ag. | structures | DE: 8343; DE: 8343; NY: 23; NY: 23; ALL: 8366; ALL: 0; ALL: 8366
Urban/Suburban: | Units | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11)
Abandoned Mine Reclamation | acres | WV: 43; WV: 43; ALL: 43; ALL: 0; ALL: 43
Green Roofs | square feet | WV: 700; WV: 700; ALL: 700; ALL: 0; ALL: 700
Rain Barrels | barrels | WV: 50; WV: 50; ALL: 50; ALL: 0; ALL: 50
Rain Gardens | gardens | WV: 3; WV: 3; ALL: 3; ALL: 0; ALL: 3
Storm Drain Marker Installation | markers/yr | DE: 800; DE: 800; ALL: 800; ALL: 0; ALL: 800
Stormwater Management, All Types (including urb. nut. man.) | acres | DE: 33385; DE: 33385; NY: 1441; NY: 1441; ALL: 34826; ALL: 0; ALL: 34826
Tree Planting | acres | DE: 99; DE: 99; PA: 652; PA: 652; WV: 322; WV: 322; ALL: 1073; ALL: 0; ALL: 1073
Wastewater: | Units | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11) | Amount Completed (7/1/08-6/30/10) | Amount Completed (7/1/10-6/30/11) | Amount Completed (7/1/08-6/30/11)
Wastewater Nitrogen | N lbs reduced | DE: 90141; DE: 90141; WV: 39304.8474; WV: 39304.8474; ALL: 129445.8474; ALL: 0; ALL: 129445.8474
Wastewater Phosphorus | P lbs reduced | DC: 15264; DC: 15264; DE: 1485; DE: 1485; WV: 83521.9431; WV: 83521.9431; ALL: 100270.9431; ALL: 0; ALL: 100270.9431

## ProgrammaticControlsPublished20
Programmatic Controls in 2009-2011 Milestone Commitments | DC | DC | DE | MD | NY | PA | VA | WV
Info from this worksheet will be used to update the "Programmatic Controls in 2009-2011 Milestone Commitments" table in DC's fact sheet from the 2011 EC mtg. Blue-highlighted cells require updates. Other jurisdictions are welcome to list and provide status on their Programmatic Controls published in the factsheets from the 2009 EC mtg. This information can be inlcuded in a table in the fact sheets for the 2012 EC mtg.
Control | 2010 Status | 2011Status | 2011Status | 2011Status | 2011Status | 2011Status | 2011Status | 2011Status
ENR – Award Contract for design by June 1, 2009 | DC: Completed; DC: Completed
ENR – Award contract for construction by December 31, 2011 | DC: Completed; DC: Completed
CSO reductions – completion of nine minimum control projects in May 2009 | DC: Ongoing
Create new tree box standards to allow for better tree growth | DC: Ongoing
Develop lot-level residential stormwater detention/retention through RiverSmart Homes incentive program | DC: Ongoing
Train federal facilities on new stormwater requirements | DC: Ongoing
Implement a program to control discharges from District and federally owned facilities | DC: Ongoing
Strengthen auto repair shop education campaign in Hickey Run (pilot) | DC: Completed; DC: Completed
Inspect all auto repair shops, laundromats and dry cleaners at least once every five years | DC: Completed; DC: Completed
Develop and implement a pet waste strategy | DC: Ongoing
Mandate installation and use of pumpout stations at all District marinas | DC: Completed; DC: Completed
Complete a DPW street sweeping study and implement long-term enhanced street sweeping and fine particle removal | DC: Completed; DC: Completed
Implement and promote new stormwater regulations that require LID construction as a first option and mandate training for site managers | DC: Ongoing
Implement an impervious area-based stormwater fee | DC: Completed; DC: Completed
Review and update zoning regulations to encourage green building | DC: Ongoing
Determine the type of trash control devices that would be the most effective in retaining large debris and sediment in hot-spot areas identified by a trash survey | DC: Ongoing
Incorporate LID into 24 percent of all District DOT projects | DC: Completed; DC: Completed