## Monitoring and baseline
Outcome: Local Leadership
Goal: Citizen Stewardship
Outcome: Local Leadership Outcome: By 2025, continually increase knowledge and capacity of local officials on issues related to water resources and in the implementation of economic and policy incentives that will support local conservation actions.
Management Approach 0: Develop approach for monitoring and baseline development
Key Action Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action | Focus Group Activities (data collection, gap analysis, prorgam/product design, cost analysis) | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate total cost of project (need) | Available funding by Partner | Total Available Funding Roll up of estimated funding | Available funding by Partner
1. Develop and implement approach for determining baseline and monitoring knowledge and capacity of local elected officials. | a. Draft, initiate review, finalize and release of Request for Proposals (RFP) to 1) develop method for measuring increase of knowledge and capacity; and 2) define baseline |  | LL workgroup LGAC/ACB STAR STAC | N/A | Spring 2016
| b. Review draft approach and provide feedback to ACB and contractor on proposed approach for monitoring and baseline |  | LL workgroup LGAC/ACB STAR STAC | N/A | Fall/Winter 2016-2017
| c. Develop strategy, schedule and plan for testing and implmenting approach for baseline development and monitoring increase in knowledge and capacity. (e.g surveys at state assocaition meeitngs, LGAC meetings, online forums, etc) |  | LL workgroup LGAC STAR STAC | N/A | 2016-2017
| d. Implement approaches for baseline development thru various state and regional forums using approaches identified by contractor and strategy defined by workgroup. | Data collection | LL workgroup
LGAC
STAR
2. Explore and implement innvoative approaches for developing baseline (e.g. phone apps, online techniques, juridictional and peer competitions)

## Training and Leadership Program
Outcome: Local Leadership
Goal: Citizen Stewardship
Outcome: Local Leadership Outcome: By 2025, continually increase knowledge and capacity of local officials on issues related to water resources and in the implementation of economic and policy incentives that will support local conservation actions.
Management Approach 1: Develop, enhance, expand leadership and training programs
Key Action Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action | Focus Group Activities (data collection, gap analysis, prorgam/product design, cost analysis) | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap ID related factor or gap in Mgmt. Strat | Estimated Project Cost Best estimate total cost of project (need) | Available funding by Partner | Total Available Funding Roll up of estimated funding | Available funding by Partner
1. Develop inventory of existing statewide, regional and local training forums attended by local officials (environmental, infrstructure, finance, transportation, etc.) | a. Develop a survey and work with jurisdictions and other partners to identify state/regional forums attended by local elected officials. | Data collection - survey/inventory | LL workgroup LGAC DC, DE, MD, PA, VA, WV State/regional associations comissions Training community Federal Agencies | DC, DE, MD, PA, VA, WV | Spring - Fall 2016
2. Conduct strategic sessions, identify and execute opportunities to include CBP content and objectives as part of exising forums for local eleceted officials. | a. Conduct planning session with 3-5 associations per Bay jurisdiction to identify opporunities to incorporate outcome goals and other CBP goals. | Program development/design | LL workgroup LGAC DC, DE, MD, PA, VA, WV State/regional associations and commissions Training Community | DC, DE, MD, PA, VA, WV | Winter 2017
| b. Conduct sessions at forums to identify needs of local elected officials. (also determine knowledge and capacity baseline) | Program development/design
| c. Incorporate watershed-wide and big picture content into forum curricula (per GIT funded report and LL workgroup feedback) | Program development/design
3. Review findings of "Cheapeake Bay Watershed Local Leadership Development Programs" report, jurisdictional, NGO, CBP funded training programs and conduct gap analysis to identify ways to expand successful models. (Online programs like MOST, Environmental Finance Center Training, Watershed Stewards Academy, national Fish and Wildlife Foundation Programs, etc). | a. Form focus group to inventory and assess existing training programs not covered by Leadership Development report. Conduct gap analysis. | Focus Group Data collection - survey/inventory | LL workgroup Jurisdictions CBT Contractor Training Community | Watershedwide | Summer 2016 - Winter 2017
| b. Develop recommended approach for delivery and (initial) content of leadership and training program. | Focus Group Data collection - survey/inventory
4. Conduct research and best practices for capacity building approaches for local leaders and governments. | a. Work with NGO's and CBP partners to inventory approaches to capacity building and determine best bast practices. |  | LL workgroup Jurisdictions CBF - Eastern Shore Training Community CBT and other NGOs | Watershedwide | Summer 2016 - Winter 2017
| b. Distribute best practices through various online and print forms, forums attended by local elected officials. | Program development design

## Peer to Peer Networks
Outcome: Local Leadership
Goal: Citizen Stewardship
Outcome: Local Leadership Outcome: By 2025, continually increase knowledge and capacity of local officials on issues related to water resources and in the implementation of economic and policy incentives that will support local conservation actions.
Management Approach 2: Increase peer to peer knowledge transfer for local officials
Key Action Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action | Focus Group Activities (data collection, gap analysis, prorgam/product design, cost analysis) | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap ID related factor or gap in Mgmt. Strat | Estimated Project Cost Best estimate total cost of project (need) | Available funding by Partner | Total Available Funding Roll up of estimated funding | Available funding by Partner
1. Inventory, evaluate, and develop gap analysis for peer to peer networks (formal and informal, person to person and municipality to municipality). Develop strategic approaches for distributing best practices and developing infrastructure for peer to peer exchanges. | a. Initiate focus group of government officials, NGOs, academics, and training expert, etc others to develop approach and strategy for inventory and gap analysis of peer to peer programs. | Focus Group
| b. Focus group to develop inventory, evaluate, peer to peer networks and identify best practices. | Focus Group data collection - inventory
| c. Focus group to conduct gap analysis. | Gap analysis
| d. Work work jurisdictions, state and regional associations to develop listening sessions (as part of existing forums) to determine preferred approaches for developing peer to peer networks. (e.g. Potomac Watershed Roundtables, PA Clean Water Consortium)) | data collection - listening sessions
2. Develop and secure funding for organization to develop and initiate a peer to peer pilot program. | a. Work with bay jurisdictions and other partners to develop concept for pilot program based on best practices. | program/product design
b. Work with Bay jurisdictions, NFWF and others to identify funding approach for pilot program.
c. Develop and publish Request for Proposals. Select organization to devlop and oversee pilot.
d. LL workgroup, coordinator, and funding org to oversee draft deliverables and progress. Contractor to develop final report highlighting lessons learned and key components of pilot program.
3. Bay Program and its partners will work with existing local officials training forums to facilitate informal peer to peer relationships through existing forums where possible. | a. Local leadership workgroup to work with associations to identify informal approach for building informal peer to peer relationships (e.g. incorporate ice breaking and one on one conversations as part of state association meetings; one page case studies with contact information; central web link of contacts). | Program/prodcut design
b. Develop approach for tracking and observing progress of informal one on one peer relationships. (survey, questionnaire)
c. Create matrix of organizations that can enhance and connect organizational networking efforts for peer to peer exchange.
4. Certification Program?

## Knowledge Transfer
Outcome: Local Leadership
Goal: Citizen Stewardship
Outcome: Local Leadership Outcome: By 2025, continually increase knowledge and capacity of local officials on issues related to water resources and in the implementation of economic and policy incentives that will support local conservation actions.
Management Approach 3: Improve Transfer of knowledge to locals
Key Action Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action | Focus Group Activities (data collection, gap analysis, prorgam/product design, cost analysis) | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap ID related factor or gap in Mgmt. Strat | Estimated Project Cost Best estimate total cost of project (need) | Available funding by Partner | Total Available Funding Roll up of estimated funding | Available funding by Partner
1. Bay Program jurisdictions and partners will initiate activities to inventory, evaluate and conduct gap anaylis of existing methods and approaches for transferring information to local elected officials. | a. Organize focus group to review key knowledge and information, review access to knowledge and information, andways this knowledge is transferred. Focus group will develop inventory of types of content and how its accessed, evaluate and perform a gap analysis. | Focus Group Activity | LL Workgroup, LGAC, CBT Contractor, State and Regional Associations, NGOs, training community
b. Focus group to develop specific receommendations for idnetifying revised approaches for transferring information and improving access for local elected officials.
c. Work with state regional ascoaitions, training community, jurisdictions, to develop and implement approaches for periodic review of content and information tranfer and access.
d. Revise and enhance transfer and acccess approaches as needed.

## Knowledge and Info Sources
Outcome: Local Leadership
Goal: Citizen Stewardship
Outcome: Local Leadership Outcome: By 2025, continually increase knowledge and capacity of local officials on issues related to water resources and in the implementation of economic and policy incentives that will support local conservation actions.
Management Approach 4: Identify and improve key knowledge and information sources
Key Action Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action | Focus Group Activities (data collection, gap analysis, prorgam/product design, cost analysis) | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap ID related factor or gap in Mgmt. Strat | Estimated Project Cost Best estimate total cost of project (need) | Available funding by Partner | Total Available Funding Roll up of estimated funding | Available funding by Partner
1. Identify and prioritize content and information beneficial to local officials such as flooding, land use policies, infrastructure, community benefits from stormwater management. | a. Establish focus group conduct research and evaluation of content and information most relevant to local elected officials. | Focus Group Activity (address mgmnt approaches 3 &4) | LL workgroup Jurisdictions Focus group State/regional associations LGAC | Watershed Wide | Spring 2016
| b. Work with state and regional associations to obtain feedback from local officials and assure that the priority content and information has been identified | Data collection - listenin sessions | LL workgroup Jurisdictions Focus group State/regional associations | Watershed Wide | Fall 2016
| c. Identify approaches for delivering priority content and information in a clear and relevant manner. |  | LL workgroup Jurisdictions Focus group State/regional associations | Watershed Wide | Spring 2017
2. Identify additional content and information from trusted sources that may be relevant to elected officials (economic data, cost benefit, finance, public perception, etc.) | a. Work with jurisdictions, local, regional and state associations and LGAC to identify trusted sources and engage these sources in discussions to determine additional content to facilitate local decision making. | Focus Group Activity | LL workgroup, LGAC, State associations, focus group | watershed Wide | Winter 2016
| b. Organize working session with experts and key trusted sources in tehcnial areas related ares (economic, finance, public perception) to explore additional content that facilitate local decision making. Develop receommended approaches for delivering content. | Focus Group Activity
|  |  |  | Watershed Wide | Spring 2016