## Sheet1
Diversity Workplan Goal: Citizen Stewardship Diversity Outcome: By 2025, identify minority stakeholder groups that are not currently represented in the leadership, decision making and implementation of conservation and restoration activities, and create meaningful opportunities and programs to recruit and engage them in the partnership's efforts.
MANAGEMENT APPROACH 1: COMMUNICATIONS AND OUTREACH
Key Acton | Performance Target | Participating Entity | Geographic Location | Estimated Completion Date | Current Status
1.1 Identify key trusted leaders and interests of underrepresented communities. Establish forums and begin dialogue to better understand how community issues link to watershed restoration. During the process, assess needs and preferences for ongoing communications like online forums, food security, etc. | 1.1.A. Recruit diverse stakeholders and leaders to participate in Chesapeake Watershed Forum. |  | Bay Jurisdictions (PA, MD, DC, DE, VA) | Annual | Ongoing
| 1.1.B. Develop a jurisdiction by jurisdiction contact list of key community leaders and interests/missions/priorities/key contact and communication preferences. | Diversity Workgroup, CBP NOAA DE-DNREC IPC | Bay Jurisdictions (PA, MD, DC, DE, VA) | Fall 2016 | We are leading a GIT funded stormwater project on urban & suburban school grounds that would target school / school system leaders, including those with diverse/minority populations. Also planning to announce internships more broadly through the Diversity Wg and through historically minority/diverse universities - we can develop university contact lists for each jurisdiction..
| 1.1.C. Plan and implement jurisdictional pilot outreach sessions led by key community leaders to determine community interest and potential links to restoration. These sessions will include new and existing forums that are currently planned and underway. | Diversity Workgroup, IPC, DOEE, DE DNREC, NOAA | Bay Jurisdictions (PA, MD, DC, DE, VA) | 2016/2017 | Ongoing
| 1.1.D. Develop a jurisdiction by jurisdiction contact list of key community leaders and interests/missions/priorities/key contact and communication preferences | Diversity Workgroup, CBP NOAA DE-DNREC IPC | Bay Jurisdictions (PA, MD, DC, DE, VA) | Fall 2016 | Ongoing
| 1.1.E. "Plan and Implement a one-day Newport News, Virginia forum during Black History Month in February 2017. Include panel discussions with key trusted community leaders who role-model environmental conservation efforts and reveal opportunities for local involvement in Bay restoration. In conjunction with this forum, hold a job/internship fair. | Alliance for the Bay | Virginia |  | Ongoing
1.2 Work with federal partners to identify opportunities to work with diverse communities adjacent to federal installations. | 1.2.A. Conduct meeting with FLC to identify opportunities to expand, create new, or better promote programs to engage and assist these communities. | Diversity Workgroup |  | 2016/2017 | No Action Yet - FLC Meeting held in 2016
1.3 Work with Toxic Contaminants Workgroup, jurisdictions and contractor to identify communities where fish consumption advisories exist (use EJ Screen tool) and initiate pilot project to improve communications and outreach. | 1.3.A. Establish review and advisory subgroup to oversee fish consumption advisory outreach project and contractor | Diversity Workgroup, Toxics Workgroup DOEE DE-DNREC |  | Winter 2016
| 1.3.B. Conduct planning session with contractor to discuss project scope and overall approach to review fish advisories in affected communities. Conduct periodic meetings to review products, advise Diversity Workgroup, and provide feedback to contractor on suggested improvements to products and deliverables. | Diversity Workgroup, Toxics Workgroup, EPA, DE DNREC | PA, MD, DC, DE, VA | Spring 2017
| 1.3.C. Advisory Subgroup to work with jurisdictions, Diversity Workgroup, contractor to devise activities that lead to dissemination and use of new fish advisory tools and approaches. Oversee implementation of activities. | Diversity Workgroup Toxics Workgroup, MD-DNR, DOEE, DE-DNREC, CBP Communications Workgroup | PA, MD, DC, DE, VA | Winter 2017
| 1.3.D. Engage community stakeholders and explore long term process for reviewing fish consumption and alternatives such as fish swapping etc. Provide recommendations to CBP | Diversity Workgroup, Toxics Workgroup, CBP Communications Workgroup, DE-DNREC | PA, MD, DC, DE, VA | Winter 2016 | 1. Completed - Diversity Workgroup and Toxics Workgroup Established Fish Consumption Review and Advisory subgroup; 2. DE- DNREC Evaluation of water, fish and sediment found low levels of contamination that do not justify advisories.
1.4 Assist the development of Tree Canopy communication and outreach strategies targeted to diverse audiences, focusing on areas with greatest need and opportunity (e.g. low canopy/underserved communities; schools, faith‐based, and other civic organizations; homeowner associations; etc.) | 1.4.A. Work with forestry workgroup and other partners to pursue a workshop and develop case studies on community outreach strategies for Tree Canopy with an emphasis on diversity/ environmental justice opportunities.with forestry workgroup and other partners to pursue a workshop and develop case studies on community outreach strategies for Tree Canopy with an emphasis on diversity/ environmental justice opportunities. | DAT USFS/Forestry Workgroup MD DNR Annapolis Parks and Rec DOEE DE DNREC DC Dept. of Transportation/Urban Forestry | PA MD DC DE VA | Fall 2017 | EPA - Diversity Coordinator serving on Committee Advisory Board
1.5 Contribute to EPA's Environmental Justice in Action Blog and use it as a resource. | 1.5.A. Contribute to EPA's Environmental Justice in Action Blog and use it as a resource. | https://blog.epa.gov/blog/category/environmental_justice/ | Bay Jurisdictions (PA, MD, DC, DE, VA) | Summer 2016 | No Action Yet
MANAGEMENT APPROACH 2: EMPLOYMENT AND PROFESSIONAL ENGAGEMENT
Key Acton | Performance Target | Participating Entity | Geographic Location | Estimated Completion Date | Current Status
2.1 Designate a diversity engagement coordinator to engage underrepresented communities and historically black colleges and universities in the watershed | 2.1.A. Each Jurisdiction and the Bay Program to explore opportunities to hire new Diversity coordinator or explore reallocation of existing staff time to strengthen Diversity coordination amongst the Partnership | Diversity Workgroup, MD-DNR, DOEE, EPA, DE-DNREC | Bay Jurisdictions (PA, MD, DC, DE, VA) | Spring/Summer 2016 Or Winter 2017 | 1. DE-DNREC - Office of Community Services and Division of Watershed Stewardship reallocation of staff time for increased communication and outreach 1. 2. DE-DNREC - Obtained funding for Summer Community Engagement Intern 4/6/16. Student withdrew to take another offer. Pursuing Univ of Delaware candidates during Fall semester through Delaware Environmental Institute (DENIN) Internship. 3. NOAA is working on this key action primarily within the Choptank Habitat Focus Area. Preparing to conduct a Choptank watershed-wide community assessment to better understand values and perspectives of communities as related to restoration. Also planning to hold focus groups with various community sectors to better understand their concerns/issues/values, and to identify community leaders. These actions are anticipated to be complete by spring 2017.
2.2 Host a pilot environmental Career Event | 2.2.A. Explore eveloping a hard copy and digital fact sheet that details career application services and offer technical assistance to those applying for jobs | Diversity Workgroup, MD DNR, National Aquarium, ACB, Community Colleges and Universities CSOSA | Bay Jurisdictions (PA, MD, DC, DE, VA) | Fall 2016 | Started - MD has met to discuss options, no offical action made to date. No actions received from other jurisdications
2.3 Connect and work with existing career service programs for job applicants | 2.3.A Each Jurisdiction and the Bay Program to explore opportunities to hire new Diversity coordinator or explore reallocation of existing staff time to stregnthen Diversity coordination amongst the Partnership | Diversity Workgroup, MD-DNR, DOEE, EPA, DE-DNREC | Bay Jurisdictions (PA, MD, DC, DE, VA) | Summer 2016 | No Action Yet - EPA/CBP/DC - DOEE/ MD has met to discuss options
2.4. Identify opportunities to create a compensated internship program specifically for individuals from diverse backgrounds working with high schools, universities and community colleges. | 2.4.A. Participation in Audubon Naturalist Society job fair in MD | Diversity Workgroup, EPA, USFS, MD-DNR, DOEE, CRC, Audubon Naturalist Society, People for Change Coalition, Private Vendors | MD | Ongoing | Complete
| 2.4.B. Enhance recruitment/outreach strategies of existing internship program to increase diverse applicant pool. | EPA, DAT, DE-DNREC, NOAA. MD-DNR, USFS, Choose Clean Water Coalition, CRC, Community Colleges and career Service departments | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing | Started - 1. MD has drafted interneship opportunities for the Department of Natural Resources, yet has not been made public. 2. NOAA plans to increase / target historically minority schools within the Chesapeake watershed for intern position announcements in 2017 such as: MD: Bowie State, Coppin State, Morgan State, UMD Eastern Shore DE: DE State VA: Norfolk State, VA State, Hampton U., VA Union U., VA U of Lynchburg DC: U. of DC, Howard PA: Lincoln U.
| 2.4.C. Evaluate models that have been tested throughout the watershed that increase green job/career training opportunities | EPA, Diversity Workgroup, DE-DNREC, NOAA. MD-DNR, USFS, Choose Clean Water Coalition, CRC, Community Colleges and career Service departments | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing | NOAA will plan to explore for our interns in 2017.
| 2.4.D. Choose and implement model to begin connecting interns with in‐demand employment opportunities | EPA, Diversity Workgroups, DE-DNREC, NOAA. MD-DNR, USFS, Choose Clean Water Coalition, CRC, Community Colleges and career Service departments | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing | Started - 1. MD has met to discuss options, no offical action made to date. 2. DE- DNREC - Division of Parks and Recreation Americorp Program interns and volunteers. NOAA will plan to explore for our interns in 2017.
2.5. Increase outreach to diverse groups for hiring full time employees | 2.5.A. Enhance recruitment/outreach strategies of existing hiring programs and explore options to reduce the amount of uncompetitive internal hiring in order to increase diverse applicant pool (e.g. environment and related career fairs) | EPA, Diversity Workgroup, DOEE, NOAA, MD-DNR, USFS, Interfaith Partners Chesapeake | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing | Started - Coordinating with Communications department All of NOAA Chesapeake Bay Office vacancies are announced publicly/competitively. NOAA will explore whether we can improve / increase outreach to and encourage applications by diverse candidates in 2017.
| 2.5.B. Reevaluate hiring practices that may inadvertently make it difficult for a diverse group of applicants to obtain jobs | EPA, MD-DNR, NOAA, ACB | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing | All of NOAA Chesapeake Bay Office vacancies are announced publicly/competitively. NOAA will explore whether we can improve / increase outreach to and encourage applications by diverse candidates in 2017.
2.6. Explore diversity and inclusion workplace training opportunities and resources for state agencies | 2.6.A MD-DNR adding a internship | MD-DNR | MD | Ongoing | Started
2.7. Explore diversity and inclusion workplace training opportunities and resources for state agencies |  | Diversity Workgroup, MD-DNR, National Aquarium, ACB, Community Colleges/Univ., CSOSA | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing | DE-DNREC - 10/2016 Executive Branch initiated comprehensive review of state of DE Diversity and iInclusion efforts. The purpose of the assessment is to develop recommendations for a more inclusive environment. 3/16/2016 DNREC Office of Community Services Title VI Plan submitted to EPA Office of Civil Rights Compliance for review. Implementation anticipated in 2017, will require all existing DNREC employees to obtain Title VI non-discrimination training certification
MANAGEMENT APPRPROACH 3: INTEGRATING AND PROMOTING ENVIRONMENTAL JUSTICE
Key Acton | Performance Target | Participating Entity | Geographic Location | Estimated Completion Date | Current Status
3.1. EPA jurisdictions and federal agencies will use EJSCREEN and other informational tools and databases in 2015 to offer additional information and perspective that could enhance partners' understanding of the watershed's diverse populations and to help target areas with potential for environmental justice concerns. Target communities and organizations for grant funding opportunities. Add new data layer to EJSCREEN for the Bay Program Watershed Model. | 3.1.A. EPA to provide training and presentations on use of EJSCREEN to GITs, CBP Workgroups and partners | EPA, MD DNR, Federal Agencies and Bay Jurisdictions (DE, DC, MD, PA, VA) | Bay Jurisdictions (PA, MD, DC, DE, VA) | 2016 | Started - 1. Provided to CBP Coordinators, Staffers, and selected GITs 2. Presented at Climate Resiliency Workgroup meeting Sept. 19 DE-DNREC - Office of Community Services Community Engagement Intern will utilize EJ Screen to identify diverse populations within the watershed for outreach and targeting to address EJ concerns and receive information about agency funding opportunities
| 3.1.B. EPA to include discussion of EJSCREEN in FY2016 CBP Grant Guidance | EPA |  | 2016 | Completed - 2016
| 3.1.C. CBP to add EJ SCREEN as a data layer for the Watershed Model | EPA, CBPO | Entire watershed | 2016 | Ongoing - Initial Screening for 8 priority outcomes completed in Nov. 15(EPA) DE-DNREC - Work is underway to enhance downtown water access and recreational opportunities in Laurel, DE, which has a significant Hispanic population.
3.2. Bay Program jurisdictions and Bay Program partners will evaluate and improve transparency and efficiency in providing community-based grant opportunities and will work with partner funding organizations, to develop a guide to assist groups in grant competition awareness, selection criteria, accountability, capacity building and grant writing training, etc., for areas with diverse and underrepresented populations. | 3.2.A. Diversity workgroup will work with the public access and climate resiliency teams to help identify potential sites in diverse communities | Diversity Workgroup | Bay Jurisdictions (PA, MD, DC, DE, VA) | 2016 | Started - Received funding for GIT Project in Sept. 2016 for public access, climate and toxics.
| 3.2.B. Jurisdictions review and revise their respective grant guidance documents as needed. |  | Bay Jurisdictions (PA, MD, DC, DE, VA) | Fall 2016 | EPA: Annually update RFP Guidance to promote projects/programs that increase diversity
| 3.2.C. Federal agencies review and revise their grant guidance documents as needed | EPA, USFS, DOEE, MD-DNR, GIT 6, NPS, Federal Agencies and Bay Jurisdictions (DE, DC, MD, PA, VA) |  |  | Jurisdictions? Federal Agencies?
| 3.2.D. Other partners review and revise their grant guidance documents as needed | EPA, USFS, DOEE, MD-DNR, GIT 6, NPS, Federal Agencies and Bay Jurisdictions (DE, DC, MD, PA, VA) | Bay Jurisdictions (PA, MD, DC, DE, VA) | Fall 2016 | Partners?
3.3. Work with local governments in the watershed to explore how the Bay Program can inform or help local decision makers maximize benefits and minimize adverse impacts from restoration project planning, siting and funding processes. | 3.3.A. EPA to review as part of revision of 2016 CBP Grant Guidance. | EPA, USFS, DOEE, MD-DNR, GIT 6, NPS, Federal Agencies and Bay Jurisdictions |  | Fall 2016 | Completed - Revised 2016 Grant Guidance
3.4. Increase collaboration with environmental justice entities throughout the Bay Watershed and incorporate their perspectives and those of community and faith-based organizations and leaders throughout the Bay Program governance structure, including its three advisory committees (citizens, local governments and scientific/technical. | 3.4.A. Diversity workgroup to work with LGAC and Local Leadership Team to explore opportunities to work with local leaders on these issues. | Diversity Workgroup, LGAC, MD-DNR & Local leadership team | Bay Jurisdictions (PA, MD, DC, DE, VA) | 2016 | Ongoing - Choose Clean Water Coalition Meeting - Sept 2016, Diversity Workgroup Meeting November 2016.
| 3.4.B. Diversity workgroup to work with community leaders to engage them in MB, PSC, CBP GITs and workgroups as active contributing members | Diversity Workgroup, GIT, MD-DNR, CAC, LGAC, STAC, Choose Clean Water Coalition | Bay Jurisdictions (PA, MD, DC, DE, VA) | 2016 | Ongoing - Reverend Calhoun and READY works program - Summer 2016
| 3.4.C. Identify key EJ groups in the jurisdictions and invite their involvement in CBP teams and workgroups | Diversity Workgroup, GIT MD DNR CAC LGAC STAC Choose Clean Water | Bay Jurisdictions (PA, MD, DC, DE, VA) | 2016 | Started - Groups identified from existing networks, listserves and identifying new groups
| 3.4.D. Reach out to existing groups such as those identified in the management strategy and additional ones like WE ACT for Environmental Justice, Blackbelt EJ Center and others | Diversity Workgroup, GITs, MD-DNR, CAC, LGAC, STAC, Choose Clean Water Coalition | Bay Jurisdictions (PA, MD, DC, DE, VA) | 2016 | No Action yet - 2017
| 3.4.E. Diversity workgroup will consult with National Fish and Wildlife Foundation’s Technical Capacity Program | EPA |  | Winter 2016 | Started - To be completed by EPA - Fall 2016
| 3.4.F. EPA, jurisdictions and Federal agencies will review and revise their RFP email lists to ensure that grant opportunities are being distributed to broad and diverse constituencies. Examples, HOA’s, community centers, rec centers, etc | EPA, NPS |  | Ongoing | Ongoing - EPA has reviewed and updated list Spring 2016 // Will now update annually when grant guidance is updated
| 3.4.G. Reach out to existing EJ groups across the watershed | Diversity Workgroup | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing
MANAGEMENT APPROACH 4: Tracking and Assessment of Diversity
Key Acton | Performance Target | Participating Entity | Geographic Location | Estimated Completion Date | Current Status
4.1. Use EPA's EJ screening tool as a base for identifying stressed or under-served Chesapeake communities | 4.1.A. Create a map that overlays data sets such as; demographic, environmental, subwatersheds, proximity to partner organizations, environmental justice groups, community service groups, etc | Diversity workgroup, EPA, CBP | Bay Jurisdictions (PA, MD, DC, DE, VA) | Spring 2016 | Started - GIT Layer Mapping project underway.
4.2. Use EPA's EJ screening tool as a base for identifying stressed or under-served Chesapeake communities | 4.2,A Encourage CBP partners to use EJ SCREEN tool and track its usage | Diversity Workgroup, EPA, CBP | Bay Jurisdictions (PA, MD, DC, DE, VA) | Spring 2016 | Ongoing
4.3. Establish a baseline of the level of diversity (staff, boards, programs and initiatives aimed at increasing internal diversity) | 4.3.A. Use a diversity demographic profile indicator for the Chesapeake Bay Program. In 2017 explore collecting diversity data of Chesapeake Bay Program Partner organizations | Diversity Workgroup, Bay Jurisdictions (DE, DC, MD PA, VA), Choose Clean Water Co., ACB, MD-DNR | Bay Jurisdictions (PA, MD, DC, DE, VA) | Summer 2016 | Completed - August 2016 - 374 respondents. Meeting with Green 2.0 completed in Summer 2016.
| 4.3.B. Analyze demographic profile results an develop a diversity basseline snf nre indecator by December 2016 | EPA | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing | Ongoing
4.4. Establish a baseline of the level of diversity (staff, boards, programs and initiatives aimed at increasing internal diversity) | 4.4.A. Develop method of tracking anecdotal and qualitative metrics of Strategy implementation |  | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing | No Action yet
| 4.4.B. Survey Partners on existing diversity programs that aim to increase diversity and inclusion in (employment, volunteerism, programs, etc |  | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing | No Action yet
4.5. Increase the Bay Program stakeholder base by tracking new partnerships that help to better identify and target underrepresented and underserved Chesapeake communities to engage partnership efforts. | 4.5.A. Identify community groups that may be candidates for environmental restoration projects and programs | Diversity Workgroup, CBP, Communications Workgroup, EPA, USFS, MD-DNR, Federal Agencies, State Agencies | Bay Jurisdictions (PA, MD, DC, DE, VA) | Summer 2016 | Ongoing
| 4.5.B. Identify and approach organizations and groups that work within diverse Chesapeake communities | Diversity Workgroup, CBP, Communications Workgroup, EPA, USFS, MD-DNR, Federal Agencies, State Agencies | Bay Jurisdictions (PA, MD, DC, DE, VA) | Summer 2016 | Ongoing
| 4.5.C. Identify community groups that may be candidates for environmental restoration projects and programs | Diversity Workgroup, Bay Jurisdictions ( DE, DC, MD, PA, VA), Choose Clean Water Co., ACB, MD-DNR | Bay Jurisdictions (PA, MD, DC, DE, VA) | Summer 2016 | Started - MD working with several communities on Eastern Shore identified as underserved on SW projects
4.6. Collect and evaluate existing diversity programs and develop a strategy for improvement | 4.6.A. Continue to develop existing baseline matrix and highlighting current gaps within the Partnership | Diversity Workgroup | Bay Jurisdictions (PA, MD, DC, DE, VA) | Ongoing | Started - Further analysis of Profile data baseline -Winter 2016
| 4.6.B. Examine EPA’s diversity dashboard to determine if it can serve as a model for Bay Partners | Diversity Workgroup, PA, MD, DC, VA, DE, Choose Clean Water Co., ACB, MD-DNR | Watershed | Spring 2016 | Started - In Progress after completion of diversity profiles