## MD P&P
| Key Action | Performance Target(s) | Partners Responsible | Status (December 2016) | Status (December 2017)
Management Approach 1: Regulatory Approaches | 1. Continue jurisdictional monitoring programs for PCB occurrence to assess need for new local TMDLs and progress related to reducing PCB loads. | Conduct a PCB monitoring survey on pre and post-ENR WWTPs in Maryland to determine if there is an increase in removal effciency from the ENR treatment technology. Conduct a second round of sampling on the two plants that are pre-ENR once the upgrade goes online. | MDE | Three sample collections (24 influent and effluent samples) have been conducted at four WWTPs in MD (Back River, Cox Creek, Mattawoman, and Elkton). A fourth sample collection will be conducted at Back River and Cox Creek WWTPs (8 influent and effluent samples) once the facilities' ENR processes come online, which is anticipated by the end of the year. Next Steps: The samples are being analyzed by Texas A&M using EPA method 1668. A final data report is expected Spring 2017. | The final round of sampling remains on hold as the Back River and Cox Creek WWTPs ENR treamtment processes's have not been completed. The contract has been extended through Dec 2018.
|  | Conduct an analysis of Bay-wide PCB concentration data to improve our understanding of PCB dynamics through-out the Bay mainstem and the influence of loadings from the Susquehanna River and C&D Canal. The project will also focus on approaches for developing a PCB TMDL to address the main stem segment listing in MD's portion of the Bay. | MDE and VIMs | MDE has contracted VIMS to conduct the analysis. The study is currently underway and will be completed by December 2017. | The study has been completed and a draft report is currently undergoing review. It is anticipated that the report will be available March 2018.
|  | Continue annual PCB fish tissue monitoring for MDE’s Fish Consumption Advisory Program to assign state-wide fish consumption advisories. The program also provides fish tissue data for MDE’s Environmental Assessments and Standards (EASP) and TMDL Programs to support Integrated Report listing assessment and TMDL development. | MDE | Fish tissue sampling was conducted in 2016 at 18 stations (72 composites) to support the consumption advisory program, IR assessment and TMDL development needs. Fish composite samples are being analyzed by UMBC for PCBs, Hg, and chlordane. Several species of fish were collected including white perch, channel catfish, and largemouth bass. It is anticipated the data results will be available Winter 2017 | Toxics data for fish tissue collected in 2016 will be available early 2018. Fish tissues sampling was conducted in 2017 at 25 stations (56 composites) to support the consumption advisory program, IR assessment and TMDL development needs. Fish composite samples are being analyzed by UMBC and UMCES CBL for PCBs, Hg, and chlordane. It is anticipated the data results will be available Winter 2018.
| 2. Continue local TMDL implementation utilizing to the extent possible the outputs of this strategy including data compilations, results of enhanced monitoring, guidance documents and local-level input | Phase 1 MS4’s which have been assigned a WLA within a PCB TMDL requiring a PCB load reduction are required to develop a PCB Implementation Plan within one year of an approved TMDL. | MD MS4s | MD SHA has submitted a PCB stormwater implementation plan to address their MS4 WLA in all currently approved PCB TMDLs. The plan is currently undergoing MDE review. SHA MS4 WLAs have been assigned in various PCB TMDLs including Back River, Baltimore Harbor, and Anacostia River. | Phase 1 MS4 Implmentation plans were developed by Anne Arundel County for the Baltimore Harbor, Baltimore County for the Bird/Gunpowder River, and Harford County for the Bush River in 2016/2017. Counties that have submitted plans are currently developing monitoring programs to support PCB TMDL implementation.

## MD Research
Key Action | Performance Target(s) | Partners | Status (Dec 2016) | Status (Dec 2017)
2. Generate further information on mercury, focused on determining whether further Chesapeake Strategies are needed to supplement national efforts to reduce its impact on fish and associated consumption advisories. | Conduct sampling of mercury in young of the year fish. Results will eventually be used to assess trends. | MDE and MD DNR |  | A report was completed in September 2016. The study did not establish a declining trend for Hg concentrations in YOY fish tissue data collected from 2008-2014. YOY fish tissue data will continue to be collected annualy. | A
| Review and obtain information documented during the establishment of Maryland’s proposed Mercury TMDL. | MDE | This action is on hold as MDE is awaiting information from an air deposition model in order to support MD’s mercury TMDL. It is anticipated that this information will not be available till the end of 2017. | MDE is still awaiting information from air deposition model. It is anticipated that this information will not be available till early 2018. Recent analysis of fish tissue data collected in 2015 has demonstrated that one of the Potomac River segments is no longer impaired for Hg. The segment will be delisted in the 2018 IR. Additional fish tissue collections are planned in 2018 to determine if the remaining waters listed for Hg are impaired. Hg TMDL development will be delayed until listing reassessment is completed.