Budget and Finance Workgroup

2016-2017 Workplan

DRAFT

Last updated: September 15, 2016

1a. Coordinate and facilitate a process for distribution of discretionary GIT Funding (starting with FY2017).

- Late 2016/Early 2017  solicit input and determine what the final role of the workgroup will be in the GIT Funding process

- Q2 2017  (placeholder) Screen for redundancies and complementary projects/proposals

2a. Coordinate partnership response to recommendations coming out of symposiums and similar forums or financial analysis reports and evaluations (e.g., 2016 Environmental Finance Symposium Report and Recommendations).

- November 30, 2016  If requested, the workgroup will draft a response to the Environmental Finance Symposium Recommendations Report (Jim Edward will Chair); this will happen within 90 days of September 1, 2016

2b. Participate in finance-related commitments in the Chesapeake Watershed Agreement (e.g., Local Leadership Outcome – “implementation of economic and policy incentives”)

- Q2/Q3 2017  Use the 2-year biennial review timeline to identify gaps in/obstacles to implementation and possibilities to fill these gaps using GIT Funding process

- Q2 2017  Solicit input from the workgroup to determine the process for working with the Chesapeake Bay Partnerships to do financing strategies; this should build upon the defined routine/schedule of the biennial review process

- Q2/Q3 2017  Facilitate small groups of private finance experts to help identify solutions to needs identified thru the biennial review

3a. Identify opportunities for including and improving funding information in other CBP products.

- June 1, 2017  Request from OMB to Federal agencies and jurisdictions for annual budget submission

- July 1, 2017  Submissions due to OMB

- September 30 (annually)  OMB report to Congress

- Summer 2018  potential revisions to CBIG/CBRAP allocation formulas

Budget and Finance Workgroup

Other/Future Topics for Consideration

DRAFT

Last Updated: September 15, 2016

- Standardization of budget data reporting templates for jurisdictional use

  - Discuss the criteria for a standard reporting template and begin drafting a recommended format.

- Potential revisions to CBIG/CBRAP allocation formulas for 2018

  - Do we have members representing all jurisdictions on the WG? Do these revisions push jurisdictions with no member to elect one?

- 2016-2017 Workplan development

  - Have we made the connection with GIT6 (between Part 2 of the workplan and the Biennial Strategy Review System?)

- Existing funding and/or financing source(s) – Master List

- Unfunded projects

  - Previous proposals put forward for GIT Funding or other $ pools

- Impact Scoring Guidelines (TetraTech)

- CBARA OMB report analysis