## Slide 1
DC Clean Rivers Project
Briefing on:
November 29, 2018
District of Columbia Water and Sewer Authority
David Gadis, General Manager
Briefing for:
Chesapeake Bay Program
Citizens Advisory Committee

## Slide 2: Agenda
DCCR Overview
DCCR Status Update
Ongoing and Future Work
Questions
Green Roof
at Fort Reno Reservoir
Anacostia River Tunnel Mining Completion
2

## Slide 3: DC Clean Rivers Project Overview
3

## Slide 4: Separate and Combined Sewer Systems
1/3 area is combined sewer (12,478 acres)
47 Combined Sewer Overflow (CSO) outfalls
4

## Slide 5: Magnitude of the Challenge: CSOs
CSO Discharge to Anacostia River
Trash in Anacostia River
Chart: CSO Overflow (mg/avg year)
| Anacostia River | Potomac River | Rock Creek | Total System
1996 | 2142 | 1063 | 49 | 3254
2017 | 1282 | 638 | 48 | 1968
2018 | 391 | 638 | 48 | 1077
LTCP Completed | 54 | 79 | 5 | 138
5

## Slide 6: Magnitude of Challenge: Surface Flooding (Summer 2012)
Rhode Island Metro
1st St NW
Flagler St NW
Rhode Island & T St NW
Rhode Island Between 1st & 2nd St NW
Rhode Island & T St NW
Rhode Island & 1st St NW
1st & V St NW
Photo courtesy of: Greg Roberts
Photo courtesy of huffintonpost.com
Photo courtesy of myfox.com
Photo courtesy of myfox.com
Photo source unknown
Photo source unknown
Photo source unknown
Photo source unknown
Photo source unknown
6

## Slide 7: What is our Purpose?
Control combined sewer overflows to the:
  Potomac River
  Anacostia River
  Rock Creek
Relieve flooding in the Northeast Boundary Area
Implemented under a Federal Consent Decree among:
  US Environmental Protection Agency (US EPA)/
  US Department of Justice (US DOJ)
  District of Columbia and
  DC Water
7

## Slide 8: Program Development
1998 - LTCP Started
2002 – Final LTCP
2005 – Consent Decree Signed
2007 - New Nitrogen Limits Require Changing LTCP
2003 – LTCP Meets WQS (EPA/DC)
2011 - DC Water Evaluates GI for Potomac River and Rock Creek
Public Participation
Public Participation
2012 – Mayor’s
Task Force
January 14, 2016 – Consent Decree Modification Entered in Federal Court
8

## Slide 9: DC Clean Rivers Project
DC Clean Rivers Project: $2.7 Billion
Nitrogen Removal: $950 Million
Total > $ 3.5 Billion
25 yr implementation (2005 – 2030)
96% reduction in CSOs & flood relief in Northeast Boundary
Approx 1 million lbs/yr nitrogen reduction predicted
DC CLEAN RIVERS PROJECT AND
NITROGEN REMOVAL PROGRAMS
9

## Slide 10: 21st Century Sewer System
23
NEW FACILITIES CONSTRUCTED TO CONTROL CSOS
10

## Slide 11: Tunnel Dewatering Pumping Station and Enhanced Clarification Facility
11

## Slide 12
12
GANTRY SYSTEM ABOVE PS AND COARSE SCREENING SHAFTS
FINE SCREENS
GRIT REMOVAL
HIGH RATE CLARIFICATION
CHLORINE CONTACT TANK
Tunnel Dewatering Pumping Station and Enhanced Clarification Facility
12

## Slide 13: What is Green Infrastructure?
Mimics natural water processes:
  Filtration, infiltration, slowing water, storage, and evapotranspiration
  Reduces CSOs by slowly releasing stormwater to the sewer system
Rain Gardens and Bioretention
Downspout Disconnection and Rain Barrels
Green Roofs
Pervious Pavement
13

## Slide 14: GI Technologies – Public Space
Permeable Alley
Sidewalk
Storage
Permeable
Parking Lane
Parking Lane
Storage
Curb Extension
Bioretention
Planter
Bioretention
Crosswalk Storage
Sewer
Separation
Siting and Design Goals:
Minimize temporary and long-term impacts to community
Match character and aesthetic of neighborhoods
Provide infrastructure upgrades by prioritizing areas for implementation
Provide ancillary benefits to community
Coordinate work with other entities (DDOT, other utilities, etc.)
14

## Slide 15: DC Clean Rivers Project Status Update
16

## Slide 16: Project Status
First Street Tunnel
Chart: CSO Overflow (mg/avg year)
| Anacostia River | Potomac River | Rock Creek | Total System
1996 | 2142 | 1063 | 49 | 3254
2017 | 1282 | 638 | 48 | 1968
2018 | 391 | 638 | 48 | 1077
LTCP Completed | 54 | 79 | 5 | 138
Legend
In operation
Planning, design or construction
Blue Plains and Anacostia River Tunnels
Tunnel Dewatering Pumping Station and 225 mgd Wet Weather Treatment facility
Northeast Boundary Tunnel (under construction)
Potomac Tunnel
Green Infrastructure for CSO 049
(Piney Branch)
Green Infrastructure for CSO 027, 028, 029
Separate CSO 025, 026
17

## Slide 17: Anacostia River Tunnel System Performance
Trash and debris removed from CSO captured by tunnel at ECF Fine Screens
November 20 marked 8 months in service
Exceeding predicted capture rate (90%>80%)
Volumes are high due to extremely rainy weather
  6th wettest May on record
  4th wettest July on record (all rain in second half of month)
  5th wettest September on record
  Wettest November on record (broke record from 1877)
<1” from wettest year on record (1889)
April 2018
November 2018
No. | Month | Rainfall, DCA Gauge (in) | Volume Captured by Tunnel (MG) | Measured Overflow (MG) | % captured | Solids Removed (tons)
1 | March 20 -31 2018 | 1.48 | 20 | 0 | 100% | 0
2 | April 2018 | 3.59 | 249 | 10 | 96% | 8
3 | May 2018 | 8.73 | 865 | 13 | 99% | 73
4 | June 2018 | 5.21 | 271 | 49 | 85% | 55
5 | July 2018 | 9.73 | 678 | 236 | 74% | 11
6 | August 2018 | 5.19 | 334 | 15 | 96% | 226
7 | September 2018 | 9.73 | 775 | 109 | 88% | 94
8 | October 2018 | 3.06 | 150 | 0 | 100% | 151
9 | November 1-28, 2018 | 7.56 | 780 | 6 | 99% | TBD
 | Total | 54.28 | 4122 | 438 | 90% | 616
18

## Slide 18: Dc clean rivers project ongoing and future work
19

## Slide 19
Division J – Northeast Boundary Tunnel
111111111111111111111111111
Work is ongoing at the following locations:
CSO 19
Mt. Olivet Road
W Street
Rhode Island Ave
4th Street
TBM Machine is actively mining (Ring no 33 as of Nov 27, 2018) from CSO 19.
Mobilize to Florida Ave and Pumping Station site in late Dec 2018.
Milestone | Date
NTP | September 15, 2017
Construction Start | March 2018
Construction Complete | August 2023
Key Map
20

## Slide 20: Northeast Boundary TBM Naming Ceremony
21

## Slide 21: Division J – Northeast Boundary Tunnel
TBM Lowering
444444444444444444
4th Street Pre-trench Excavation for Drop Shaft
22

## Slide 22: Division RC-A – Rock Creek GI Project A
Project Boundary:
Key Map
Kansas Ave.
New Hampshire Ave.
Missouri Ave.
Project facilities were designed, permitted, and constructed in three phases:
Construction started in September 2017
Substantial Completion achieved October 9, 2018
23

## Slide 23: Division PR-A – Potomac River Project A
11111111111111111111111111
Project Boundary:
Key Map
Construction underway and tracking for on time completion.
Project includes:
  Planter Bioretention
  Alley Permeable Pavement
  Parking Lane Permeable Pavement
Item | Status
Contract Award | April 9, 2018
Construction NTP | April 30, 2018
Place in Operation | CD Deadline June 23, 2019
24

## Slide 24: Potomac River Tunnel
11111111111111111111111111
Tunnel connections for CSOs 027-029 contingent on Green Infrastructure practicability determination
Schedule Facility Planning/
Environmental Approvals: 2015-2018
Preliminary Design: 2019-2022
Procurement: 2022-2023
Final Design/Construction: 2023-2030
25

## Slide 25: CSO 025 and 026 Sewer Separation
11111111111111111111111111
Separation of combined sewer system tributary to two Potomac River outfalls
Small, highly urbanized sewersheds in Georgetown Historic District
Construction contract to be awarded by March 2021
Placed in operation by March 2023
26

## Slide 26
Questions and Answers
Brandon Flora, PE
brandon.flora@dcwater.com
202-787-4414

## Slide 27: Blue Plains Nitrogen Removal
Blue Plains has consistently exceeded nitrogen removal requirements set by Chesapeake Bay Program and NPDES Permit