## Sheet1
GIT | GIT Needs from STAR | Timeline | Completed Y/N | Timeline | STAR workgroup; primary science provider
Items from 2016-17
Green: completed. Yellow: ongoing, to be continued, Red: not started; new needs listed at bottom of table
WIP Outcome
Water Quality Outcomes | Provide support to develop WIPs | 2017 | apply tools | 2018-19 | Modeling WG, ITAT
| Develop land cover dataset | 2016-17 | Y | every 2-4 years | Land Cover WG: GIS Grantee; USGS
| Enhance watershed and SPARROW model |  | Y |  | Modeling WG: CBP modeling team
| Examine Susquehanna reservoirs' impact on N and sed transport |  | Y, ongoing | 2018-19 | Modeling WG; CBP modeling team
| Assess N and sed response to management practices |  | Ongoing | 2018-19 | ITAT/Modeling WG
| Incorporate BMP efficiencies and land cover/use | Oct. 2015 - October 2016 | Y |  | Modeling WG; CBP modeling team
| Conduct STAC peer reviews | Winter/Spring 2016 | Y |  | Modeling WG; STAC
| Use WQ data to assess PA's progress | 2017 | Ongoing | 2018-19 | Modeling WG
| Run scenarios and modeling tools | January 2016 - September 2016 | Ongoing | 2018-19 | Modeling WG: CBP modeling team
| Co-benefits of nutrient and sediment practices (ranking, fact sheets) | 2017 | Completed; fact sheets being finalized
Attainment and Monitoring Outcome
| Update nontidal nutrient and sediment Loads and Trends (all sites) | every two years | Y | 2018 and beyond | ITAT: USGS
| Update River-input loads and trends to Bay | Annually | Y | 2018 and beyond | ITAT/USGS, MD DNR, VA DEQ
| expand on BEI report for add'l monitoring needs | 2016-2017 | Will use this process
| Incorporate Citizen Science Monitoring for WQ standards (publication through Citizen Science Association journal) |  | In progress |  | Criteria Assessment Protocol WG; CBP monitoring team
Approve Nontraditional Partner/Cit sci data MOU
| develop targeted shallow water monitoring strategy |  | IN progress |  | Integrated Monitoring Networks WG
| Factors affecting loads and trends at the River Input Stations | 2016-2017 | In progress, 2018 |  | ITAT; USGS
| Explaining nutrient loads and trends in the watershed | 2016-2017 | Synthesis report, 2018 |  | ITAT; USGS
| Overview of sediment sources and changes in the watershed |  | Synthesis report, 2018 |  | ITAT; USGS
| Improve knowledge of sed and N sources; USGS |  | Synthesis report, 2018 |  | ITAT
| WQ functions of wetlands |  | In progress |  | Expert panel
| Improve understanding of tidal water response to load changes |  | Synthesis report, 2018 |  | ITAT: UMCES
Policy and Prevention Outcome: PCBs
Toxic Contamiants Outcomes | PCB trends in fish, water, sediment, air | 2017 | in progress | 2018-19 | TCW; states
| Update toxic contaminant indicator | 2017 | Completed | every 2 years | TCW; Status and Trends
| PCB Source tracking (need to complete guidance document) | 2017 | in progress |  | TCW;
| PCB Story Map | 2017 | being finalized |  | TCW
|  | 2017 | being finalized |  | TCW
Research Outcome
| Summarize mercury information to consider for policy | 2017 | not attempted | 2018-19 | TCW
| Effects of contaminants on fish and wildlife (EDC study) | 2017 | Ongoing | 2018-19 | TCW; USGS, FWS,
| Sources, Occurance, and distribution of contaminants (EDC study) | 2017 | Ongoing | 2018-19 | TCW; USGS, States
| Relative Risk of Contaminants (develop approach) | 2017 | not attempted | 2018-19 | TCW; EPA, USGS
| Relative Risk: BMP analysis for multiple outcomes | 2017 | Completed |  | WWQ GIT; GIT funding
| Relative Risk of Contaminants: co-benefits fact sheet | 2017 | being finalized |  | TCW
| Relative Risk: Urban and Agricutural settings (existing info reports) | 2016 | Completed |  | TCW; GIT Funding
| Relative Risk: Contaminants in Agricutural settings | 2017 | upcoming | 2018-19 | TCW: STAC
New Needs suggested by States and TCW leaders
A& M outcome | Shorter Term DO Criteria Assessments (MD)
A& M outcome | Using CONMON and Dataflow data for assessing standards attainment.(MD)
WIP outcome | Improved mapping of Soil Phosphorus (PA)
WIP outcome | Improvement of manure quality data that supports accurate characterization of manure loads, additionally how these loads are impacted by nutrient management approaches. (PA)
WIP outcome | Refined BMP efficiencies - N, P, and TSS (MD) |  |  |  | New GIS RFP?
WIP outcome | Routine updates to high resolution land-cover (MD) |  |  |  | New GIS RFP?
WIP outcome | Improved estimates of streambank/bed sediment loads and floodplain deposition (co-benefit for stream health also)
WIP outcome | Relation between nutrient/sediment reductions and stream condition (co-benefit for steam health also)
WIP outcome | Better understanding of the causation for reaches where bank/bed erosion is a source of sediment (co-benefit for steam health also)
WIP outcome | Effects of climate change on amounts of nutrients & sediment (PSC)
WIP outcome | Optimization of BMPs and addressing co-benefits (WQ GIT)
Toxic PCBs | Evaluate Stormwater BMP PCB Removal Effectiveness (MD)
Toxic PCBs | Multiple-state modeling for PCBs (TCW); Ex: lower susq/upper bay
Toxic PCBs | Science support for targeting sources
Toxic PCBs | More quantative data on co-benefits of nutrient and sediment reduction
Toxic Research | Improve knowledge of EDC impact on aquatic life
Toxic Research | Approaches for developing co-benefits between nutreient and sediment BMP estimates and multiple toxic contaminants
Toxic Research | Toxic contamiant in urban areas (summaries and implicaitons)
Forest Buffer Outcome
Need to be developed
Note on B6: CRCStaffers: Develop a new land-cover data set for the CBP watershed model.
Note on D6: Williams, Michelle: 1-meter land cover dataset developed for inclusion in Phase 6 Watershed Model prior to model release in 2017
Note on B7: CRCStaffers: Enhance the CBP watershed model using USGS measured loads for calibration as well as SPARROW model, groundwater models and other science findings.
Note on D7: Williams, Michelle: SPARROW incorporated into Phase 6 Watershed Model as part of multiple modeling approach
Note on B8: CRCStaffers: Examine the impact of Susquehanna reservoirs on changes in nutrient and sediment transport to Chesapeake Bay.
Note on D8: Williams, Michelle: Lower Susquehanna Watershed Assessment Report released march 2016 (USACE)
Note on B9: CRCStaffers: Better utilize monitoring data to assess progress and explain observed changes in nutrients and sediment in response to management practices.
Note on B10: CRCStaffers: Incorporate data inputs, such as BMP efficiencies and land use/land cover
Note on D10: Williams, Michelle: Incorporated into Phas 6 Watershed Model/CAST
Note on B11: CRCStaffers: Regarding MA3 KA4. Release beta and final version of the Phase 6 Watershed Model
Note on D11: Williams, Michelle: Done in December 2016
Note on B12: CRCStaffers: Utilize empirical, historical and current water quality data to assess Pennsylvania's progress towards meeting goals.
Note on B13: CRCStaffers: Regarding MA3 KA4. Release beta and final version of the Phase 6 Watershed Model
Note on D13: Williams, Michelle: Key scenarios (No action, E3, Phase II WIPs, and progress runs done)
Note on B16: CRCStaffers: The USGS will work with the partners to compile quality assure the information to update loads and trends.
Note on D16: Williams, Michelle: final presentation from Doug Moyer at 2/12/18 WQGIT conference call
Note on B17: CRCStaffers: USGS will completely update the reporting of loads to the Bay and trends of nutrients and sediment loads in the watershed; revised products will be prepared to communicate these results.
Note on B18: CRCStaffers: Expand upon the water quality-focused Building Environmental Intelligence report to a new process to address additional monitoring needs associated with the 2014 Chesapeake Bay Agreement. Integrate the role of Citizen Science to address gaps in water quality-related monitoring and assessment needs. Work with partners and Management Board to consider and attempt to implement recommendations.
Note on B19: CRCStaffers: Coordinate and integrate Citizens Monitoring effort funded by the Chesapeake Bay Program. Develop high quality citizens monitoring programs to assess water quality standards. Target areas where implementation will potentially show progress.
Note on D19: Williams, Michelle: Project update from Chesapeake Monitoring Network at 10/23/17 WQGIT conference call
Note on B21: CRCStaffers: Develop strategy to target shallow water monitoring program with limited resources. Incorporate all spatially and temporally intensive monitoring results into Bay water quality standards attainment.
Note on B22: CRCStaffers: Test watershed factors influencing water-quality trends in tidal waters.
Note on B23: CRCStaffers: Release of a report and communication products regarding nitrogen sources and transport processes in smaller agricultural and urban watersheds.
Note on B24: CRCStaffers: Compare observed and expected trends in the watershed and relation to management actions.
Note on B25: CRCStaffers: Improve knowledge of sediment and nitrogen sources and residence times.
Note on B26: CRCStaffers: Utilize empirical, historical and current water quality data to assess Pennsylvania's progress towards meeting goals.
Note on B27: CRCStaffers: Improve knowledge of the water-quality functions of created and restored nontidal wetlands.
Note on B28: CRCStaffers: Support efforts to improve the understanding of tidal water response to changes in watershed loads.
Note on B36: CRCStaffers: Coordinate and integrate Citizens Monitoring effort funded by the Chesapeake Bay Program. Develop high quality citizens monitoring programs to assess water quality standards. Target areas where implementation will potentially show progress.