## Stewards.
High Level Summary of Comments 1. Lacks detail and needs to include more specific and targeted actions 2. Needs more emphasis on cross-outcome collaboration 3. Edit the document for clarity and readability 4. Seek input from local officials before developing the workplan
For CBP Use Only
Comment # | Category / Management Strategy | Management Strategy Section | Comment | Source | Date Comment Submitted | Date Received by Goal Team(s) | Team(s) Considering Comment | Goal Team Response or Resolution | Date of Goal Team Response
5.ST.LL.1 | Local Leadership |  | While there are improvements since the first draft, the local leadership strategy is perhaps the least developed of all the strategies. It documents the challenges and gaps to achieve the goal to “Continually increase the knowledge and capacity of local officials on issues related to water resources and in the implementation of economic and policy incentives that will support local conservation actions.” The strategy notes that “specific suggestions will be considered during development of the workplan, which will be completed by the end of 2015.” This makes it difficult to comment on the management strategy. | Charlie Stek, CAC | 2015-05-01 | 2015-05-11 | GIT 6 | Thank you for your comment. We plan to provide specific detail in the workplan. | 2015-05-22
5.ST.LL.2 | Local Leadership |  | Clearly it is a challenge to continually increase the knowledge of some 1800 units of local government and the 10s if not 100s of thousands of local elected and appointed officials and their senior staffs. Perhaps one way to start is narrow the numbers by identifying those local jurisdictions in the watershed which encompass waters which contribute the largest sources of pollution to a river or stream which flows into the Chesapeake and targeting those leaders initially for awareness building, outreach and education utilizing existing non-profits or state programs with education capacities. | Charlie Stek, CAC |  | 2015-05-11 | GIT 6 | We will address the need to target our efforts toward the areas of greatest need and impact in the workplan. | 2015-05-22
5.ST.LL.3 | Local Leadership |  | • The Strategy should still try to focus more on rivers and local waters and less on the Bay. Most local officials will connect better to local waters than to the Bay. The strategy can be strengthened to better make those connections. • We commend the inclusion of using outdoor field trips, boat trips and/or farm trips for local decisions makers to help increase knowledge and change perspectives. We hope the workplan will stress a more systematic approach. • It is good to see the mention of using existing local government forums as a way to deliver the messages. We encourage the inclusion of more concrete steps on delivering the message using existing local government associations and existing leadership programs into the workplan. • We still believe the strategy should include Land Use related workgroups in the cross-goal collaboration. | Charlie Stek, CAC | 2015-05-01 | 2015-05-11 | GIT 6 | These comments will be considered during workplan development. The Land Use Outcomes are included in the cross-collaboration section. | 2015-05-22
5.ST.LL.4 | Local Leadership |  | p. 3, Local Engagement paragraph: "The nature of this outcome and resulting strategy is the building of knowledge and capacity of local officials; hence there is a specific, critical role for local government officials and associated local leaders. Additionally, watershed associations, nongovernmental organizations and other local community and other under-represented groups play a critical role in reaching local officials and building this constituency for conservation action." p. 4, #2, Factors Influencing: "Effective messaging and public relations community conscious-raising activities defined as accurate measurement and clear communication of positive changes in the watershed from natural resource, economic, and cultural perspectives." p. 4, #3, "Size, geography and civic and political complexity of the watershed which creates distinct regional needs." Comment: "insert small geographical-regional-map of Chesapeake Bay states." | Richard W. Allen, Maryland Department of Natural Resources. | 2015-04-30 | 2015-05-11 | GIT 6 | Editorial changes were made to the document based on these suggestions. A map will not be included. | 2015-05-22
5.ST.LL.5 | Local Leadership |  | P. 8, 1st paragraph, comment: "This approach seeks to pair existing leaders with diverse emerging leaders" p. 8, 3rd paragraph, comment: ""This may include expanded availability of online resources such as...a newsletter and/or database for the local official community" May want to consider a print newsletter as well. " p. 8, bullets after 3rd paragraph, comment: "Add a bullet that says, "Create partnerships with various universities to link students in environmental policy programs with elected officials for shadowing opportunities for both parties" - Increases knowledge and builds relationships. " p. 9, first bullet, "Identify and prioritize key information and information sources that may benefit local officials (e.g. economic benefits, cost benefits, multiple benefits of stormwater management like socioeconomic and community improvement for under-represented under-served populations, climate change, etc.)" Comment: "incorporate Faith communities into power-point presentations; develop key messages flashing between turnpikes/interstates of Chesapeake Bay states. " | Richard W. Allen, Maryland Department of Natural Resources. | 2015-04-30 | 2015-05-11 | GIT 6 | • "diverse" was added to this sentence • This comment will be considered for the workplan; • This is an activity more related to citizen stewardship and environmental literacy and already being executed by the Alliance for the CB. • This bullet point was edited. • This will be considered in the workplan. | 2015-05-22
5.ST.LL.6 | Local Leadership |  | p. 9, Approaches Targeted to Local Participation, comment: "What are the specific approaches? Check this successful program out: http://www.participatorybudgeting.org/" "Mention what the specific role could be of local leaders and groups here. For example, local leaders encourage more citizens to be engaged in conservation issues to influence policy decision through voting. p. 10, add to list of bullets: "Monitoring progress for who else? Include in this section the importance of making this progress available to a diversity of constituents, especially those at the community level. Access to this information by the public will prepare groups and individuals to see where they need to demand and encourage policy change, more specifically. " | Richard W. Allen, Maryland Department of Natural Resources. | 2015-04-30 | 2015-05-11 | GIT 6 | • This section was re-written. • A sentence was added to the paragraph above the list about making this progress available to a diveristy of consitituents. | 2015-05-22
5.ST.LL.7 | Local Leadership |  | Provide Robust Local Technical Assistance We recommend that federal and state agencies provide technical assistance and resources to localities and better approach local businesses when pursuing public water access projects. Local governments are key decision makers in access site development and they are motivated by projects that can demonstrate a strong economic impact. Local business involvement is essential, and agencies should share models of success within the Chesapeake watershed that can be replicated and build momentum in emerging communities. Federal and state agencies should also provide local communities resources on managing conflicts among users—which too often prevent access sites from being built or opened to the public. Local governments and partners should be provided a toolkit and resources on public access development, including a guide for working with neighbors and landowners that addresses issues including liability, maintenance, and stewardship. A model of success that can be replicated throughout the region is the Anne Arundel Public Water Access Committee in Maryland, which is comprised of recreationists and business owners. This committee advises the Anne Arundel County Department of Parks and Recreation on access site development while building broader community support. | Edward Stierli | 2015-04-30 | 2015-05-11 | GIT 6 | Some of these points will assist our development of the workplan, such as tool kits for conflict resolution. Since many of the points made are directly related to publci access, we feel this comment was likely directed toward the Public Access management strategy . | 2015-05-22
5.ST.LL.8 | Local Leadership |  | COG region is recognized by the EPA and states for its leadership to improve water quality and contribute to the Bay Restoration efforts (e.g., through the use of state of the art wastewater facilities, and the use of innovative stormwater management programs and practices). • Support the Partnership’s efforts to improve the knowledge and understanding of elected officials, and to provide resources/mechanisms to do so based on what local needs are. • Recommend that the Partnership work with local governments to integrate messaging, outreach, and education efforts not only to avoid duplication of effort; but also to ensure that the public gains a more complete and consistent understanding of these water issues. • Recommend that the strategy more clearly integrate this work with the Diversity and Environmental Literacy management strategies. • Recommend that where local leadership has that knowledge and understanding (e.g. in COG region); that the Partnership continue to work with that local leadership to enhance the voice and input of local governments and help support efforts to demonstrate the local benefits of these | Craig Rice, WashCOG | 2015-04-30 | 2015-05-11 | GIT 6 | These comments will be considered during workplan development. | 2015-05-22
5.ST.LL.9 | Local Leadership |  | The Preamble to the Watershed Agreement “acknowledges that the Partnership cannot address every issue at once and that progress must be made in a strategic manner, focusing on efforts that will achieve the most cost-effective results.” It also states that “one of the most important lessons the partners have learned from the past three decades is that although watershed-wide partnerships can help to coordinate and catalyze progress, implementation happens locally.” It is with these two statements in mind that we offer the following general comments: 1. If local government participation is needed to achieve an Outcome, Management Strategies must (a) make it clear that local participation is needed, (b) clearly describe local governments’ role in achieving the Outcome, and (c) explain how local governments can get the tools and resources they need to assist with implementation. While many of the Management Strategies strive to do this, more work is needed to clearly address local governments’ role. 2. When possible and when local governments have a defined role in achieving the Outcome, Management Strategies should include information about the COST AND BENEFITS to local government. Without this information, local governments may be reluctant to become engaged because of the concern it will cost more in time and money to implement than are available. 3. Local governments need a better understanding of the Chesapeake Bay Watershed Agreement, including distinction between voluntary and mandatory components. Some local governments have expressed concern that this effort may lead to greater regulatory control. A Partnership-endorsed and supported strategy for communicating with local governments is critical. 4. To help those outside the Chesapeake Bay Program better understand the organizational infrastructure, all Management Strategies should identify Team Lead, Workgroup Lead, and Opportunities for Cross-Goal Team Collaboration as presented in the Wetland Management Strategy under Participating Partners. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | These comments were made in reference to all management strategies. Not just Local Leadership. We implemented these changes where applicable. | 2015-05-22
5.ST.LL.10 | Local Leadership |  | General Comments 1. The Management Strategy should be edited to minimize redundancy and increase readability. LGAC will be submitting suggested edits, in the form of a revised document with changes tracked, directly to the Local Leadership Workgroup. 2. The term “capacity” should be defined the first time it is used and then throughout as necessary. If capacity is understood to include funding, consider adding a Management Approach that addresses local governments need for increased funding. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | Janine's suggested edits were made where possible. Capacity was defined on page 2. | 2015-05-22
5.ST.LL.11 | Local Leadership |  | Goal, Outcome and Baseline 1. Include the following language in the second paragraph after the Outcome: "The development of this baseline will involve multiple factors, including the knowledge and capacity among local leaders. Measuring knowledge and capacity of local officials is problematic. This might be accomplished by a self-evaluation survey provided to local officials. Given turnover rates among local officials in some jurisdictions, results would reflect only a moment in time. Public opinion polls may be more useful. Other factors, such as effective programs, policies, models and management actions, will be helpful in building a baseline and determining metrics for this Goal." | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | This suggested language was adapted and used in the newest version of the document. | 2015-05-22
5.ST.LL.12 | Local Leadership |  | Participating Partners 1. The Local Government Advisory Committee should be listed under Other Key Participants. 2. Suggest replacing the existing text under Local Engagement with the following text: "Success of the Local Leadership Outcome relies on building knowledge and capacity of local leaders. During the last decade, federal and state regulations were significant in guiding Chesapeake Bay program efforts. Increasingly, continued progress in the watershed will depend on voluntary, informed actions by local officials, watershed association, non-government organizations (NGOs), grassroots leaders and individual citizen stewards. Working together to identify specific, critical roles for local leaders in a culture of mutual respect, and ensuring local knowledge and capacity are sufficient will D40become increasingly important." | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | LGAC and CAC were added as participants in the document. The Local Engagement section was edited to incorporate this input. | 2015-05-22
5.ST.LL.13 | Local Leadership |  | Factors Influencing 1. The text and bulleted lists are somewhat redundant. Consider revising into one concise statement or list. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | The factors were thoughtfully ranked and prioritized, so they will stay in a list format. | 2015-05-22
5.ST.LL.14 | Local Leadership |  | Current Efforts and Gaps 1. The first item in the bulleted list says “Bay funded…” Should this read “Chesapeake Bay Program funded…”? This item doesn’t appear to belong in this list since it is not a current effort related to achieving the Outcome specifically but rather a research project intended to inform a management approach. Suggest removing it from the list and describing in a brief paragraph in order to clarify what the project is and what it seeks to accomplish. 2. In the section titled “Cross Collaboration among Management Strategies” there should be a reference to other management strategies that specifically call out the need for increased knowledge at the local government level. • The following suggested edits to the third paragraph may achieve this: Likewise, the achievement of the Local Leadership Outcome affects the success of many other goals and outcomes because many depend on local implementation of actions. The following management strategies specifically identify a need for increased knowledge and capacity among local governments:(solicit list from GITs/workgroups) A strong culture of excellence in natural resource management among local officials can provide the framework for action necessary to achieve the vision articulated in the Chesapeake Bay Watershed Agreement. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | The item about the CBP funded project is an important current effort, so we won't be removing it. The Cross Collaboration was edited for clarity in response to this comment. | 2015-05-22
5.ST.LL.15 | Local Leadership |  | Management Approaches 1. Management Approaches should be numbered to make the document more readable. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | The management approaches were numbered to make the document easier to read. | 2015-05-22
5.ST.LL.16 | Local Leadership |  | 2. Suggest revising the third Management Approach, Improve “knowledge management”, to read as follows: Volumes of information are available on the internet and through various jurisdictions, associations and organizations. While information is plentiful, local officials repeatedly expressed concern that specific information is not readily accessible nor in an easy-to-interpret form. Time is a scarce resource. Some local leaders envision a tool that would provide one-stop, quick access to successful models and processes by topic. A portal that extracts successful models and processes from existing organization and association data bases could prove catalytic in engaging local communities in Bay-related initiatives. Steps to investigate the feasibility of various tools, such as a cloud-based portal, may include: • Convene a diverse group of multi-jurisdiction leaders with limited resources (staff, time and money) who want to support Bay restoration efforts. • Learn their priorities for models and best practices by topic. • Reach out to NGOs and other partners to identify sources for outstanding models and practices in the topic categories. • Brainstorm options for better delivering quick access to successful models and processes. • Evaluate whether proceeding to the next phase would add value toward achieving Chesapeake Bay partners’ goals. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | The knowledge management section was renamed to remove the confusion associated with this term of art and improve the clarity. A portal will be considered as one potential tool for dissemination of information. | 2015-05-22
5.ST.LL.17 | Local Leadership |  | Improving knowledge management includes ensuring effective communication with local leaders and their communities. Steps to enhance communication may include: • Identify existing communication methods and outreach mechanisms used by states, federal agencies and NGOs to reach local officials. • Determine options to enhance and improve these approaches. • Establish best practices for working with less engaged municipalities and local audiences. • Review approaches for effectiveness periodically. • Identify ways to continually improve these approaches based upon needs of local officials. Examples of options to explore include increasing regional collaboration regionally; providing funding for municipal and regional visioning sessions; identifying companies and organizations to assist with knowledge transfer; identifying other techniques to address knowledge gaps; establishing better establish teaching/training relationships with universities and community colleges. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | This section was revised in response to this comment. | 2015-05-22
5.ST.LL.18 | Local Leadership |  | 3. Suggest revising title and content of the fourth Management Approach, Identify and improve key information sources, to read as follows: • Identify information needed to improve communication with localities Local officials’ information needs differ from those of the general public or the scientific community. Development of key information sources will be created as part of this approach. While messages for local officials and the general public may be similar, content tone and presentation should be distinct. Local officials want to know what is proposed or required, resources provided, deadlines, responsibilities, and how actions will support local priorities. Effective public communication is clear, brief and contextual; addresses obstacles perceived by local leaders; and builds community support. With both types of communication, continually building a broad-based culture of excellence surrounding Chesapeake Bay restoration will be vital. Steps to improve communication include: • Identify and prioritize types of information and information sources beneficial to local officials from their perspectives, such as flooding resiliency, community benefits from stormwater management, and cost-benefits of green canopy. • Deliver the information in a manner that is collegial, clear and relevant. • Continuously evaluate communications from the perspective of the message intended versus the message as it was received • Refine messaging so it communicates content while it builds respectful relationships Examples of options to explore include targeted new releases and case studies providing economic justification for investments. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | This section was revised in response to this comment. | 2015-05-22
5.ST.LL.19 | Local Leadership |  | 4. “Approaches Targeted to Local Participation” could be strengthened by including the following text: To facilitate greater local participation from underserved and underrepresented communities, the CBP Local Leadership Workgroup will work closely with the Diversity Action Team to identify non-traditional partners and conduits for achieving the Outcome. Additional actions, tools or technical support needed to empower local governments to participate in achieving the Outcome will be identified in the Work plan. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | This section was incorporated into the Cross-Outcome Collaboration section in reponse to this comment. | 2015-05-22
5.ST.LL.20 | Local Leadership |  | 5. Under the heading Cross-Outcome Collaboration and Multiple Benefits it reads “The following management strategies identify the need to increase local officials’ knowledge as being necessary to achieve the Outcome” but there is no list following. A list of Outcomes that call for increasing local officials’ knowledge should be included in this management strategy if possible. If that isn’t possible then this sentence should be removed. See comment number #2 under Current Efforts and Gaps also. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | A list of the outcomes was listed. | 2015-05-22
5.ST.LL.21 | Local Leadership |  | VI Monitoring Progress 1. Delete last bullet which calls for an estimate number of education programs, online resources, etc. | Janine Burns, LGAC | 2015-04-30 | 2015-05-11 | GIT 6 | Did not delete this bullet as one of several suggested ideas on monitoring progress. | 2015-05-22
5.ST.LL.22 | Local Leadership |  | • Bear in that mind local governments place a keen focus and priority on Bay restoration efforts required first and foremost in their NPDES MS4 permits, followed by those called for in the Watershed Implementation Plans. The Management Strategies heap on another level of additional expectations and implementation costs and activities. The cost burden and time commitment already borne by local governments to comply with the permits and make progress toward achieving the TMDLs is substantial. Therefore, expectations need to be reasonable and practicable, with implementation timeframes spread out beyond 2025. • Local governments have limited resources for following or participating in the many environmental efforts and initiatives that vie for local government attention and action, and quite often overlap. These many efforts need to be consolidated to simplify the process and expectations for Bay restoration and addressing other environmental issues. Strategies need to be prioritized based on practicable and reasonable expectations to infuse feasibility into the implementation process. • The management strategies acknowledge that local governments will shoulder much of the work for Bay restoration, but it does not appear that local governments were intimately involved in developing the management strategies. Given the focus on local engagement, the work groups should seek input from local officials and practitioners, representing both urban and rural areas, during the development and implementation of recommendations that impact local governments. | Brenda Dinne, Carroll County Land Use, Planning & Development | 2014-04-30 | 2015-05-11 | GIT 6 | The workgroup sought the input of local officials on several occaistions through stakeholder meets held between the time period of December 2014 to May 2015. Input of local officials will continue to be sought out during workplan development and implementation. A list of the stakeholders was added in Appendix A. | 2015-05-22
5.ST.LL.23 | Local Leadership |  | Local decisions, including those related to land use, have a significant role in the Bay restoration efforts. Since this topic is discussed in many strategies, any future action regarding land use should maintain local control over land use decisions, where intimate knowledge of local landscapes and communities is crucial to appropriate decisions. Furthermore, we applaud the use of language “encouraging” local governments to incorporate additional considerations into comprehensive plans, rather than recommending further comprehensive plan mandates. Comprehensive plans are already getting too complex and cumbersome, removing some of the flexibility to address unique local character and issues. (Pgs 3-4: Black Duck, Pg 6: Riparian Forest Buffer, Pgs 2-7: Land Use Options Evaluation; Pg 10: Public Access Site Development) | Brenda Dinne, Carroll County Land Use, Planning & Development | 2014-04-30 | 2015-05-11 | GIT 6 | We feel this comment was likely directed toward a different management strategy, and therefore we did not make any changes in response to this comment. | 2015-05-22
5.ST.LL.24 | Local Leadership |  | As mentioned multiple times throughout, measures and indicators can be a valuable tool to demonstrate conditions and progress. True measures of progress require time. We strongly caution against turning these measures and indicators into future additional legislated or regulated requirements. Local governments struggle enough to meet all of the demands and mandates placed upon them. Flexibility is key for local governments. (Pgs 14, 17: Stream Health; Pgs 1-2, 5: Land Use Metrics & Measures Outcome) | Brenda Dinne, Carroll County Land Use, Planning & Development | 2014-04-30 | 2015-05-11 | GIT 6 | We feel this comment was likely directed toward a different management strategy, and therefore we did not make any changes in response to this comment. | 2015-05-22
5.ST.LL.25 | Local Leadership |  | We encourage the Chesapeake Bay Program to recognize that many of the draft strategies have important local components. For example, Montgomery County already has a robust holistic watershed restoration program designed to enhance water resources in the County as well as meeting its MS4 Permit requirements. Montgomery County also developed outreach programs that develop organizational capacity within local watershed groups, and increase citizen stewardship. Further development of the Chesapeake Bay management strategies should support existing local programs. | Lisa Feldt, Montgomery County Dept. of Environment | 2015-04-30 | 2015-05-11 | GIT 6 | We plan to work with several of the other outcomes to support local governments on issues related to water quality, SAV, oysters, etc. This was made more clear in the cross-outcome collaboration section. | 2015-05-22
5.ST.LL.26 | Local Leadership |  | Local engagement. The section in the management strategy notes the jurisdictions conducted outreach to local entities and emphasizes their important role in implementation, yet fails to commit to providing the local level targets and accountability called for in the Phase 2 WIPs. According to EPA guidance on the WIPs (http://www .epa. gov /reg3 wapd/pdf/pdf chesbay/PhaseiiWIPS/GuideforthePhaselIWIPs 330final.pdf ), the Phase 2 WIPs were to be designed to include specific information that facilitates actions by local partners to control nitrogen, phosphorus and sediment to achieve the allocations." EPA also recommended that the jurisdiction develop " .. .local area targets [that] will help partners better understand their expected contribution to meet the TMDL allocations and assumptions." Yet, except for Maryland, no other state has assigned local (e.g., county) level planning targets within their jurisdiction and no jurisdiction is setting milestone goals or tracking implementation at the local level - at least not in a form that is publically available. We have stated, on numerous occasions, our belief that programmatic and implementation goals should be expressed at the local level. This level of accountability and transparency is needed to provide "reasonable assurance" that necessary pollution reductions from all sources will be achieved by a date certain. As part of the work plans for achieving these outcomes, we strongly encourage the jurisdictions to indicate how they will work with local entities to set local level pollution reduction targets as well as implementation goals in their next set of milestones. The relative ease of use of MAST, CAST, and VAST, particularly with an integrated cost-component, should help make this effort do-able. | Kim Koble, Chesapeake Bay Foundation | 2015-05-01 | 2015-05-11 | GIT 6 | We feel this comment was likely directed toward a different management strategy, and therefore we did not make any changes in response to this comment. | 2015-05-22
5.ST.LL.27 | Local Leadership |  | The Strategy issued by the FLC declared that local communities have the greatest interest and ability to impact conservation of their local environment and directed the federal agencies to ''support the restoration activities" local citizens. The present language in the draft limits local collaboration to "local governments", failing to even mention local watershed organizations and citizens Therefore, the proposed draft should be amended include the following: "Supporting Local Efforts- Local communities have the greatest interest in and have demonstrated the ability to stop pollution in their local Waterways. The state and federal regulatory agencies shall directly support the restoration efforts of local governments, watershed organizations, and citizens, particularly with regard to innovative technology. These stakeholders shall be included in approving .any new guidelines with regard to stream restoration projects. | Fred Kelly, Severn Riverkeeper Program | 2015-04-18 | 2015-05-11 | GIT 6 | We feel this comment was likely directed toward a different management strategy, and therefore we did not make any changes in response to this comment. | 2015-05-22
5.ST.LL.28 | Local Leadership |  | Management strategies are only as good as the people who execute them. The proposed management strategies fail to address the cultural opposition to innovative technology at the permitting division of the Maryland Department of the Environment (MDE). Such opposition has killed important restoration projects and is blocking permits for new restoration technology. MDE is killing opportunities to advance the science. At the same time, the Maryland Department of Natural Resources (DNR) has supported advancements in stream restoration. The essential difference is that the staff at DNR support local governments and citizens, whereas the staff at MDE more often oppose local efforts. For example, MDE recently denied local citizens a permit to replace a broken bulkhead with a living shoreline. While the Secretary of MDE was touting the benefits of such living shoreline projects, his permitting division was denying the permit. The Severn Riverkeeper and the local citizens had to sue MDE to obtain the permit. It is the actions of regulatory agencies and not their strategy documents that impact Bay restoration. Since the culture of opposition has continued under several Secretaries, that citizens should not have to sue MDE for permits, and the regulatory authority over permits originally resided with DNR, the draft should be amended as follows: "Policy and Administration factors limit restoration projects that stop pollution. Key among these factors are the issuance of permits for stream restoration projects and the regulatory and policy guidance available for such projects. The regulatory authority for restoration permits should be transferred to the Maryland Department of Natural Resources, where it originally resided and where the experienced expertise exists. Guidelines for the requirement to demonstrate functional lift should not ex elude projects that utilize new technology. Such technology can be evaluated and scientific data can be obtained. The stakeholders who design and build such projects, such as the local governments and local watershed organizations, shall be included in the drafting and adoption of a1l guidelines. The current assessment of jurisdictions to meet their 2017 and 2025 WIP targets heightens the need to address these factors to implement projects that meet the sediment and nutrient loads reductions necessary to improve stream health." | Fred Kelly, Severn Riverkeeper Program | 2015-04-18 | 2015-05-11 | GIT 6 | We feel this comment was likely directed toward a different management strategy, and therefore we did not make any changes in response to this comment. | 2015-05-22
5.ST.LL.29 | Local Leadership |  | 1. Section IV, Gaps subsection: The gaps identified in Section I should be included in the list of gaps in this subsection. These include: no metrics currently available to measure the local leadership outcome, no current knowledge baseline, and no existing effective way of measuring the knowledge and capacity of local officials. 2. The gaps identified in Section I are mentioned in Section VI, Monitoring Progress, but filling these gaps should be mentioned up front in Section V, Management Approaches, because they are not only important to monitoring progress, but also in developing the most effective management approaches. 3. Section IV, Actions, Tools and Support to Empower Local Government and Others section: 151 sentence: replace "if" with "of'. 4. Section IV, Actions, Tools and Support to Empower Local Government and Others section: 2"d sentence: The meaning of this sentence is not clear. | Julie Pippel, Maryland State Water Quality Advisory Committee | 2015-04-24 | 2015-05-11 | GIT 6 | • The information about gaps was related to the baseline, so that's why it was in this section. • An additional bullet point added to the gaps section is being considered. • This edit was made. • An edit to this sentence is being considered. | 2015-05-22
5.ST.LL.30 | Local Leadership |  | 5. This strategy, like most of these strategies, is very complex because the issues and challenges are complex. The large set of possible steps and tasks proposed, however, could itself become an impediment to effective progress on this outcome. This strategy is a good example of why additional thought and planning will be needed before development of the first biennial workplans (see General Comment 1). Would it be possible to come up with an approach that utilizes existing local elected and appointed officials' "already been scheduled" meetings to add to the knowledge base about the Bay Agreement? For example, MML holds meetings regularly in addition to the two conferences. 6. Couldn't time be set aside to educate local officials about how their decisions have an impact on the overall improvement of the Bay? After a series of utilizing "already been scheduled meetings" for this purpose, a survey could be administered to assess knowledge gained. 7. As the Local Leadership Outcome strategy notes, there is high turnover of local officials so setting up a rather complicated framework to measure, hold coursework etc. may not fit this high turnover. 8. Information is needed in an understandable form for local officials to refer to when making the decisions that they have to make at the local level. This is essential. If emphasis could be placed on this piece-much progress could be achieved. | Julie Pippel, Maryland State Water Quality Advisory Committee | 2015-04-24 | 2015-05-11 | GIT 6 | These comments will be considered during workplan development. | 2015-05-22