## Sheet1
Bay TMDL 2025 Progress Schedule
Legend: | BMP Items
QAPP Items
Task Decription | Responsible Party | Task Start Date | Task due Date | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01
NEIEN Appendix Draft: BMP Listing, descriptions, and mapping are due from jurisdictions for any proposed BMPs that will be submitted for progress assessment that are NOT included in the NEIEN Appendix. An initial draft will be presented at the July 3rd WTWG for input. | Jurisdictions | 2025-07-01 | 2025-07-31 | bar: 2025-07-01
Initial Updates to Quality Assurance Project Plans (QAPPs) Due: These initial updates should address any unresolved revision requests made in the Final 2024 Progress QAPP Review Memos. Changes since the previous progress year in field, laboratory, quality control, and/or data management procedures must be reported in this QAPP. Highlight or otherwise flag these changes from the previous progress year's approved version, submit to the CBPO by September 1st. For additional requested updates, please reference the QAPP update emails sent over the summer by Ruth Cassilly and Auston Smith Additionally, updates to jurisdictions’ BMP Verification Program Plans (VPPs) describing new programs and/or data sources and changes to methods of tracking, reporting, and verification are due by September 1st. Partners must notify the project officer prior to this deadline if changing the number of samples, the number of sites, or parameters measured. If there are no changes, the recipient must provide written documentation (i.e. email) to Ruth Cassilly (rcassilly@chesapeakebay.net and Auston Smith (smith.auston@epa.gov), cc Durga Ghosh (dghosh@chesapeakebay.net) confirming a review was conducted and no changes have occurred. | Jurisdictions | N/A | 2025-09-01 | bar: 2025-07-01 to 2025-08-01
NEIEN Appendix Draft Review: Final jurisdictional requests for NEIEN Appendix adjustments received for inclusion consideration. The August 7th Watershed Technical Workgroup will provide a second forum for the review of the 2025 Progress NEIEN Appendix that includes consideration edits received since July. Final feedback will need to be received by email prior to August 25, 2025. This task due date of August 25 is to allow for one week to finalize this product internally and integrate it into CAST | Jurisdictions | 2025-08-01 | 2025-08-25 | bar: 2025-08-01
Submit Following Land Use Datasets: 1) permitted forest harvest acres, 2) continually disturbed and permitted construction acres – including estimates of any unpermitted acres and 3) CAFO/AFO animal splits by county within the CB Watershed | Jurisdictions | 2025-08-01 | 2025-11-03 | bar: 2025-08-01 to 2025-10-01
NEIEN Appendix Finalization: CBPO will finalize the NEIEN Appendix for BMPs receiving credit on September 1 and circulate that via email to workgroup membership. It will also be posted on CAST here: https://cast.chesapeakebay.net/Home/TMDLTracking#progressReportingSection This finalized version of the NEIEN Appendix for 2025 progress and any major changes since the previous progress year will be presented at the September 4th Watershed Technical Workgroup. | CBPO | N/A | 2025-09-01 | bar: 2025-08-01
CBPO Scheduling for Initial Verification Discussions: Auston Smith will send out scheduling poll emails this week to ensure initial verification calls can be held with all jurisdictions the week of December 8-12th. This is to prevent a lag between jurisdictional data submissions, the initial verification call agenda, and rerun data visualized through Tableau. Please reply to the scheduling poll ASAP (to be sent in November) to ensure members of your team can be available during the week of December 8-12th. Please flag in advance if this is not possible. Verification Agendas will be sent with scheduling poll emails and will be attached to the meetings based on December 1st COB rerun data. As flagged below, follow up verification discussions will be held as necessary. | CBPO and Jurisdictions | 2025-09-01 | 2025-09-30 | bar: 2025-09-01
Overview of draft Phase 7 NEIEN Appendix: This overview will highlight differences between the finalized P6 NEIEN Appendix to be finalized in September 2025 for 2025 Progress and the revised NEIEN Appendix that will be used to report annual progress in Phase 7 of CAST in 2028/29. The purpose of this overview is to socialize the Phase 7 product to the group and prepare them to finalize it for the upcoming Phase 7 integration at the December 2025 meeting. The overview will be presented at the October 2nd WTWG meeting, following the finalization of the Phase 6 NEIEN Appendix for 2025 Progress. | CBPO and Jurisdictions | 2025-10-02 | 2025-10-02 | bar: 2025-10-01
Jurisdictions Can Submit BMP Implementation Data to NEIEN: Assuming LU and Animal Data has been received, this submission process will be ongoing from September 1 -December 1. Expectation is that December 1st will be last submission for jurisdictional data before test CAST scenarios begin. During WTWG meetings during this period, CBPO will provide updates on received land use data. BMPs should be submitted by this due date for the July 1 to June 30 2025 period from jurisdictions for the 2025 Progress Phase 6 model assessment – both wastewater data and non-wastewater BMPs. NEIEN validation reports will be available before December 1 and are available upon request from Jessica Rigelman (jrigelman@chesapeakebay.net). Scenarios with loads will be run after December 1st to allow time for this year's final land use to be prepared and incorporated into CAST. Please copy Auston (smith.auston@epa.gov) on all communication on submitted data. These submitted datasets should address refinement comments received from previous progress scenarios and review(s). | Jurisdictions | 2025-09-01 | 2025-12-01 | bar: 2025-09-01 to 2025-11-01
Jurisdictions Submit QAPP Refinements: Requests for refinement of QAPPs from Sept 1 submission (Version 1) must be addressed. Updated QAPP submissions are due December 1, (Version 2) but can be submitted earlier. Additional revisions between Dec.1 and the Feb 6 deadline (Version 3) may be necessary as a result of verification discussions and progress scenario review. These updates should address any unresolved revision requests made since the initial QAPP update due September 1, 2025. Among other requested additions, these updates should describe new data sources, programs and methodologies for tracking, reporting, and verification for 2025 Progress. | Jurisdictions | 2025-09-01 | 2025-12-01 | bar: 2025-09-01 to 2025-11-01
Point Source Data Submission due to CBPO via Point Source Data Submission Application: 1) Biosolid and ag spray irrigation mass and nutrient concentration application by count, 2) CSO connections and pass-through data, 3) Large monitored onsite septic system load data (commercial and residential) 4) Rapid infiltration basin load data (RIBs) | Jurisdictions | 2025-09-01 | 2025-12-01 | bar: 2025-09-01 to 2025-11-01
Initial CBPO-Jurisdiction Scheduled Verification Calls: CBPO will have the initial scheduled verification discussions scheduled back in September with jurisdictions to discuss BMP and wastewater trends of note, and QAPP status. Agendas outlining QAPP questions, BMP trends, and point source facilities for discussion will be included on the meeting invite and sent ahead of time with the scheduling poll. | CBPO and Jurisdictions | 2025-12-08 | 2025-12-12 | bar: 2025-12-01
CAST Reports available for Jurisdictional Review and Feedback: Reporting of revised data following the initial Dec 1 submission, which is used for the initial verification discussion, are due by 12pm EST each Friday during this window. Follow-up verification calls to address questions will be scheduled during this period as needed. New reports for 2025 progress will be run each Friday and will be available the following Monday. In some cases the reports may be available earlier; jurisidictions have the option to check on the report completion status as needed. | CBPO and Jurisdictions | 2025-12-01 | 2026-02-06 | bar: 2025-12-01 to 2026-02-01
QAPP Outstanding Comments Response due: It is expected that jurisdictions address all outstanding EPA QAPP review comments in their Review Memos by this date. Addressing these comments and any corresponding progress submission data problems should occur no later than February 6 to ensure full credit of quality data. | CBPO and Jurisdictions | 2025-12-01 | 2026-02-06 | bar: 2025-12-01 to 2026-02-01
Final 2025 Progress Run Available: All updates to BMP data must be submitted by this deadline to ensure a final progress run can be provided to jurisdictions to close the process for that particular progress year | CBPO and Jurisdictions | N/A | 2026-02-06 | bar: 2025-12-01 to 2026-02-01
Final Review of Jurisdictional QAPPs and Approval Memos Issued: This memo summarizes jurisdictional QAPP approval status for the relevant Progress year and tracks the status of revision requests between EPA CBPO and jurisdictions. In addition, the memo documents any outstanding revision requests expected for the subsequent progress year submission in September 2025. | EPA | 2025-02-09 | 2026-03-06 | bar: 2026-02-01 to 2026-03-01
2025 Progress Finalized and Released on CAST: Following finalization of communication surrounding 2025 progress by the CBPO Web Team and EPA Indicators Team, the final progress scenario will be released on CAST for public use ~first week of May. | CBPO | 2026-05-01 | 2026-05-08 | bar: 2026-03-01 to 2026-05-01
Disclaimer: As with 2024 Progress, the finalization of 2025 Progress may be delayed due to provide adequate time to address unresolved issues surrounding the verification assessments. The schedule may need to be altered to accommodate the availability of jurisdictional representatives and/or to accommodate the delays mentioned above. The Bay Program Office Staff will attempt to stay on schedule and will update jurisdiction technical teams directly on progress. Any updates on the schedule will be provided at the Watershed Technical Work Group (WTWG) monthly meetings.