## Sheet1
Task Role | Responsibilities
Content Lead | Initial drafting; consultation lead (scheduling, facilitation, note-taking, disseminating)
Major Focus | Available for targetted feedback, focuses any extra review/research in this area
Element | Task-specific | CBC | CBPO* | DC | DE | FED | MD | NY | PA* | VA | WV | Notes
1 - Introduction | [11 empty] | General updates necessary to reflect revised CBWA, however anticipate a discussion on DEIJ section
2 - Ethics | [11 empty] | Intent is to ensure that partnership implementation groups can understand federal grant making rules as they engage in workgroup or GIT activities. Interested in ensuring the same for any jurisdictional policies.
3 - Leadership | Partnership (i) | [10 empty] | All partners will have a strong focus in how the PSC element is designed, but agreed that PSC chair is best to lead with pen
| Federal (ii) | [10 empty] | Feds will focus on FLC / FOD path forward.
4 - Implementation | MB Transfer (i) | [10 empty] | CBC partner sits on both groups; positioned to collaborate closely with PSC and Goal Team revisions, but recognize broad interest
| Goal Teams (ii) | [10 empty] | All partners interested in how the Goal element is designed; Federal partners have been closely engaging with Goal Teams and positioned to develop, coordinate and collaborate.
| Support Teams (iii) | [10 empty] | CBPO lead; Interested partners identified themselves for increased focus and participation in revisions
| Advisory (iv) | [10 empty] | PSC chair lead given Advisory Committee designee framework and configuring PSC engagement.
5 - Public Meeting Procedures | Decision Making (i) | [10 empty] | Assume all members will want to have a strong focus in decision-making, but agreed CBPO chair is best to lead with pen considering meeting coordination roles
| Participation (ii) | [10 empty] | MD has championed particiption thorugh B25 processed and positioned to continue leading; will be closely engaged with Decision-Making piece.
6 - Operations & Accountability | Prioirty Setting (i) | [10 empty] | Assume all members will have a major focus, but agreed PSC chair is best to lead and couples with leadership element.
| Mgmt Strategies (ii) | [10 empty] | CBPO lead; Interested partners identified themselves for increased focus and participation in revisions