## Calendar
| Year | 2026 |  |  |  |  | Month | 1 |  |  |  | Start Day | 1 |  | 1:Sun, 2:Mon …
2026 | [6 empty] | Year-at-a-glance
2026-01-01 | [7 empty] | 2026-02-01 | [7 empty] | 2026-03-01 | [6 empty] | Meetings | Material Post Date (subject to additional updates)
S | M | T | W | T | F | S |  | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | PSC | Two weeks in advance.
|  |  |  | 2026-01-01 | 2026-01-02 | 2026-01-03 |  | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 |  | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | Management Board | One week in advance except for June 11.
2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 |  | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 |  | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | [Sig] Implementation Team | Depends on meeting frequency, but members will have shared, live access to materials.
2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 |  | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 |  | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | Federal Office Directors | Showing these meetings to conceptualize internal feedback needs.
2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 |  | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 |  | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | Federal Holiday
2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | [9 empty] | 2026-03-29 | 2026-03-30 | 2026-03-31
2026-01-25: January: Writing process begins. MB opportunity for feedback on internal engagement. PSC briefing of plan. Less need for frequent meetings. |  | February: Writing continues. Still no major need to meet frequently. MB anticipated to be a brief of progress (writing and engagement) and focused on Mgmt Strats template. | [7 empty] | March: From end of February, more frequent meetings to prepare for draft delivery to PSC. Scheduled meetings to account for internal coordination requirements, prior to Signatory deliberation.
[23 empty] | Pause Revision | Meeting Date | Explanation
[23 empty] | February 2 | February 5 | Only 48h for internal coordination. Early in drafting process. Meeting focus will be on reporting out key concepts of revisions and engagement.
2026-01-25: 2026-04-01 |  | 2026-05-01 | [7 empty] | 2026-06-01 | [6 empty] | February 20 | February 26 | 72h window for internal coordination. Meeting focus will be to identify critical revisioins to address in March as part of the initial draft to the PSC.
S | M | T | W | T | F | S |  | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | March 16 | March 19 | 48h window, given need to incorporate MB feedback. Meeting focus will be on resolving / framing of critical issues before sharing draft with PSC on 3/24.
|  |  | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | [6 empty] | 2026-05-01 | 2026-05-02 |  |  | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | N.A. | April 9 | ~2-week window for internal coordination from March 24-April 7th. Each partner compiles a list of remaining issues. Scope out necessary revisions on April 9th.
2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 |  | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 |  | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | April 27 | May 4 | 72h window (not considering Friday) for internal coordination. Meeting focus will be on sharing options to resolve issues.
2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 |  | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 |  | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | May 18 | May 26 | 72h window (not considering Friday) for internal coordination. Meeting focus will be on confirming draft for MB consensus. Identify issues for review on June 8th.
2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 |  | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 |  | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | May 28 | June 8 | Over a week window given requirement to post final draft for June MB. June 8th meeting focus on resolving final issues for June MB consensus.
2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 |  |  |  | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 |  | 2026-06-28 | 2026-06-29 | 2026-06-30 |  |  |  |  | N.A. | June 25 | Prepare for PSC meeting.
2026-05-31
April: Address revisions (anticipate a lot of individual and small group coordination). 4/9 MB will be transitioned to 4/16. Implementation Team meet on 4/9 to debrief from PSC and prepare for revisions and MB meeting. | [7 empty] | 2026-05-24: May: More frequent meetings to prepare for June MB, although best to be aligned with any changes in April. May MB a recap of revisions and feedback opportunity. Final revisions made at the end of May. |  | June: Meeting on 9th to situate for consensus process. Final touches after June MB to deliver materials to PSC. Possible meeting on 25th for a pre-PSC briefing, but may not be necessary.
Note on O9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FOD also meeting
Note on T11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FOD meeting also