## Sheet1
Agriculture Workgroup Task Matrix
green = completed
orange = immediate work needed
yellow = ongoing
red = overdue
Task | Recommendation Date | Recommendation Contact | Datasets Needed | Dataset Contacts | CBP Leads | Update | Expected Completion Date
Compare land uses between CBP Watershed Model and USDA-CEAP's. | 5222013 | Matt Johnston | CEAP land uses | Lee Norfleet | Mark Dubin; Matt Johnston; Peter Claggett | May 22, 2013 - Proposed at Building a Better Bay Model Workshop | 8012013
Investigate Cropland Data Layer and determine if it is possible to use CDL in defining gegraphic distribution of land uses. | 5222013 | Matt Johnston | CDL through time | Thomas Morgart; Craig Goodwin | Mark Dubin; Matt Johnston; Peter Claggett | May 22, 2013 - Proposed at Building a Better Bay Model Workshop | 10012013
Work with the states to gather local agricultural land use data. | 5222013 | Matt Johnston | Multiple local land use datasets | State Ag Agency Contacts | Mark Dubin; Matt Johnston; Peter Claggett | May 22, 2013 - Proposed at Building a Better Bay Model Workshop | 1012014
Define new agricultural land uses using the USDA's CDSI land cover as a guide. | 2142013 | Mark Dubin; Dana York | NA | NA | Mark Dubin; Matt Johnston; Peter Claggett | May 22, 2013 - Proposed at Building a Better Bay Model Workshop; February, 2013 - Recommended at Ag Workgroup meeting | 1012014
Define loading rates for new all new agricultural land uses. | 2132013 | Mark Dubin | Full literature review needed for each land use. | NA | Mark Dubin; Matt Johnston; Peter Claggett | February, 2013 - Recommended at Ag Workgroup meeting | 1012015