## Sheet1
Agriculture Workgroup Expert BMP Panels: Rolling Master 2016 Timeline DRAFT 3/16/16
Key:
| = | Panel convenes, deliberates, and drafts report.
| = | Panel releases report. Coordinator and chair usher it through partnership approval.
| = | WQGIT approval.
BMP Panel: | February | March | April | May | June | July | August | September | October | November | December | Panel Current Status
Cover Crops | 2/24: Panel conference call. | 3/17: Panel conference call. Panel begins working on literature review. | End of April: Panel completes literature review. | Panel writes and drafts report. | End of June/Early July: Panel finalizes report. | Early July: Open comment period for partnership review. -AgWG holds webinar to kick-off comment period. | August 17-18: AgWG approves report | Sept. 1: WTWG approves report |  |  |  | -Panel is considering candidates for completing additional work that will be provided through technical assistance funds.
Sept. 26-27: WQGIT approves final report
Nutrient Management | 2/24: Panel conference call. | 3/31: NMP follow-up call Panel holds conference calls every 2 weeks. Panel begins working on literature review. | End of April: Panel completes literature review. | Panel writes and drafts report. | End of June/Early July: Panel finalizes report. | Early July: Open comment period for partnership review. -AgWG holds webinar to kick-off comment period. | August 17-18: AgWG approves report | Sept. 1: WTWG approves report |  |  |  | -Panel has expressed concerns regarding the use of fertilizer sales data, and will be discussing this with the AMS during their 3/4 and 3/9 conference calls. -Panel is revising the structure of their BMP representation in the model. -Panel has not begun literature review yet.
Sept. 26-27: WQGIT approves final report
Manure Injection/ Incorporation | 2/12: Panel conference call. | End of March: NMP follow-up call Panel holds conference calls every 2 weeks. Panel begins working on literature review. | End of April: Panel completes literature review. | Panel writes and drafts report. | End of June/Early July: Panel finalizes report. | Early July: Open comment period for partnership review. -AgWG holds webinar to kick-off comment period. | August 17-18: AgWG approves report | Sept. 1: WTWG approves report |  |  |  | -Panel is considering candidates for completing additional work that will be provided through technical support funds.
Sept. 26-27: WQGIT approves final report
Conservation Tillage | Last panel meeting: 11/2 | Week of 3/14: Panel holds conference call to discuss final results of literature review. -Panel holds conference calls every two weeks | Panel comes to consensus on recommendations to be included in report. Panel writes and drafts report. | Panel writes and drafts report. Panel holds conference calls ever 2 weeks. Report completed by end of May/early June. | Early June: Open comment period for partnership review. -AgWG holds webinar to kick-off comment period. | 7/21: AgWG approves report. | 8/4: WTWG approves report. | 9/12: WQGIT approves report |  |  |  | -Panel is adding one additional category to tillage. -Panel has almost completed literature review.
Cropland Irrigation |  | Partnership review of proposed membership. | 4/21: AgWG approves membership. Panel has open stakeholder session. | Panel holds regular conference calls. | Panel completes literature review. Panel holds regular conference calls. | Panel writes and drafts report. Panel holds regular conference calls. | Panel writes and drafts report. Panel holds regular conference calls. | Panel finalizes report. | Early October: Panel releases report for partnership comment. -AgWG holds webinar to kick-off comment period. | 11/16-17: AgWG approves report. | 12/1: WTWG approves report. | -Panel charge and scope already approved by the AgWG. Coordinator is working on developing final list of membership for approval.
12/12: WQGIT approves report.
Agricultural Stormwater |  | Partnership review of proposed membership. | 4/21: AgWG approves membership. Panel has open stakeholder session. | Panel holds regular conference calls. | Panel completes literature review. Panel holds regular conference calls. | Panel writes and drafts report. Panel holds regular conference calls. | Panel writes and drafts report. Panel holds regular conference calls. | Panel finalizes report. | Early October: Panel releases report for partnership comment. -AgWG holds webinar to kick-off comment period. | 11/16-17: AgWG approves report. | 12/1: WTWG approves report. | -Panel charge and scope already approved by the AgWG. Coordinator is working on developing final list of membership for approval.
12/12: WQGIT approves report.
Animal Waste Management Systems | WQGIT approval. April: Panel hosts public stakeholder session on 4/7; panel works to draft report; WQGIT approval. May: Panel continues to discuss and draft its report; WQGIT approval. June: Panel finalizes its report for release to CBP partnership for review and comment; WQGIT approval. July: Seek AgWG approval following 30-day comment period; WQGIT approval. August: AgWG approval, followed by WTWG approval; WQGIT approval. September: WQGIT approval | Panel has held its first call and is actively clarifying and assigning tasks for panel members.
Manure Treatment Technologies | WQGIT approval. March: Panel finalizes draft report for release to partnership in mid- to late-March. Webinar to present recommendations TBD.; WQGIT approval. April: Potentially seek AgWG approval of report following 30 day comment period and response to comments. Dates TBD based on initial release of report.; WQGIT approval. May: Seek AgWG and/or WTWG approval; WQGIT approval. June: WTWG and or/WQGIT approval; WQGIT approval. July: WQGIT approval | Panel is finalizing its report for release in Marcfh 2016.
Agricultural Ditch |  | Develop panel membership and hold partnership review. | 4/21: AgWG approves panel membership. Hold first meeting/open stakeholder meeting | Panel holds public meeting; completes literature review 5/30 Panel holds regular conference calls. | Panel holds regular conference calls. | Panel writes and drafts report. Panel holds regular conference calls. | Panel finalizes report. | End of September: Panel releases report for partnership comment. -AgWG holds webinar to kick-off comment period. | 10/20: AgWG approves report. | 11/3: WTWG approves report.
11/28: WQGIT approves report.