## Sheet1
Agriculture Workgroup Rolling Master 2016 Timeline DRAFT 8/24/16
Panels Key:
| = | Panel convenes, deliberates, and drafts report.
| = | Panel releases report. Coordinator and chair usher it through partnership approval.
| = | WQGIT approval.
Group: | February | March | April | May | June | July | August | September | October | November | December | January | Additional Notes
Modeling Team/Watershed Technical Workgroup | 2/1: Beta 1 draft documentation released | 3/10: Webinar to AgWG | 4/11: Comments on Beta 1 due to Modeling Team 4/19: Release Beta 2 | 5/1: Beta 2 documentation released | 6/3: Comments on Beta 2 due to Modeling Team 6/17: NEIEN BMPs and other inputs due to Modeling Team | 7/7: Beta 2 release webinar | 8/9-10: Beta 3 released 8/31: WTWG deadline for NEIEN BMP submission requirements | 9/30: Deadline for state submissions to NEIEN/All Phase 6 Submissions due (excepting Land Use) |  |  | 12/6-12/7: Beta 4 released | 1/3: Release Phase 6.0 Model and documentation. 1/12: Webinar on Phase 6.0 model | Dates and deadlines presented for the Modeling Team are subject to change. -The Phase 6 model is scheduled to be released in March, 2017.
Ag Modeling Subcommittee (AMS) | 2/11: AMS conference call | 3/4: AMS conference call 3/9: AMS conference call | 4/6: AMS conference call 4/14: Joint meeting with NMP. 4/21: AMS presents interim SB components to AgWG. This initiates AgWG open comment period on proposed SB changes. | 5/19: AgWG approves interim revisions to SB for July beta calibration. | 6/1: AMS delivers SB components to Modeling Team. 6/16: AMS update to the AgWG. | 7/21: 'Fatal flaw' review by AgWG begins. 30 day comment period. | 8/11 & 8/17: AMS conference calls. 8/19: 'Fatal flaw' comments due to AMS. 8/24: AMS update to AgWG. 8/31: Report on SB delivered to STAC | 9/26: AMS presents to AgWG proposed changes to SB resulting from 'Fatal flaw' review. (Tentative) End of September: AgWG receives STAC comments on SB |  |  |  |  | -AMS will be accepting comments from the AgWG on the proposed interim components to Scenario Builder. -The AMS has provided preliminary results from the Beta 3a and 3b model runs on the Agriculture Workgroup website under the Projects and Resources tab.
Cover Crops | 2/24: Panel conference call. | 3/17: Panel conference call. Panel begins drafting white paper. | 4/21: Panel presents preliminary report to AgWG. | 5/19: Update AgWG on preliminary report. Panel compiles crop data. 5/26: Panel conference call. | 6/16: Panel presents revised preliminary report to AgWG. | 7/20-7/21: AgWG approves panel preliminary report. | August: Panel releases report for partnership review. | September: WTWG/AgWG approves report (tentative) |  |  |  |  | -The panel's preliminary report was approved by the AgWG in July. Panel is currently working on developing their report and recommendations.
September: WQGIT approves report.
Nutrient Management | 2/24: Panel conference call. | 3/31: Panel conference call. Panel begins drafting white paper. | 4/14: Conference call with AMS. 4/21: Panel presents preliminary report to AgWG. | 5/6: Panel conference call. 5/19: AgWG approves preliminary report Panel develops efficiency values. | Panel continues to develop efficiency values. | Panel writes and drafts report. 7/20-21: Panel gives updates to AgWG. Week of 7/25: Panel releases report to partnership. | 8/1: Draft report released for Partnership comment. 8/31: Comments on draft report due to Mark Dubin and Lindsey Gordon. | 9/7: WTWG/AgWG approves report (tentative) |  |  |  |  | -Panel released their draft report for partnership review on August 1. Comments are due to Mark Dubin and Lindsey Gordon by COB August 31.
9/12 or 9/26: WQGIT approves report.
Manure Injection/ Incorporation | = February: 2/12: Panel conference call.; WQGIT approval. March: Panel begins drafting white paper.; WQGIT approval. April: 4/21: Panel presents preliminary report to the AgWG.; WQGIT approval. May: 5/19: AgWG approves preliminary report Panel works on literature review.; WQGIT approval. July: Panel writes and drafts report.; WQGIT approval. August: August: Panel releases report for partnership review.; WQGIT approval. September: September: WTWG/AgWG approves report (tentative) | -Panel is currently working on developing their report and recommendations.
September: WQGIT approves report.
Conservation Tillage | = February: Last panel meeting: 11/2; WQGIT approval. March: Week of 3/14: Panel holds conference call to discuss final results of literature review. Panel begins drafting white paper.; WQGIT approval. April: 4/21: Panel presents preliminary report to AgWG.; WQGIT approval. May: 5/19: AgWG approves preliminary report; WQGIT approval. July: Panel writes and drafts report.; WQGIT approval. August: August: Panel releases report for partnership review.; WQGIT approval. September: September: WTWG/AgWG approves report (tentative) | -Panel is currently working on developing their report and recommendations.
September: WQGIT approves report.
Cropland Irrigation |  |  |  | 5/19: Update AgWG on proposed membership. |  | Partnership review of proposed membership. 7/20: Final panel membership presented to AgWG. | Panel holds brief, introductory conference call. | Panel holds open stakeholder session. Panel holds regular conference calls. | Panel drafts report. | Early November: Panel releases report for partnership comment. -AgWG holds webinar to kick-off comment period. | 12/15: AgWG approves report. | January: WTWG approves report. | -Panel membership was approved by the AgWG in July, and the panel will work to hold their open stakeholder meeting in September.
January: WQGIT approves report.
Agricultural Stormwater | WQGIT approval. November: Early November: Panel releases report for partnership comment. -AgWG holds webinar to kick-off comment period.; WQGIT approval. December: 12/15: AgWG approves report.; WQGIT approval. January: January: WTWG approves report. | -Panel charge and scope already approved by the AgWG. Coordinator is working on developing final list of membership for approval.
January: WQGIT approves report.
Animal Waste Management Systems | WQGIT approval. April: 4/7: Panel holds open stakeholder session.; WQGIT approval. May: Panel continues to discuss and draft its report 5/19: Panel presents preliminary report to AgWG.; WQGIT approval. June: Panel continues data review and development of recommendations; WQGIT approval. July: Panel develops recommendations and draft report; WQGIT approval. August: Panel works to finalize draft report for partnership review; WQGIT approval. September: Panel releases preliminary recoverability estimates fo AgWG approval in early September; panel releases full draft report for partnership review late September or early October | The panel is working on developing a draft preliminary report to present to the AgWG in September.
Manure Treatment Technologies | WQGIT approval. March: 3/31: Release report to partnership. This begins 30-day partnership review period.; WQGIT approval. April: 4/14: Two-hour webinar on panel report. 4/21: Present report to AgWG; WQGIT approval. May: 5/2: Partnership review period closes. 5/19: Update AgWG on comments received and potential report revisions.; WQGIT approval. July: 7/20: AgWG approved panel's technical recommendations.; WQGIT approval. August: 8/4: Update presented to WTWG; WQGIT approval. September: 9/1: Seek WTWG approval | Panel released the report for partnership review on Thursday, March 31. They hosted a public webinar to present this report to the partnership on Thursday, April 14th. The AgWG approved the report during their July monthly face-to-face meeting.
9/12: Earliest potential date for WQGIT approval
Agricultural Ditch |  | Develop panel membership and hold partnership review. | 4/21: AgWG approves panel membership. | Hold first meeting 5/23 Panel holds regular conference calls. | Panel works on literature review Panel holds regular conference calls. | Panel works on literature review Panel holds regular conference calls. | Panel completes literature review. 8/31: Panel holds Open Stakeholder Session. | Panel writes and drafts report. Panel finalizes report. | End of October Panel releases report for partnership comment. -AgWG holds webinar to kick-off comment period. | 11/20: AgWG approves report. | 12/3: WTWG approves report. |  | The Panel is holding a public stakeholder meeting on Aug 31st. Panel members provided materials for literature review. The panel is working towards completon of a literature review for the end of August
12/28: WQGIT approves report.