## Sheet1
Agriculture Workgroup Rolling Master 2016 Timeline DRAFT 9/6/16
Panels Key:
| = | Panel convenes, deliberates, and drafts report.
| = | Panel releases report. Coordinator and chair usher it through partnership approval.
| = | WQGIT approval.
Group: | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | Additional Notes
Modeling Team/Watershed Technical Workgroup | 7/7: Beta 2 release webinar | 8/9-10: Beta 3 released 8/31: WTWG deadline for NEIEN BMP submission requirements | 9/30: Deadline for state submissions to NEIEN/All Phase 6 Submissions due (excepting Land Use) |  |  | 12/6-12/7: Beta 4 released | 1/3: Release Phase 6.0 Model and documentation. 1/12: Webinar on Phase 6.0 model |  | Dates and deadlines presented for the Modeling Team are subject to change. -The Phase 6 model is scheduled to be released in March, 2017.
Ag Modeling Subcommittee (AMS) | 2016-07-01: 7/21: 'Fatal flaw' review by AgWG begins. 30 day comment period.; 2016-08-01: 8/11 & 8/17: AMS conference calls. 8/19: 'Fatal flaw' comments due to AMS. 8/24: AMS update to AgWG. 8/31: Report on SB delivered to STAC; 2016-09-01: 9/2: AMS conference call 9/7: AMS update to AgWG, request decision on changes to SB. 9/22: AMS presents to AgWG proposed changes to SB resulting from 'Fatal flaw' review. (Tentative) End of September: AgWG receives STAC comments on SB | -AMS will be accepting comments from the AgWG on the proposed interim components to Scenario Builder. -The AMS has provided preliminary results from the Beta 3a1 (also known as Beta 3c) model runs on the Agriculture Workgroup website under the Projects and Resources tab.
Cover Crops | 2016-07-01: 7/20-7/21: AgWG approves panel preliminary report.; 2016-09-01: Panel releases report for partnership review.; 2016-10-01: October: WTWG/AgWG approves report (tentative) | -The panel's preliminary report was approved by the AgWG in July. Panel is currently working on developing their report and recommendations.
October: WQGIT approves report.
Nutrient Management | 2016-07-01: Panel writes and drafts report. 7/20-21: Panel gives updates to AgWG. Week of 7/25: Panel releases report to partnership.; 2016-08-01: 8/1: Draft report released for Partnership comment. 8/31: Comments on draft report due to Mark Dubin and Lindsey Gordon.; 2016-09-01: 9/22: WTWG/AgWG approves report | -Panel released their draft report for partnership review on August 1. Comments were due to Mark Dubin and Lindsey Gordon by COB August 31. A revised draft of the report is expected to be presented to the AgWG on September 15th, and the AgWG will be asked to approve the report on September 22nd.
9/26: WQGIT approves report.
Manure Injection/ Incorporation | 2016-07-01: Panel writes and drafts report.; 2016-09-01: Panel releases report for partnership review.; 2016-10-01: October: WTWG/AgWG approves report (tentative) | -Panel is currently working on developing their report and recommendations.
October: WQGIT approves report.
Conservation Tillage | 2016-07-01: Panel writes and drafts report.; 2016-09-01: Panel releases report for partnership review.; 2016-10-01: October: WTWG/AgWG approves report (tentative) | -Panel is currently working on developing their report and recommendations.
October: WQGIT approves report.
Cropland Irrigation | Partnership review of proposed membership. 7/20: Final panel membership presented to AgWG. | 8/23: Panel holds brief, introductory conference call. | 9/19: Panel holds face-to-face meeting and open stakeholder session. Panel holds regular conference calls. | Panel drafts report. | Early November: Panel releases report for partnership comment. -AgWG holds webinar to kick-off comment period. | 12/15: AgWG approves report. | January: WTWG approves report. |  | -Panel membership was approved by the AgWG in July, and the panel will hold their open stakeholder meeting on September 19th at the Wye Research Center in Queenstown, MD.
January: WQGIT approves report.
Agricultural Stormwater | 2016-11-01: Early November: Panel releases report for partnership comment. -AgWG holds webinar to kick-off comment period.; 2016-12-01: 12/15: AgWG approves report.; 2017-01-01: January: WTWG approves report. | -Panel charge and scope already approved by the AgWG. Coordinator is working on developing final list of membership for approval.
January: WQGIT approves report.
Animal Waste Management Systems | 2016-07-01: Panel develops recommendations and draft report; 2016-08-01: Panel works to finalize draft report for partnership review; 2016-09-01: Panel releases preliminary recoverability estimates fo AgWG approval in early September; panel releases full draft report for partnership review late September or early October 9/7: Panel presents preliminary report to AgWG. 9/15: AgWG approves preliminary report (tentative) | The panel is working on developing a draft preliminary report to present to the AgWG on September 7th. The AgWG will be asked to approve the preliminary report on September 15th (tentative).
Manure Treatment Technologies | 2016-07-01: 7/20: AgWG approved panel's technical recommendations.; 2016-08-01: 8/4: Update presented to WTWG; 2016-09-01: 9/1: Seek WTWG approval | Panel released the report for partnership review on Thursday, March 31. They hosted a public webinar to present this report to the partnership on Thursday, April 14th. The AgWG approved the report during their July monthly face-to-face meeting. The panel received approval from the WTWG on September 1st, and expects to receive WQGIT approval on September 12th.
9/12: Earliest potential date for WQGIT approval
Agricultural Ditch | Panel works on literature review Panel holds regular conference calls. | Panel completes literature review. 8/31: Panel holds Open Stakeholder Session. | Panel writes and drafts report. Panel finalizes report. | End of October Panel releases report for partnership comment. -AgWG holds webinar to kick-off comment period. | 11/20: AgWG approves report. | 12/3: WTWG approves report. |  |  | The Panel is holding a public stakeholder meeting on Aug 31st. Panel members provided materials for literature review. The panel is working towards completon of a literature review for the end of August
12/28: WQGIT approves report.