## Sheet1
Agriculture Workgroup Rolling Master 2017 Timeline DRAFT 6/27/17
Panels Key:
Panel convenes, deliberates, and drafts report.
Panel releases report. Coordinator and chair usher it through partnership approval.
WQGIT approval.
Group: | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | Additional Notes
Agriculture Workgroup | Conference Call 4/20: Briefing: NFWF Technical Assistance Chesapeake Bay Survey Briefing: Proposed Review of Phase 6 Model Input Data Briefing: AMS Update Update: AgWG Phase 6 E3 and No Action Scenarios | Conference Call 5/18: Briefing/Decision: AMS Update Briefing: Demo on Tableau Data Visualization Website for Phase 6 fatal flaw review Briefing: Phase 6 Review document (Dave Montali) Conference Call 5/31: Decision: The AgWG will discuss and make a recommendation on the time-scale for future P scenarios. | Quarterly Meeting 6/28-6/29: Decision: Form an EPEG to establish charge and scope of proposed Mortality Management BMP Panel. Update: BMP Panel progress Briefing: Roadside Ditch Management Practices draft proposal Presentation: Report on exploring land-based strategies to address Conowingo infill phosphorus and sediment increases Briefing/Decision: AMS Update & presentation on Scenario Builder documentation Discussion: Phase 6 Fatal Flaw Review and review of Inputs Presentation: BMP Quick Reference Guide Review/Discussion: Phase 6 E3 and No Action Scenarios for agricultural sector | Conference Call 7/20: Decision: Finalization of draft Phase 6 E3 and No Action Scenarios Decision: Final recommendation on the time-scale for future P scenarios. Discussion: Fatal Flaw review of Phase 6 model and review of inputs. | Conference Call 8/17: (tentative) Decision: Finalization of Expert Panel Establishment Group to develop scope and charge for panel. | The AgWG made the following decision during their conference call on May 31: Decision: The AgWG made a recommendation to the WQGIT to move forward with implementing a 25-year time frame for P simulation in the initial Phase 6 scenarios. During the summer of 2017, other time-frames of 1, 10, 50, and 100 years will be tested, and this decision will be revisited during fall of 2017.
E3 and No-Action Scenarios | Brieifing on draft E3 and No Action scenarios. |  | 6/28-6/29 AgWG: Briefing: Revised E3 and No Action scenarios presented to AgWG for continued review and comment. | 7/20 AgWG: Decision: Finalization of draft Phase 6 E3 and No Action Scenarios
Ag Modeling Subcommittee (AMS) | Early April: AMS conference call to begin review of final Phase 6 input data. 4/20: Briefing: AMS update to AgWG | 5/17: AMS conference call. 5/18: Briefing/Decision: AMS agriculture model input data review recommendations | 6/28-6/29: Update: Update to the AgWG on comments from AMS on draft final Phase 6 model. Presentation on Scenario Builder documentation. |  |  | Dates and deadlines presented for the Agricultural Modeling Subcommittee are subject to change. Timeline to be determined by the Partnership.
Cropland Irrigation | Panel holds regular conference calls. | Panel holds regular conference calls. | 6/6: Face-to-face meeting for panel to discuss results of literature review. AgWG 6/28-29: Update on work of panel. | Panel holds regular conference calls. | Panel holds regular conference calls. | Panel membership was approved by the AgWG in July, and the panel held their open stakeholder meeting on September 19th at the Wye Research Center in Queenstown, MD. Panel is holding regular meetings to develop preliminary recommendations.
Agricultural Ditch | Panel holds regular conference calls. | Panel holds regular conference calls. | 6/22: Conference call for panel to discuss literature review and next steps. AgWG 6/28-29: Update on work of panel. | Panel holds regular conference calls. | Panel holds regular conference calls.
Agricultural Stormwater |  |  | AgWG 6/28-29: Discussion: Establishing formal membership of panel based on preivously developed scope of work and charge. |  |  | Panel coordinator is updating the EPEG recommendation report for review and approval by the AgWG.
Mortality Management |  |  | AgWG 6/28-29: Discussion: Forming Expert Panel Establishment Group to develop scope and charge for panel. |  | AgWG 8/17: (tentative) Decision: Finalization of Expert Panel Establishment Group to develop scope and charge for panel. | Panel coordinator will propose establishing an EPEG to draft panel charge and scope during the June AgWG quarterly meeting.