## Slide 1: CBP Partnership Proposal for Ensuring Full Accountability of Best Practices and Technologies Implemented
CBP Management Board Briefing
February 9, 2012 Conference Call

## Slide 2: Requests for Decisions/Actions
Requested Decision: MB agreement to proceed forward with the process/schedule as modified and recommended by WQGIT
Requested Action: Provide specific direction on where within the overall process and schedule the MB wants briefing updates and wants to weigh in on decision making
Requested Action: Provide specific direction on who within the Partnership will make decisions on the BMP Verification Panel membership

## Slide 3: Verification Requests
Citizen Advisory Committee
  Repeated requests for BMP verification
Chesapeake Executive Order Strategy
  USDA and EPA commitment to develop/implement mechanism for tracking/reporting ‘voluntary conservation practices’ by July 2012
NRC’s Ches Bay Independent Evaluation Report
  Five science-based conclusions focused on ‘accurate tracking of BMPs’
Chesapeake Bay TMDL’s Appendix S
  EPA expectations for offset credit verification

## Slide 4: Verification Requests
September 8, 2008 Letter
  “…EPA will use the Bay TMDL to promote transparency and accountability…”
November 4, 2009 WIP Expectations Letter
  “…reasonable assurance…”
December 29, 2009 Accountability Letter
  “…the establishment of an accountability framework…”
April 2, 2010 Phase I WIP Guide
  “Element 6: Tracking and Reporting Protocols”

## Slide 5: Verification Work Underway
NEIEN
  Successful submission of 2010 progress data
NACD
  Project for development of data collection/verification protocols for non-cost shared ag practices
USGS MOU’s with NRCS/FSA
  Improving access to federal cost-shared data
USDA Office of Environmental Markets
  Synthesis of verification of environ. credits
Responses to NRC CB Indep. Evaluation Report
  MB’s recommended responses sent to PSC

## Slide 6: Proposal to Partnership
Build a Partnership-wide BMP Verification Program working up through CBP Partnership
  Source/Habitat Workgroups GITs MB PSC
Address full array of practices across all sources
  Agricultural lands, forest lands, wetlands, developed lands, on-site treatment systems, wastewater dischargers, stream corridors, tidal shorelines
Factor in innovative approaches taken by jurisdictions, local municipalities, and conservation districts
  Recognize unique circumstances across the partnership and that one size does not fit all

## Slide 7: Verification Framework
Verification principles
  Partnership agreement on principles to guide the jurisdictions’ development/implementation of verification programs
Source sector-specific verification protocols
  Developed through the WQGIT’s source sector workgroups and Vital Habitat GIT’s habitat workgroups and approved by the Partnership
Verification panel
  Verification experts charged by the Partnership to review/make recommendations on jurisdictions’ proposed verification programs (aka BMP panels)

## Slide 8
3) CBPO Source Sector Teams’ narrative syntheses of available info on verification protocols shared with workgroups/teams
2) WQGIT review/approval to proceed with proposed approach
1) CBPO Source Sector Teams’ presentation of proposed approach to WQGIT
4a) Source Sector and Habitat Workgroups review, discuss, and agree on source sector-specific verification protocols
4b) Watershed Technical Wkgp, NEIEN Team, Bay TAS Team, and Offsets and Trading Wkgp consider implications for Partnership’s model simulation, tracking, reporting and accountability systems, offset/trading programs
5) Outcomes from all the WQGIT’s and Vital Habitats GIT’s workgroups/teams woven together into draft BMP verification principles and protocols
PROPOSED PARTNERSHIP APPROACH
Completed 1/9/2012
Work Underway
Late March 2012
Work Underway
Completed 1/9/2012

## Slide 9
6a) WQGIT review/discussion/modification/ approval to present revised draft BMP verification principles, protocols and program to Management Board
7) MB review/discussion/modification/approval to present proposed BMP verification principles, protocols and program to Principals’ Staff Committee
5) Outcomes from all the WQGIT/Vital Habitat GIT’s workgroups/teams woven together into draft BMP verification principles and protocols
8) PSC review/discussion/modification/adoption of BMP verification principles, protocols, and program for the Partnership
9) PSC communication of the Partnership’s BMP Verification Program to partners and stakeholders through some formal agreement mechanism
PROPOSED PARTNERSHIP APPROACH (Con’t)
6b) Parallel review of draft BMP verification principles, protocols and program by the other Goal Implementation Teams;
briefings for CAC, STAC, and LGAC
10) BMP Verification Panel Reviews State’s Proposed Verification Programs
Scheduled in March 2012
May/June 2012
Summer 2012
Fall 2012
Starting Fall 2012

## Slide 10: In Parallel
Federal Cost Shared Practices: Complete work by USGS through MOUs with NRCS and FSA to provide jurisdictions and wider partnership with full access to all federal cost shared agricultural conservation practices
Double Counting: Complete work by USGS, states, NRCS and FSA to put in place protocols for preventing double counting of individual practices funded by multiple sources

## Slide 11: In Parallel
Historic Data Clean-up: Jurisdictions’ completion or commitment to finish clean up for tracked and reported practices from1985 to present using CBRAP funds and/or EPA contractor resources
Practice Life Spans: Partnership agreement on practice specific life spans and information management protocols for enforcing those life spans within each jurisdictions’ NEIEN-based BMP tracking, verification and reporting system

## Slide 12: Proposed Schedule
January: WQGIT briefing/decisions on proposed approach
February: Briefings for MB, PSC and decisions to proceed with process, schedule
Jan-March: Source sector/habitat workgroups review syntheses, reach agreement on protocols
Jan-March: Workgroups/teams with model simulation, tracking, reporting, accountability, and offsets/trading responsibilities address in parallel

## Slide 13: Proposed Schedule
Late March: CBPO source sector/habitat teams weave together integrated set of draft recommendations
April: WQGIT reviews/modifies/approves set of recommendations to go to Management Board
Spring: Reviews by the other five GITs; BMP verification briefings for CAC, LGAC, and STAC
Late Spring: Convene BMP Verification Panel; seek their involvement in principles review, workgroup protocol development

## Slide 14: Proposed Schedule
May-June: MB reviews/modifies/approves set of recommendations to go to Principals’ Staff Committee
May/June: Highlight focus on BMP verification, expanded accounting for practices at EC meeting
Summer: PSC reviews/modifies/adopts the BMP verification program for the partnership and formally communicates to partners/stakeholders

## Slide 15: Proposed Schedule
Starting Fall/Winter 2012: jurisdictions present their proposed BMP verification programs to the Panel for review
2013: Following CBP Partnership approval of their BMP verification program, jurisdictions can track, verify, report, and receive credit for the full array of cost shared and non-cost shared practices
2014: Account for expanded verified practices, technologies when reporting on 2012-2013 milestones and developing 2014-2015 milestones

## Slide 16
Questions from MB Members

## Slide 17: Request for Decision
Requested Decision: MB agreement to proceed forward with the process/schedule as modified and recommended by WQGIT
  Continue forward and engage source sector and habitat workgroups as well as accounting workgroup/teams on protocol development
  Convene small ‘steering committee’ under WQGIT to guide process all the way up through final PSC decisions
  Briefing for PSC on February 16
  Briefings for CBP Advisory Committee in March

## Slide 18: Request for Action
Requested Action: Provide specific direction on where within the overall process and schedule the MB wants briefing updates and wants to weigh in on decision making
  Briefing update(s) at upcoming MB March meeting, April conference call?
  May/June review/modification/approval of draft CBP BMP Verification Program to go forward to PSC for final partnership review/adoption
  Briefings on states’ proposed verification programs starting in the summer?

## Slide 19: Request for Action
Requested Action: Provide specific direction on who within the Partnership will make decisions on the BMP Verification Panel membership
  Management Board?
  Principals’ Staff Committee?

## Slide 20
Rich Batiuk
Associate Director for Science
U.S. Environmental Protection Agency
Chesapeake Bay Program Office 410 Severn Avenue Annapolis, MD 21403
410-267-5731 (office)
443-223-7823 (cell)
batiuk.richard@epa.gov
www.chesapeakebay.net