## Slide 1: CBP BMP Verification Program Development: Progress to Date and Forthcoming Issues
CBP Principals’ Staff Committee Briefing
May 14, 2012 Meeting

## Slide 2: Progress to Date
All source sector workgroups actively developing verification protocols
BMP Verification Committee has draft set of revised verification principles about ready to share with the WQGIT and source workgroups
BMP Verification Committee has a working draft Verification Review Panel charge and membership ready for a second round of review at its mid-May conference call

## Slide 3: Forthcoming Issues
Addressing practices which are not functionally equivalent to established standards or CBP partnership approved practices
Knowing when we have established verification protocols providing assurance of effective implementation across source sectors, funding sources, and jurisdictions
What are the ‘bounds’ on supporting adaptability across jurisdictions

## Slide 4: Forthcoming Issues (Con’t)
Not pitting resources for on-the-ground implementation vs. BMP verification as though it was an either/or situation
Commitment to effectively communicating the importance of verification as an integral component of program implementation, not an undesired add-on/requirement
Addressing concerns about the request for historical data clean-ups and the resources required
Address concerns about verification process in regard to trading programs.

## Slide 5: Revised Schedule
June: initial review of all the elements of the partnership’s verification program—principles, protocols, and panel—to determine what fits, what doesn’t (late March)
July: reviewing the backbone of the basinwide verification program—the states’ existing tracking and reporting systems
Sept: review of all the revised elements and ask the question—are we ready to move the proposed verification program up the partnership management structure? (April)

## Slide 6: Revised Schedule (Con’t)
Oct: WQGIT review/approval (April)
Nov: MB review/approval (May/June)
Dec: PSC review/approval (Summer 2012)
Winter 2012/2013: PSC communication of the Partnership’s BMP Verification Program to partners/stakeholders through some formal agreement mechanism (Fall 2012)
Spring 2013: BMP Verification Review Panel reviews states’ proposed verification programs (Starting fall 2012)

## Slide 7: Requests for Action
Requested Action: Approval to proceed forward with the revised (reality checked) schedule.

## Slide 8
Rich Batiuk
Associate Director for Science
U.S. Environmental Protection Agency
Chesapeake Bay Program Office 410 Severn Avenue Annapolis, MD 21403
410-267-5731 (office)
443-223-7823 (cell)
batiuk.richard@epa.gov
www.chesapeakebay.net