## Slide 1: Concepts and Timeline for Developing a CBP Biennial Strategy Review System DRAFT August 29, 2016 DRAFT

## Slide 2: Biennial Strategy Review System Why is it needed?
Fulfill 2014 Chesapeake Bay Watershed Agreement (Agreement) commitment to biennially re-evaluate and update management strategies. PSC is required to report on implementation to the Executive Council.
Support PSC charge to use the Decision Framework to adaptively manage (later re-affirmed in the Agreement).
Establish consistent method for identifying changes to goals and outcomes articulated through the Agreement.
Utilize the Indicators Framework to track progress toward outcomes, to understand what factors influence outcome achievement, and whether the program did what it said it would do.
Support evolving partnership needs related to accountability, transparency, and decision-support identified through stakeholder research.
Promote core values such as flexibility, trust, open conversation, efficiency, predictability, collaboration, and solution-finding.

## Slide 3: The Timeline How do we do it?
Planned two-year schedule
Regular meetings designed to accomplish specific objectives
Work-planning/in-depth discussions distributed throughout the year
Appropriate decision-makers provided with robust information to guide work
Clearly defined process and outputs.

## Slide 4
Date | Action
August 2, 2016 | Present draft options to GIT6. Solicit input for revisions.
August 30, 2016 | Present revised draft options to GIT Chairs. Present during GIT Chairs meeting, have Chairs review and comment.
September 6, 2016 | GIT 6 and STAC representatives review comments from GIT Chairs and modifies options as needed.
September 2016 | Present revised draft options to the Management Board for review and discussion.
October 2016 | Revise and edit the draft Operational Plan to incorporate Management Board suggestions at full-day GIT6 meeting.
November 2016 | Present recommended draft to the Management Board and conduct a “test run” scenario at the MB meeting (i.e., Blue Crab).
December 2016 | Present final draft of Operational Plan to Management Board for approval and implementation.
Biennial Strategy Review System – Development Timeline

## Slide 5: Biennial Strategy Review Meetings Types and Purpose
2-Day Biennial Review
EC
PSC
Biennial Review Meeting – High-level retrospective program-wide review to celebrate our successes and identify important stories. Discuss developments in environmental (monitoring, science) and economic (available resources) conditions, and results of program evaluations (e.g., Independent Evaluator). Identify science needs and future focus for GIT Progress meetings, and summarize recommendations to be reported to the PSC.
Principals’ Staff Committee – Provide input on any significant shifts in strategy and approval of outcome changes, with public input, resulting from the Biennial Review to prepare for PSC report on implementation progress to the Executive Council.
Executive Council – Concurrence and partner commitment to significant strategy shifts and approval of goal/outcome changes.
Goal Implementation Teams Progress Sessions – Review management strategy and work plan progress highlighting successes, challenges and obstacles. Provide rationale for any planned shifts in strategies and workplans. Receive input and problem solving support from Management Board, including Advisory Committee chairs.
Interim Management Board Meetings – As needed, follow-up on issues identified in GIT Progress Sessions, new issues related to challenges or strategy shifts, other business.
GIT Progress MB Sessions
Time-sensitive Topics

## Slide 6: Meetings Content Standardization Simplifying our work
Standard, easy to use templates would support developing:
  Pre-brief background papers
  Goal Implementation Team progress session presentation
  Materials for Interim Management Board meetings on issues that arise between progress meetings
Templates would include a standard series of questions to focus the reviews, such as:
  What are the major accomplishments?
  What are the barriers?
    Proposed solutions
    Needed resources

## Slide 7
2017
Jan.
Mar.
Feb.
May
Apr.
Jun.
Jul.
Aug.
Oct.
Sep.
Nov.
Dec.
Jan.
Mar.
Feb.
Apr.
2018
2018
May
Jul.
Jun.
Sep.
Aug.
Oct.
Nov.
Dec.
Feb.
Jan.
Mar.
Apr.
May
Jul.
Jun.
Aug.
2019
2-day Biennial Review
Biennial “Concept Timeline”
Interim Meeting Objectives
Resolution of specific issues and challenges
Information sharing
PSC
PSC
PSC
EC
EC
EC
2-day Biennial Review
Periodic GIT Progress
MB Meeting
Periodic GIT Progress
MB Meeting
Periodic GIT Progress
MB Meeting
Periodic GIT Progress
MB Meeting
Time-sensitive Topics
Time-sensitive Topics
Time-sensitive Topics
Time-sensitive Topics

## Slide 8
PSC
2017
Jan.
Mar.
Feb.
May
Apr.
Jun.
Jul.
Aug.
Oct.
Sep.
Nov.
Dec.
Jan.
Mar.
Feb.
Apr.
2018
2018
May
Jul.
Jun.
Sep.
Aug.
Oct.
Nov.
Dec.
Feb.
Jan.
Mar.
Apr.
May
Jul.
Jun.
Aug.
2019
2-day Biennial Review
Categories (based on GITs)
Sustainable Fisheries (GIT1)
Protect & Restore Vital Habitats (GIT2)
Protect & Restore Water Quality (GIT3)
Maintain Healthy Watersheds (GIT4)
Foster Chesapeake Stewardship (GIT5)
Enhance Partnering, Leadership and Management & Climate Resiliency (GIT6 & CRWG)
2-day Biennial Review
EC
PSC
EC
PSC
EC
OPTION 1 – Progress Sessions organized by GITs
Sustainable Fisheries (GIT1)
- Blue Crab (2)
- Oysters
- Forage Fish
- Fish Habitat
- Wetlands
- Black Duck
- Stream Health
- Brook Trout
- Fish Passage
- SAV
Vital Habitats (GIT2)
- Forest Buffer
- Tree Canopy
- 2017, 2025 WIPs
- WQ Standards Attainment & Monitoring
- Toxic Contaminants (2)
Water Quality (GIT3)
Healthy Watersheds (GIT4)
- Healthy Watersheds
- Land Use Methods & Metrics Development
- Land Use Options Evaluation
Stewardship (GIT5)
- Citizen Stewardship
- Diversity
- Environmental Literacy (2)
- Protected Lands
- Public Access
Partnering/Leadership & Climate (GIT6, STAR)
- Local Leadership
- Climate Monitoring & Assessment
- Climate Adaptation

## Slide 9: Option 1 GIT Themes
Pros:
Each GIT has day devoted to its issues for discussion of progress
Meetings only once per 2 years.
Cons:
Doesn’t foster cross-GIT discussion and participation
Indicator data not always timely
Challenging for some GITs with many outcomes
Opportunity for in-depth discussion with MB too infrequent.

## Slide 10
2017
Jan.
Mar.
Feb.
May
Apr.
Jun.
Jul.
Aug.
Oct.
Sep.
Nov.
Dec.
Jan.
Mar.
Feb.
Apr.
2018
2018
May
Jul.
Jun.
Sep.
Aug.
Oct.
Nov.
Dec.
Feb.
Jan.
Mar.
Apr.
May
Jul.
Jun.
Aug.
2019
2-day Biennial Review
2-day Biennial Review
Categories (based on current Communication Themes)
Abundant Life – GIT 1&2
Climate – STAR
Clean Water – GIT 3&4
Conserved Lands, Engaged Communities, Local Gov’t – GIT 5&6
PSC
PSC
EC
EC
EC
OPTION 2 – Bi-annual Progress Sessions organized by current Communication Themes
PSC
Climate Resiliency
- Climate Adaptation
- Climate Monitoring and Assessment
Clean Water
- 2107 WIPs
- 2025 WIPs
- WQ Standards Attainment/Monitoring
- Toxic contaminants (2)
Conserved Lands, Engaged Communities, Local Gov’t
- Land Use Methods/Metrics Dvlpmt.
- Land Use Options Evaluation
- Protected Lands
- Stewardship/ Public Access, etc.
- Fish Passage
- Forest Buffers
- Stream Health/ Br. Trout
- SAV
- Tree Canopy
Abundant Life
- Blue Crab (2)
- Fish Habitat
- Forage Fish
- Oysters
- Wetlands
- Bl. Duck

## Slide 11: Option 2 Communication Themes
Pros:
Complementary outcomes discussed together supports more cross-GIT collaboration
Aligns with existing communications themes.
Cons:
Some outcome discussions will be unwieldy, e.g., abundant life has 13 outcomes
Potential lack of timely indicator data
Meetings infrequent with much to cover.

## Slide 12
Jan.
2017
Jan.
Mar.
Feb.
May
Apr.
Jun.
Jul.
Aug.
Oct.
Sep.
Nov.
Dec.
Jan.
Mar.
Feb.
Apr.
2018
PSC
2018
May
Jul.
Jun.
Sep.
Aug.
Oct.
Nov.
Dec.
Feb.
Mar.
Apr.
May
Jul.
Jun.
Aug.
2019
OPTION 3 (recommended)– QUARTERLY Progress Sessions organized to foster integrated outcome discussions (& tied to release of indicator data)
Categories: Integrated Outcomes (tied to release of indicators)
Healthy Watersheds (GIT: 1, 2, 4, 5)
Water Quality (GIT: 3, 4)
Crabs as Ecosystem Snapshot (GIT: 1, 2)
Connected Bay System (GIT: 1, 2, 4)
Change & Resiliency (GIT: 2, CW)
Culture of Stewardship (GIT: 5, 6)
Taking Action on Toxics (GIT: 3, 4)
Next Generation of Stewards (GIT: 5)
2-day Biennial Review
2-day Biennial Review
EC
PSC
PSC
EC
EC
Healthy Watersheds
- Healthy Watersheds
- Protected Lands
- Stream Health/Brook Tr.
- Tree Canopy
- Fish Habitat
Water Quality
- 2017/25 WIPs
- Standards Attain.
- Land Use Methods
- Forest Buffers
Crabs/Eco Snapshot
- Bl. Crab Abundance
- Bl. Crab Mgmt.
- SAV
Connected Bay System
- Forage Fish
- Fish Passage
- Oysters
- Land Use Options
Change & Resiliency
- Wetlands
- Black Duck
- Climate Resiliency
Stewardship
- Citizen Stewardship
- Local Leadership
- Public Access
- Diversity
Action on Toxics
- Toxics Policy/Prevnt.
- Toxics Research
- Land Use Meth./Metrics
Next Gen Stewards
- Stud. Env. Literacy
- Env. Lit. Planning
- Sust. Schools
Healthy Watersheds
- Healthy Watersheds
- Protected Lands
- Stream Health
- Tree Canopy
- Fish Habitat

## Slide 13: Option 3: Recommended Cross-outcome/indicator Themes
Pros:
Encourages most cross-outcome/cross-GIT collaboration
Planned around cross-outcome story lines and logic yielding key opportunity for meaningful strategy changes (if needed)
Tied to indicators data release ensuring timely information
Facilitates more robust discussion with fewer outcomes/meeting.
Cons:
GITS will need to present multiple times through the year on different outcomes.

## Slide 14: Decision Governance Model

## Slide 15
Management Board recommends to PSC whether changes, additions, deletions are needed (p. 3).
PSC recommends, Executive Council decision (p. 3).
Make correction.
No elevation necessary.
        Are there corrections to the MS that will improve achievement of the outcome?
GIT proposes changes.
          Are modifications to the Goal necessary?
No
Yes
Yes
No
Are the Workplan actions being completed as expected?
Can barriers be removed by GIT or Workgroup action?
Elevation to Management
Board necessary. 3, 4
      Seeing expected outcome/indicator/
      measure improvement?
Yes
No elevation necessary. 2
No 1
Yes
No
Yes
No
PSC moves forward with modification of outcome, with public input. Modification published on web (p 3).
          Are modifications to the Outcome necessary?
Yes
No
        1 Review Management Strategy (p. 15) assumptions, factors, and approaches to determine if changes need to be made to Management Strategy approaches, factors influencing, monitoring, etc.
        2 Workplan updated with next biennial actions; signatories update participation (p. 3).
        3 Either at Biennial Review or at “special emphasis” slot in regular Management Board meeting (depending on urgency and critical path).
4 Management Board Action: identify other GITs/Workgroups/Advisory Committees that would help resolve barrier(s), identify action(s) a signatory can take, elevate to PSC, etc.
= GIT decision; MB informed
= MB decision; PSC informed
= PSC decision; EC informed
= EC decision