Brook Trout WG 2021 SRS Cycle

SRS Check in: Yet to be scheduled, should be scheduled for some time in late May.

- Highlight our current logic and action plan

- Write Narrative analysis

- Meet with SRS team to discuss documents and common requests with other work groups

STAR Materials Due: July 15th

- DRAFT 2022-2023 logic and action plan

- DRAFT QPM Presentation

- DRAFT Management Strategy

- Narrative analysis

STAR Dry Runs: July 22nd

- Receive feedback from STAR on presentation and documents

QPM Materials Due: July 26th

- FINAL 2022-2023 Logic and Action Plan

- FINAL Presentation

- FINAL Narrative Analysis

- FINAL Management Strategy

QPM: August 12th

- Deliver presentation

Near Final SRS Materials Due: November 10th

- Near Final Presentation

- Near Final Logic and Action Plan

- Near Final Narrative Analysis

- Near Final Management Strategy

Signatory Review begins: November 11th

Signatory Review Ends: November 29th

Final Materials Due: December 8th

- Final Presentation

- Final Logic and Action Plan

- Final Narrative analysis

- Final Management Strategy

Final Materials Presented to MB: December 9th