## Sheet1
EVOLVING List of Updates & Changes to be Considered for CAST-23 and the Phase 7 Version of CAST Last Update 8/18/21
BMPs | ORIGINAL APPROVAL | AgWG Priority Level | Potential TIMELINE | JURISDICTIONS | LEAD | CBPO Contact | ACTION | NOTE | Status
Dairy Precision Feeding | Simpson & Weammert, 2009 https://archive.chesapeakebay.net/pubs/BMP_ASSESSMENT_REPORT.pdf | ? | Possible for 2021 Progress- if approved by relevant groups in the partnership. | PA | Bill Angstadt (PA) | Mark Dubin | Proposal for suggested change in implementation tracking based on updated science to be presented to the AgWG. | PA actively working on solution to tracking challenges. Seeking flexibility in CBP requirements. This would require a change to the Simpson & Weammert (2009) report recommendations. Dr. Virginia Ishler (Penn State) and Dr. Kathy Soder (ARS), both involved in original recommendations, have more recent reserach on dairy herds and MUN levels. Jennifer Reed-Harry (Penn Ag Ind. Assoc.) & Ron Ohrel (Mid-Atlantic Dairy Assoc.) working on dairy processor co-op sub-population verification. Brady Seeley (DEP) writing up a narrative of path forward. Interested in tracking % of PA dairy population under DPF versus individual herd management. Up to 70% of PA dairy population may use DPF. | Bringing dairy expertise to AgWG/Ad Hoc to review new science. PA assembled team to discuss new science, tracking, and reporting for dairy presicion feeding. June AgWG presentation on MUN research. PA and CBPO working on proposal to present at future AgWG for approval.
Rotational/Precision Grazing | STAC, 2010 https://cast.chesapeakebay.net/FileBrowser/GetFile?fileName=GrazingPastureMgmt2010.pdf | N/A | N/A | PA (withdrawn) | N/A | N/A | No Action |  | Withdrawn
Heavy Use Area Protection (HUAP) | Loafing Lot BMP, 2003 | N/A |  | PA | Ted Tesler | Mark Dubin, Loretta Collins | No Action. RESOLVED 01/13/20 | Track & Reporting issue. Can NRCS 561 reported as Loafing Lot Management? Is 561 exclusive to Loafing Lots (non-poultry) across all jurisdictions? Every state tracks differently, some can differentiate poultry pads from loafing lots. | Withdrawn
Heavy Use Area Protection (HUAP) - Poultry Pads | AWMS EP 2016 | N/A | N/A | MD, DE, WV (withdrawn) | N/A | N/A | No Action. RESOLVED 11/13/20 | Concern regarding crediting for poultry pads. Language included in 2016 AWMS EP report. Poultry pads defined as part of AWMS BMP. | Withdrawn
Winter Crop (proposed) | Cover Crop Expert Panel 2016 https://www.chesapeakebay.net/documents/Phase_6_CC_EP_Final_Report_12-16-2016-NEW_TEMPLATE_FINAL.pdf | ? | Phase 7 (possibly sooner) | PA, NY, MD |  | Loretta Collins | Fall 2021 AgWG update | PA no change in EP recs, "WINTER CROP" proposal (EP)- corn silage-man-forage (multi-species foraging & feed- greenchop. "triple cropping" over two years. Charlie White (Penn State) research. Man N uptake (not leached) NEW SCIENCE! AgWG consider EP for winter crop. legume/legume-grass hay LU as most appropriate for application of BMP. | Fall 2021 AgWG Update; July 2021 AgWG AdHoc discussion; Jan 2021 Charlie White AgWG talk; Ken Staver 2021 AgWG discussion
USDA-NRCS/CBP BMP Correspondence | N/A | ? | Annual Updates | All | Olivia Devereux | Olivia Devereux |  | A crosswalk of NRCS practice names and codes to the CAST BMP name may be helpful in selecting the CAST BMP that best represents your management action. https://cast.chesapeakebay.net/Documentation/BMPs | On-going, as needed updates.
MODELING | ORIGINAL APPROVAL/CROSSOVER | Priority Level | Potential TIMELINE | JURISDICTIONS | LEAD | CBPO Contact | ACTION | NOTE | Status
Manure Treatment & Transport | MTT EP 2016 https://www.chesapeakebay.net/documents/MTT_Expert_Panel_Report_WQGIT_approved_Sept2016.pdf Phase 6 CBWM 2017 | ? | Phase 7 | PA, MD |  | Loretta Collins | PA request to AgWG for study group; Check w/ MWG on progress on refined modeling efforts and efforts in general for the CBWM. | Backfill, Local tracking of manure; 1. PA needs better tracking and reporting- pilot project Penn Ag Industries lead, SCC, PA 4r Alliance, manure-haulers & brokers possible regulartory change 2. PA wants study group on inter-county manure transport county-level budgets. AgWG study group: how to do this? Need farmers to reduce applications but need to move. Liq manure tansport is short distances- NEED INCENTIVES for short-distance MT. MTT- Jason/Ted | Further discussion needed with Modeling WG. Will finer scale modeling provide opportunity for finer scale accounting for manure transport?
Ag Loading Rates | Ag Loading Rate Review Steering Committee Agricultural Modeling Subcommittee (AMS), 2016 | ? | Phase 7 | All |  |  |  | Review of ag loading rates determined by committee under the Agricultural Modeling Subcommittee (AMS) in development of the Phase 6 CBWM. Associated with concerns regarding N loads attributed to soybean land use (loading includes impact of N fixation on residual soil N) | Fall 2021 AgWG determination of how to address Phase 7 data update needs. Who will do this, how, and when.
Pasture Nutrient Management | NM EP 2016; Phase 6 CBWM 2017 | N/A | N/A | PA, NY (Withdrawn) | N/A | N/A | N/A | Nutrient spread curves; Manure eligible for beans (for sulfur) full season and bean sm gr. Winter Crops (EP); Nutrient Spread Slopes: request to limit pasture applications due to unintended consequences. Reviewed current eligibility in CAST source data. RESOLVED 11/13/20. | Withdrawn
Animal Populations (General) | Phase 6 CBWM | ? | Next Watershed Model Model | All | Mark Dubin | Mark Dubin |  | Improvements in accounting and distribution of animal population data to more accurately reflect ag production in the CBW; challenge with Ag Census data are the assumptions and distributions that have to be made where the census provides "(D)" for a particular crop/animal in a county; areas where the census does not provide county scale data seems provide the opportunity to seek additional state/local/industry data to inform the process of assigning appropriate data to the county. | Fall 2021 AgWG determination of how to address Phase 7 data update needs. Who will do this, how, and when.
AG DATA INPUTS | ORIGINAL APPROVAL | Priority Level | Potential TIMELINE | JURISDICTIONS | LEAD | CBPO Contact | ACTION | NOTE | STATUS
Animal: Dairy | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD, NY | Vanessa Van Note, Ruth Cassilly | Vanessa Van Note | CBPO looking into the possibilty of using annual NASS survey for dairy | Annual NASS Survey may help improve accuracy between census trends. | On-going. Seek periodic updates
Animal: Equine | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD, ? | TBD | CAST Team |  | May currently be using best data available. Additional NASS data sources may not capture full profile of horse ownership. | On-going. Seek periodic updates
Animal: Beef | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD, ? | TBD | CAST Team |  | May currently be using best data available. Additional NASS data sources may not capture full spectrum of beef operations. | On-going. Seek periodic updates
Crop: Annual Implementation Reports (AIR) | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD | TBD | Mark Dubin | Jason Keppler reach out to MD USDA office | USDA Partners- NRCS | On-going. Seek periodic updates
Crop: USDA-FSA crop reporting | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD | TBD | Mark Dubin |  | USDA Partners?; NRCS Nation comm crop index. Ind. crops by county. (FSA crop reporting) | On-going. Seek periodic updates
Fertilizer Sales Data | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD, PA, VA, NY | States, Industry Partners | Mark Dubin |  | Lindsay Thompson, Janelle Eck/ MDA organizing review with state chem (MD) to be followed by PA and other Bay States. DE has engaged in clean-up of data in recent years. Create a template in MD and move to other states. May be redundancy in reporting by registrants. | MDA in discussions with state chemist, Lindsay T. and Janelle E.