## Sheet1
BMPs | ORIGINAL APPROVAL | Priority Level | CAST-21 | TIMELINE | JURISDICTIONS | LEAD | CBPO Contact | ACTION | NOTE | Status
Dairy Precision Feeding | Simpson & Weammert, 2009 | PA Leading | Possible for 2021 Progress- if approved by relevant groups in the partnership. | TBD | PA | Bill Angstadt (PA) | Mark Dubin | Presentation to AgWG/Ad Hoc on recent MUN research and suggested change in implementation tracking based on updated science. Dairy expertise necessary (e.g. Penn State dairy specialist). | PA actively working on solution to tracking challenges. Seeking flexibility in CBP requirements. This would require a change to the Simpson & Weammert (2009) report recommendations. Dr. Virginia Ishler (Penn State) and Dr. Kathy Soder (ARS), both involved in original recommendations, have more recent reserach on dairy herds and MUN levels. Jennifer Reed-Harry (Penn Ag Ind. Assoc.) & Ron Ohrel (Mid-Atlantic Dairy Assoc.) working on dairy processor co-op sub-population verification. Brady Seeley (DEP) writing up a narrative of path forward. Interested in tracking % of PA dairy population under DPF versus individual herd management. Up to 70% of PA dairy population may use DPF. | Bringing dairy expertise to AgWG/Ad Hoc to review new science. PA leading effort.
Rotational/Precision Grazing | STAC, 2010 | N/A | N/A | N/A | PA (withdrawn) | N/A | N/A | No Action |  | Withdrawn
Heavy Use Area Protection (HUAP) | Loafing Lot BMP, 2003 | PA Leading | Possible for 2021 Progress- if approved by relevant groups in the partnership. |  | PA | Ted Tesler | Mark Dubin, Loretta Collins | Request info tracking of barnyard BMPs across states. Loretta will work with Ted on gather information. | Track & Reporting issue. Can NRCS 561 be crosswalked to Loafing Lot Management? Is 561 exclusive to Loafing Lots (non-poultry) across all jurisdictions? | Requesting information on tracking and reporting methods of AWMS and Barnyard BMPs from each jurisdiction. PA leading leading effort.
Heavy Use Area Protection (HUAP) - Poultry Pads | AWMS EP 2016 | N/A | N/A | N/A | MD, DE, WV (withdrawn) | N/A | N/A | No Action. RESOLVED 11/13/20 | Concern regarding crediting for poultry pads. Language included in 2016 AWMS EP report. Poultry pads defined as part of AWMS BMP. | Withdrawn
Winter Crop (proposed) | NM Expert Panel 2016 |  | No | Next Watershed Model (possibly sooner) | PA, NY, MD |  | Vanessa Van Note | Loretta reach out to Dr. White, AgWG presentation in early 2021? | PA no change in EP recs, "WINTER CROP" proposal (EP)- corn silage-man-forage (multi-species foraging & feed- greenchop. "triple cropping" over two years. Charlie White (Penn State) research. Man N uptake (not leached) NEW SCIENCE! AgWG consider EP for winter crop. legume/legume-grass hay LU as most appropriate for application of BMP. | Further discussion in Ad Hoc and invitation to brign expertise to AgWG/Ad Hoc.
MODELING | ORIGINAL APPROVAL/CROSSOVER | Priority Level | CAST-21 | TIMELINE | JURISDICTIONS | LEAD | CBPO Contact | ACTION | NOTE | Status
Manure Treatment & Transport | MTT EP 2016, Phase 6 CBWM 2017 | ?/next model phase | No | Next Watershed Model | PA, MD |  | Vanessa Van Note | PA request to AgWG for study group; Check w/ MWG on progress on refined modeling efforts and efforts in general for the CBWM. | Backfill, Local tracking of manure; 1. PA needs better tracking and reporting- pilot project Penn Ag Industries lead, SCC, PA 4r Alliance, manure-haulers & brokers possible regulartory change 2. PA wants study group on inter-county manure transport county-level budgets. AgWG study group: how to do thi? Need farmers to reduce applications but need to move. Liq manure is short distance- NEED INCENTIVES for short-distance MT. MTT- Jason/Ted | Further discussion needed with MWG.
Pasture Nutrient Management | NM EP 2016; Phase 6 CBWM 2017 | N/A | N/A | N/A | PA, NY (Withdrawn) | N/A | N/A | N/A | Nutrient spread curves; Manure eligible for beans (for sulfur) full season and bean sm gr. Winter Crops (EP); Nutrient Spread Slopes: request to limit pasture applications due to unintended consequences. Reviewed current eligibility in CAST source data. RESOLVED 11/13/20. | Withdrawn
AG DATA INPUTS | ORIGINAL APPROVAL | Priority Level | CAST-21 | TIMELINE | JURISDICTIONS | LEAD | CBPO Contact | ACTION | NOTE | STATUS
Animal: Dairy | Phase 6 CBWM | High: on-going | Possible, Workplan TASK 1 | Update Jan 2021 | MD, NY | Loretta | CAST Team | Loretta Collins will look into the possibilty of using annual NASS survey for dairy | Annual NASS Survey use to improve accuracy of between census trends. Loretta having starting converstions with CBPO. | On-going. Seek periodic updates
Animal: Equine | Phase 6 CBWM | ? | Possible, Workplan TASK 1 | Milestone Updates | MD, ? | TBD | CAST Team |  | May currently be using best data available. Additional NASS data sources may not capture full profile of horse ownership. | On-going. Seek periodic updates
Animal: Beef | Phase 6 CBWM | ? | Possible, Workplan TASK 1 | Milestone Updates | MD, ? | TBD | CAST Team |  | May currently be using best data available. Additional NASS data sources may not capture full spectrum of beef operations. | On-going. Seek periodic updates
Crop: Annual Implementation Reports (AIR) | Phase 6 CBWM | High: on-going | Possible, Workplan TASK 1 | Milestone Updates | MD | TBD | Mark Dubin | Jason Keppler reach out to MD USDA office | USDA Partners- NRCS | On-going. Seek periodic updates
Crop: USDA-FSA crop reporting | Phase 6 CBWM | High: on-going | Possible, Workplan TASK 1 | Milestone Updates | MD | TBD | Mark Dubin | Jason reach out to Mark: Bill will share crop info with the group | USDA Partners?; NRCS Nation comm crop index. Ind. crops by county. (FSA crop reporting) USDA-CBP Liaison position needs to be filled. Actioning NRCS chief Kevin Norton | On-going. Seek periodic updates
Fertilizer Sales Data | Phase 6 CBWM | High: on-going | Possible, Workplan TASK 1 | Milestone Updates | MD, PA, VA, NY | States, Industry Partners | Mark Dubin | Updates? | Lindsay Thompson, Janelle Eck/ MDA organizing review with state chem (MD) to be followed by PA and other Bay States. DE has engaged in clean-up of data in recent years. Create a template in MD and move to other states. May be redundancy in reporting by registrants. | On-going. Seek periodic updates