## Sheet1
GIT | GIT Needs from STAR | Timeline | Completed Y/N | Timeline | STAR workgroup
Water Quality | WQ Criteria Attainment patterns summary | June, 2016 | Y |  | 2018 manuscript
| Update in patterns in WQ standards attainment DO, clarity/SAV and chlorophyll | December, 2016 | Y
| Publish WQ Criteria Tech Addendum | December, 2016 | Published 2017 |  | CAP WG
| Implement new process to quantify trends in tidal WQ parameters | Annually in 2016/2017 | yes, paper being completed |  | Integrated Trends and Analysis Team (ITAT)
| WQ results attained from 2 of 6 high flow events for mid point assessment | 2017 | yes, extended into 2017 |  | DNR/UMCES/USGS
| Monitor high flow events at Conowingo | On/before May 30, 2016 | yes, extended into 2017 |  | DNR/UMCES/USGS
| Conowingo impacts on WQ monitoring plans | On/before May 30, 2016 | DNR set up study |  | ITAT
| 125 sites of nutrient and sediment samples | 2016-2017 | Y |  | IMN WG needed to maintain network
| Update loads and Trends USGS | 2016-2017 | Y
| USGS to update reporting/communicating of loads to Bay | 2016 | Y (2016); in progress for 17 |  | ITAT/USGS
| expand on BEI report for add'l monitoring needs | 2016-2017 | Will use this process
| Incorporate Citizen Science Monitoring for WQ standards |  | In progress |  | Criteria Assessment Protocol WG
| develop targeted shallow water monitoring strategy |  | IN progress |  | Integrated Monitoring Networks WG
| Test watershed factors influencing WQ trends in tidal waters | 2016-2017 | In progress, 2018 |  | ITAT
| Release report/communication of nitrogen sources | 2016-2017 | Synthesis report, 2018 |  | ITAT
| Compare observed and expected trends in watershed |  | Synthesis report, 2018 |  | ITAT
| Improve knowledge of sed and N sources |  | Synthesis report, 2018 |  | ITAT
| Use WQ data to assess PA's progress |  | Ongoing |  | Modeling WG
| WQ functions of wetlands |  | Synthesis report, 2018
| Improve understanding of tidal water response to load changes |  | Synthesis report, 2018 |  | ITAT
| Develop land cover dataset | 2016 | Y |  | Land Cover WQ
| Enhance watershed and SPARROW model |  | Y |  | Modeling WG
| Examine Susquehanna reservoirs' impact on N and sed transport |  | Y |  | Modeling WG
| Assess N and sed response to management practices |  | Synthesis report, 2018 |  | ITAT/Modeling WG
| Incorporate BMP efficiencies and land cover/use | Oct. 2015 - October 2016 | Y |  | Modeling WG
| Conduct STAC peer reviews | Winter/Spring 2016 | Y |  | STAC/Modeling WG
| Run scenarios and modeling tools | January 2016 - September 2016 | Y |  | Modeling WG
| Maintain and grow tidal and nontidal monitoring networks | Annual | In progress priority |  | IM WG
TOXIC CONTAMINANT WG NEEDS TO BE ADDED.
| Approve Nontraditional Partner/Cit sci data MOU | 2018
| WQ Stds Indicator Trend publication | 2018
| Incorporate Citizen Science Monitoring for WQ standards (publication through Citizen Science Association journal) | 2018
Note on B2: CRCStaffers: Summarize patterns in water-quality criteria attainment over time in tidal waters from 1985-2014
Note on D2: Williams, Michelle: Presented with other standards attainment data at 11/27/17 WQGIT conference call
Note on B3: CRCStaffers: Provide an update describing temporal and regional patterns in water quality standards attainment of dissolved oxygen, water clarity/SAV and chlorophyll.
Note on D3: Williams, Michelle: Trends presented by Qian Zhang at 11/27/17 WQGIT conference call
Note on B4: CRCStaffers: Publish a new Ambient Water Quality Criteria Technical Addendum that provides updated guidance on water quality standards attainment assessment methods for the tidal bay jurisdictions
Note on D4: Williams, Michelle: Responses to STAC comments on 2017 draft addendum were presented at 11/13/17 WQGIT conference call
Note on B5: CRCStaffers: Implement new process for quantifying trends in tidal water-quality parameters. The new process incorporates advances in methods to provide more information on trends in water-quality patterns over time.
Note on B6: CRCStaffers: Water quality results attained from 2 of the 6 high flow events assessed in April 2015 will be submitted to the CBP to be included in the 2017 CB Mid Point Assessment
Note on B7: CRCStaffers: Monitor any high flow event of greater than 100,000 cfs at Conowingo Dam occurring before May 30, 2016
Note on B8: CRCStaffers: Develop alternative monitoring plans to gather sufficient information to inform Conowingo impacts on Bay water quality standards now that it has reached "dynamic equilibrium" in the event than less that 6 high flow events occur before May 30, 2016
Note on B9: CRCStaffers: The partners in the network will collect nutrient and sediment samples from over 125 sites throughout the watershed.
Note on D9: Williams, Michelle: 115 nontidal monitoring stations data used in loads and trends analysis presented to WQGIT at 2/12/18 conference call
Note on B10: CRCStaffers: The USGS will work with the partners to compile quality assure the information to update loads and trends.
Note on D10: Williams, Michelle: final presentation from Doug Moyer at 2/12/18 WQGIT conference call
Note on B11: CRCStaffers: USGS will completely update the reporting of loads to the Bay and trends of nutrients and sediment loads in the watershed; revised products will be prepared to communicate these results.
Note on B12: CRCStaffers: Expand upon the water quality-focused Building Environmental Intelligence report to a new process to address additional monitoring needs associated with the 2014 Chesapeake Bay Agreement. Integrate the role of Citizen Science to address gaps in water quality-related monitoring and assessment needs. Work with partners and Management Board to consider and attempt to implement recommendations.
Note on B13: CRCStaffers: Coordinate and integrate Citizens Monitoring effort funded by the Chesapeake Bay Program. Develop high quality citizens monitoring programs to assess water quality standards. Target areas where implementation will potentially show progress.
Note on D13: Williams, Michelle: Project update from Chesapeake Monitoring Network at 10/23/17 WQGIT conference call
Note on B14: CRCStaffers: Develop strategy to target shallow water monitoring program with limited resources. Incorporate all spatially and temporally intensive monitoring results into Bay water quality standards attainment.
Note on B15: CRCStaffers: Test watershed factors influencing water-quality trends in tidal waters.
Note on B16: CRCStaffers: Release of a report and communication products regarding nitrogen sources and transport processes in smaller agricultural and urban watersheds.
Note on B17: CRCStaffers: Compare observed and expected trends in the watershed and relation to management actions.
Note on B18: CRCStaffers: Improve knowledge of sediment and nitrogen sources and residence times.
Note on B19: CRCStaffers: Utilize empirical, historical and current water quality data to assess Pennsylvania's progress towards meeting goals.
Note on B20: CRCStaffers: Improve knowledge of the water-quality functions of created and restored nontidal wetlands.
Note on B21: CRCStaffers: Support efforts to improve the understanding of tidal water response to changes in watershed loads.
Note on B22: CRCStaffers: Develop a new land-cover data set for the CBP watershed model.
Note on D22: Williams, Michelle: 1-meter land cover dataset developed for inclusion in Phase 6 Watershed Model prior to model release in 2017
Note on B23: CRCStaffers: Enhance the CBP watershed model using USGS measured loads for calibration as well as SPARROW model, groundwater models and other science findings.
Note on D23: Williams, Michelle: SPARROW incorporated into Phase 6 Watershed Model as part of multiple modeling approach
Note on B24: CRCStaffers: Examine the impact of Susquehanna reservoirs on changes in nutrient and sediment transport to Chesapeake Bay.
Note on D24: Williams, Michelle: Lower Susquehanna Watershed Assessment Report released march 2016 (USACE)
Note on B25: CRCStaffers: Better utilize monitoring data to assess progress and explain observed changes in nutrients and sediment in response to management practices.
Note on B26: CRCStaffers: Incorporate data inputs, such as BMP efficiencies and land use/land cover
Note on D26: Williams, Michelle: Incorporated into Phas 6 Watershed Model/CAST
Note on B27: CRCStaffers: Regarding MA3 KA4. Release beta and final version of the Phase 6 Watershed Model
Note on D27: Williams, Michelle: Done in December 2016
Note on B28: CRCStaffers: Regarding MA3 KA4. Release beta and final version of the Phase 6 Watershed Model
Note on D28: Williams, Michelle: Key scenarios (No action, E3, Phase II WIPs, and progress runs done)
Note on B33: CRCStaffers: Coordinate and integrate Citizens Monitoring effort funded by the Chesapeake Bay Program. Develop high quality citizens monitoring programs to assess water quality standards. Target areas where implementation will potentially show progress.