## Table of Issues
EVOLVING* List of Agricultural Updates & Changes to be Considered for Future CAST Versions & Phase 7
Last Update 02/16/22
*Items below in no particular order
Contact Loretta Collins (lcollins@chesapeakebay.net) with comments/questions.
Greyed - out items are withdrawn and/or resolved
BMP- Effectivness, Tracking and/or Reporting | ORIGINAL APPROVAL | AgWG Priority Level | Potential TIMELINE | INTERESTED JURISDICTIONS | LEAD | CBPO Contact | ACTION | NOTE | Status
Dairy Precision Feeding (DPF) | Simpson & Weammert, 2009 https://archive.chesapeakebay.net/pubs/BMP_ASSESSMENT_REPORT.pdf | ? | 2022 Progress Reporting (not reliant on CAST changes)- if approved by relevant groups in the partnership. | PA | Mark Dubin, UMD | Mark Dubin, UMD | Proposal for suggested change in implementation tracking based on updated science | Several state WIPs include DPF as part of 2025 goals, only NY has reported DPF as of 2019. PA actively working on solution to tracking challenges. Seeking flexibility in CBP requirements. This would require a change to the Simpson & Weammert (2009) report recommendations. Dr. Virginia Ishler (Penn State) and Dr. Kathy Soder (ARS), both involved in original recommendations, have more recent reserach on dairy herds and MUN levels. Jennifer Reed-Harry (Penn Ag Ind. Assoc.) & Ron Ohrel (Mid-Atlantic Dairy Assoc.) working on dairy processor co-op sub-population verification. Brady Seeley (DEP) writing up a narrative of path forward. Interested in tracking % of PA dairy population under DPF versus individual herd management. Up to 70% of PA dairy population may use DPF. | PA assembled team to discuss new science, tracking, and reporting for dairy presicion feeding. June 2020AgWG presentation on MUN research. https://www.chesapeakebay.net/what/event/agriculture_workgroup_conference_call_june_20211 PA and CBPO working on proposal to present at future AgWG for approval for 2022 BMP progress reporting.
Riparian Grass Buffers | Riparian Riparian Forest and Grass Buffer Expert Panel https://www.chesapeakebay.net/documents/Riparian_BMP_Panel_Report_FINAL_October_2014.pdf | ? | ? | ? | ? | Loretta Collins | Propose review of grass buffer effectiveness efficiencies and credit duration as part of prioritization process in the AgWG. Partner lead needed, as well as identification of resources needed. | Discussed in the context of credit duration at BMP Verification Ad Hoc Action Team. From EP (2014): Both grass and forested buffers have been shown to reduce nitrogen effectively. Grass can provide dense protection of soil surfaces, but usually generates more runoff than forest. Several studies have found that grass buffers are less effective than forest buffers at removing nutrients (Lowrance 1998, Mayer et al. 2005). Sweeney and Newbold (2014) looked at forest and grass buffers through a meta- analysis and found that there is a lack of research on natural landscape grass buffers, as opposed to experimental plots with artificial flow. Few studies were cited that could definitively point to an appropriate TN efficiency for grass buffers. The original TN discount to 70 % of the forest buffer efficiency was reaffirmed in the 2009 BMP Assessment Report which clearly noted that more research was needed to support this (Simpson and Weammert 2009). In the absence of data to support or refute this estimation, the Panel recommends no change. Both forest and grass buffers receive the same TP and TSS efficiencies. Grass buffers receive 70 % of the forest buffer TN efficiencies. The regional efficiencies established by Simpson and Weammert (2009) are averages referring published literature from that region when available. More information on the ranges, standard errors, and measures of dispersion among the estimates for each region is needed (see Section 7). The same studies did not provide supporting evidence for grass being 70% as efficient as forest buffers in TN removal (see Section 4H). | BMP Verification Ad Hoc Action Team determined that review of grass buffer BMP should go through the AgWG (September 2021). Item added to this list for consideration of the AgWG.
Winter Crop (proposed) | Cover Crop Expert Panel 2016 https://www.chesapeakebay.net/documents/Phase_6_CC_EP_Final_Report_12-16-2016-NEW_TEMPLATE_FINAL.pdf | ? | Phase 7 (possibly sooner) | PA, NY, MD |  | Loretta Collins | Expected Spring 2022 AgWG update | PA no change in EP recs, "WINTER CROP" proposal (EP)- corn silage-man-forage (multi-species foraging & feed- greenchop. "triple cropping" over two years. Charlie White (Penn State) research. Man N uptake (not leached) NEW SCIENCE! AgWG consider EP for winter crop. legume/legume-grass hay LU as most appropriate for application of BMP. | July 2021 AgWG AdHoc discussion; Jan 2021 Charlie White AgWG talk; Dec 2020 Ken Staver discussion on cover crops; AgWG CAST Concerns Ad Hoc
USDA-NRCS/CBP BMP Correspondence and Reporting | N/A | On-going | Annual Updates | All | Leon Tillman, NRCS | Olivia Devereux | Feb 2022 Leon Tillman, NRCS, will present on updates to NEIEN to accommodate NRCS practices. | A crosswalk of NRCS practice names and codes to the CAST BMP name may be helpful in selecting the CAST BMP that best represents a management action. https://cast.chesapeakebay.net/Documentation/BMPs | On-going, as needed updates. Update guidance for matching NRCS practices to established CBP (CAST) BMPs and accomodating NRCS practices in NEIEN.
MODELING | ORIGINAL APPROVAL/CROSSOVER | Priority Level | Potential TIMELINE | JURISDICTIONS | LEAD | CBPO Contact | ACTION | NOTE | Status
Variable-Scale Modeling | Phase 7 Proposal | Priority to be determined by WQGIT | Phase 7 | ? |  | Gary Shenk | Explanation from Gary Shenk and Olivia Devereux Sept 2021 AgWG meeting | The Variable Scale Modeling topic is an upgrade to the scale of the underlying processes simulated in the watershed model. Many studies show that a small percentage of the land area generates a large majority of the nonpoint source loads, particularly for pollutants such as phosphorus and sediment. Additional work has shown significant cost savings from geographic targeting of BMPs. Many of the processes governing runoff operate at the field to small watershed scale. The current Phase 6 CAST allows users to target BMPs at a land-river segment based on current watersheds averaging 80 square miles. A Phase 7 CAST using land-river segments at the scale of the NHD100k would allow targeting and differential crediting of BMPs down to the level of approximately one square mile. A Phase 7 Cellular model would have the potential to allow for targeting on a much finer scale pending validation of the approach. Greater accuracy watershed modeling; Enables adjustment of scale for different purposes, Scale of various activities needs to determined | Discussed Oct 25-26 2021 WQGIT vitual meeting. See Watershed Modeling Workplan Options See notes:https://www.chesapeakebay.net/channel_files/44060/phase_7-_plus_additional_activities_planning_01-10-22_.pdf https://www.chesapeakebay.net/channel_files/41830/watershed_modeling_workplan_options_for_2025_v2021_08_26_clean.pdf
[Simplify] Nutrient Application Calculation | Phase 7 Proposal | Priority to be determined by WQGIT | Phase 7 CBWM | ? |  | Gary Shenk | Explanation from Gary Shenk and Olivia Devereux Sept 2021 AgWG meeting | Greater accuracy watershed modeling; Enables adjustment of scale for different purposes, Scale of various activities needs to determined | To be considered Oct 25-26 WQGIT vitual meeting. See Watershed Modeling Workplan Options (Simplify Nutrient Application Calculation section). https://www.chesapeakebay.net/channel_files/41830/watershed_modeling_workplan_options_for_2025_v2021_08_26_clean.pdf
Manure Treatment & Transport | MTT EP 2016 https://www.chesapeakebay.net/documents/MTT_Expert_Panel_Report_WQGIT_approved_Sept2016.pdf Phase 6 CBWM 2017 | ? | Phase 7 CBWM | PA, MD |  | Loretta Collins | Further discussion needed with Modeling WG regarding Phase 7 development. Will finer- scale modeling provide opportunity for finer-scale accounting for manure transport? | Backfill, Local tracking of manure; 1. PA needs better tracking and reporting- pilot project Penn Ag Industries lead, PA SCC, PA 4r Alliance, manure-haulers & brokers possible regulartory change 2. PA wants study group on inter-county manure transport county-level budgets. AgWG study group: how to do this? Need farmers to reduce applications but need to move. Liq manure tansport is short distances- NEED INCENTIVES for short-distance MT. MTT- Jason/Ted PA request to AgWG for study group; Check w/ MWG on progress on refined modeling efforts and efforts in general for the CBWM. | Winter/Spring 2022 AgWG determination of how to address Phase 7 data needs. Who will do this, how, and when.
Ag Loading Rates | Ag Loading Rate Review Steering Committee Agricultural Modeling Subcommittee (AMS), 2016 https://cast.chesapeakebay.net/FileBrowser/GetFile?fileName=P6ModelDocumentation%2F2A_AgLoadingRateDocumentation_Final_AgWG_approved_Jan2016.pdf | High | Phase 7 CBWM | All |  | Loretta Collins | Review as part of Phase 7 development. | Review of ag loading rates determined by committee under the Agricultural Modeling Subcommittee (AMS) in development of the Phase 6 CBWM. Associated with concerns regarding N loads attributed to soybean land use (loading includes impact of N fixation on residual soil N) | Winter/Spring 2022 AgWG determination of how to address Phase 7 data needs. Who will do this, how, and when.
Animal Populations (General) | Phase 6 CBWM | ? | Phase 7 CBWM | All | Vanessa Van Note, Mark Dubin | Vanessa Van Note, Mark Dubin | Fall 2021- Discussions regarding use of private industry data on-going in AgWG and WTWG. | Improvements in accounting and distribution of animal population data to more accurately reflect ag production in the CBW; challenge with Ag Census data is the assumptions and distributions that have to be made where the census provides "(D)" for a particular crop/animal in a county; areas where the census does not provide county-scale data provides the opportunity to seek additional state/local/industry data to inform the process of assigning appropriate animal population data to the county. | Winter/Spring 2022 AgWG determination of how to address Phase 7 data needs. Who will do this, how, and when.
AG DATA INPUTS | ORIGINAL APPROVAL | Priority Level | Potential TIMELINE | JURISDICTIONS | LEAD | CBPO Contact | ACTION | NOTE | STATUS
Animal: Dairy | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD, NY | Vanessa Van Note, Ruth Cassilly | Vanessa Van Note | CBPO looking into the possibilty of using annual NASS survey for dairy | Annual NASS Survey may help improve accuracy between census trends. | On-going. Seek periodic updates
Animal: Equine | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD, ? | TBD | Vanessa Van Note |  | May currently be using best data available. Additional NASS data sources may not capture full profile of horse ownership. | On-going. Seek periodic updates
Animal: Beef | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD, ? | TBD | Vanessa Van Note |  | May currently be using best data available. Additional NASS data sources may not capture full spectrum of beef operations. | On-going. Seek periodic updates
Animal: Poultry- Layers | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD, NY | Vanessa Van Note, Mark Dubin | Vanessa Van Note | CBPO looking into the possibilty of using annual NASS survey for layers (egg production). Other data sources (e.g., industry, CAFO permits) may be considered. | Annual NASS Survey may help improve accuracy between census trends. Hillandale Farms facility data and CAFO permit information illustrates that the Ag Census is not capturing the full scope of animal operations. In the case of Hillandale the omission results in significant underestimation of respective county-level layer population in CAST. | On-going. Seek periodic updates. AgWG to discuss Hillandale data incorporation Fall 2021. This item is outstanding from the CAST-21 Workplan. Potential incorporation in CAST-23 and/or Phase 7. Hillandale example is bridge to discuss alternative data sets to account for animal population in Phase 7 CBWM. Discussion October/November 2021 AgWG meeting. AgWG Survey or gather comments and question on Hillandale and animal data in general in Winter 2021-2020.
Crop: Annual Implementation Reports (AIR) | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD | TBD | Mark Dubin |  | USDA Partners- NRCS Chesapeake Bay Coordinnator, Leon Tillman, appointed in 2021. Use of alternative data sets to supplement NASS data where available is desirable where such data is available. | On-going. Seek periodic updates
Crop: USDA-FSA crop reporting | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD | TBD | Mark Dubin |  | USDA Partners?; NRCS Nation comm crop index. Ind. crops by county. (FSA crop reporting) | On-going. Seek periodic updates
Fertilizer Sales Data | Phase 6 CBWM | ? | 2-year CAST updates/Phase 7 | MD, PA, VA, NY | States, Industry Partners | Mark Dubin | Seek update from states on fertilizer data collected and reported to AAPFCO by state chemists. | Lindsay Thompson, Janelle Eck/ MDA organizing review with state chem (MD) to be followed by PA and other Bay States. DE has engaged in clean-up of data in recent years. Create a template in MD and move to other states. May be redundancy in reporting by registrants. | MDA in discussions with state chemist.
Soil Phosphorus Data Set | Phase 6 CBWM | High- MB Ask | Phase 7 CBWM | All | Isabella Bertani | Gary Shenk | Contact Gary with soil P data | MB ask for more expansive set of soil P data during Phase 6 review | On-going. Data submitted from WV. In-coming from NY. Updated data sets needed from PA, MD, DE, VA.
Manure Concentration Data | Phase 6 CBWM | High- EPA grant guidance indicated need for updated poultry and swine data on annual or bi-annual basis from states. | Phase 7 CBWM | All |  | Olivia Devereux, Jess Rigelman |  | Poultry and Swine data from Phase 5 characterization studies. Other animal groups based on 2005 ASABE national data set. | On-going. Seek periodic updates
Rotational/Precision Grazing | STAC, 2010 https://cast.chesapeakebay.net/FileBrowser/GetFile?fileName=GrazingPastureMgmt2010.pdf | N/A | N/A | PA (withdrawn) | N/A | N/A | No Action |  | Withdrawn
Heavy Use Area Protection (HUAP) | Loafing Lot BMP, 2003 | N/A |  | PA | Ted Tesler | Mark Dubin, Loretta Collins | No Action. RESOLVED 01/13/20 | Track & Reporting issue. Can NRCS 561 reported as Loafing Lot Management? Is 561 exclusive to Loafing Lots (non-poultry) across all jurisdictions? Every state tracks differently, some can differentiate poultry pads from loafing lots. | Withdrawn
Heavy Use Area Protection (HUAP) - Poultry Pads | AWMS EP 2016 | N/A | N/A | MD, DE, WV (withdrawn) | N/A | N/A | No Action. RESOLVED 11/13/20 | Concern regarding crediting for poultry pads. Language included in 2016 AWMS EP report. Poultry pads defined as part of AWMS BMP. | Withdrawn
Pasture Nutrient Management | NM EP 2016; Phase 6 CBWM 2017 | N/A | N/A | PA, NY (Withdrawn) | N/A | N/A | N/A | Nutrient spread curves; Manure eligible for beans (for sulfur) full season and bean sm gr. Winter Crops (EP); Nutrient Spread Slopes: request to limit pasture applications due to unintended consequences. Reviewed current eligibility in CAST source data. RESOLVED 11/13/20. | Withdrawn

## Acronyms
AAPFCO | Association of American Plant Food Control Officials
AgWG | Agriculture Workgroup (CBP)
ASABE | American Society of Agricultural of Biological Engineers
BMP | Best Managent Practice
CAFO | Confined Animal Feeding Operation
CAST | Chesapeake Assessment Scenario Tool
CBP | Chesapeake Bay Program
CBPO | Chesapeake Bay Program Office
CBWM | Chesapeake Bay Watershed Model
DPF | Dairy Precision Feeding
EP | Expert Panel
MB | Management Board (CBP)
MDA | Maryland Deparement of Agriculture
MT | Manure Transport
MTT | Manure Treatment Technologies
MUN | Milk Urea Nitrogen
MWG | Modeling Workgroup (CBP)
NASS | National Agricultural Statistics Service (USDA)
NEIEN | National Environmental Information Exchange Network
NRCS | Natural Resources Conservation Service
PA SCC | Pennsylvania State Conservation Commission
STAC | Scientific Technical Advisory Committee (CBP)
USDA | United States Department of Agriculture
WIP | Watershed Implementation Plan
WQGIT | Water Quality Goal Implementation Team (CBP)