## Stream Restoration
Date (of event or document) | Event | Document(s) | Key Actions or Recommendations & Status | Document(s) Summary | Contact
2000-06-28 | Chesapeake 2000 partnership agreement | Chesapeake 2000 (C2K) | 1) HGIT works on stream related habitat issues. Status: ongoing. 2) WQGIT works on stream related water quality issues. Status: ongoing. | C2K support projects will create results that contribute to progress towards living resource goals on an annual basis, collaborating with CBP partners to continually improve the efficiency of our efforts leading to the restoration of the Chesapeake Bay and its tributaries. | CBPO
2009-09-28 | Site Tour and Follow-up Letter: AACO/DNR/SRF | Meeting and follow up letter | Follow up meeting with larger CBPO staff to include Eco-cluster and modelers (Status: completed on 10-29-2009) | Letter, following multi-site tour in AACO, outlining sediment transport issues from eroding streams and highlight need to address in order for AACO/DNR to meet TMDL commitments | Ron Bowen
2009-10-29 | Meeting: AACO with Cfox & CBPO | Agenda & AACO Stream Sed/P/N Loads - Meeting with Chuck Fox/Jwinters/CBP Modelers/Eco Cluster | Led to CBPO identification for need to focus on sediment and stream issues; one input pointing to need for stream/sediment coordinator (Status: 1) CBPO/EPA & HGIT: identify need to focus on stream restoration issues 2) CBPO: led to creation of Stream/Sediment Coordinator) | Built case for stream restoration as critical to AACO meeting TMDL load reductions | Ron Bowen
2010-12-31 | Action Plan Item Follow-up | EO 13508 Action Item WQ 2.1 Status Report | Seven funding opportunities for water quality, habitat, fish passage, and others listed. (Status: EO action item completed; did not appear to lead to other action) | "The purpose of this document is to respond by December 2010, to the Executive Order 13508 Strategy for Protecting and Restoring the Chesapeake Bay Watershed (May 12, 2010), or the EO Strategy, action item to pursue funding existing options available for stream restoration grants. This paper also makes recommendations for implementation for consideration of further action by the Federal Office Directors." More specifically, EPA is to “pursue funding of stream restoration grants. EPA will, by December 2010, complete an assessment of options to direct existing funds from other program areas to support increased funding for stream restoration grants. If these funds become available, they would be targeted and directed for use at a local government, local watershed and community-based level.” (Strategy page 32) This directive translated into an action item in the Fiscal Year 2011 Action Plan; Executive Order 13508; Strategy for Protecting and Restoring the Chesapeake Bay Watershed by the Federal Leadership Committee for the Chesapeake Bay (September 30, 2010). The action, WQ.2.l (Action Plan page 19) is to "Pursue funding of stream restoration grants. #1 Complete an assessment of options to direct existing funds to support increased funding for stream restoration." | FOD/FLC/JWinters/JGriener
2011-06-22 | CBPO/EPA issued RFP | Request for proposals (RFP) | CBPO: to award cooperative agreement for stream/sediment coordinator to: synthesis of research and restoration findings; best management/restoration practice review/approval/crediting; scenario builder development/enhancement/application; watershed/estuarine models application/analysis; sediment management/stream restoration cost-effective/efficiency analysis; sediment/stream restoration programmatic gap/capacity analysis; expanded stream/shoreline restoration practice tracking/reporting/verification; jurisdiction implementation support; and team/workgroup support. (Status: cooperative agreement awarded; work ongoing) | RFP for Stream/Sediment Coordinator | Julie Winters
2012-02-21 | CBPO/EPA Cooperative Agreement awarded | Grant agreement (multi-year) | 1) Grant awarded to Center for Watershed Protection (CWP) to serve a stream/sediment coordinator. 2) Habitat GIT becomes home for stream/sediment coordinator. Status: CWP, as stream/sediment coordinator, to fulfil: Objective #1 – Provide Modelling Support. Objective #2 – Coordinate Partnership Scientific Input (i.e., expert panel work). Objective #3 – Programmatic Evaluation, Reporting, and Verification (i.e., Habitat Goal Implementation Plan work). | Cooperative agreement (award date: 2/21/2012) | Julie Winters
2012-03-22 | Executive Order issued by POTUS, and Federal Implementation Plan | Executive Order 13604 | Resulted in: Implementing Executive Order 13604 on Improving Performance of Federal Permitting and Review of Infrastructure Projects: A Federal Plan and Review Process for Better Projects, Improved Environmental and Community Outcomes, and Quicker Decisions (June 2012) (Status: no actions in context of work in Chesapeake Bay) | Executive Order to significantly reduce the aggregate time required to make decisions in permitting and review of infrastructure projects by the Federal Government, while improving environmental and community outcomes. | White House FR and Guidance
2012-09-04 | Meeting: CB stream restoration practioners from MD/VA/DC jurisdiction level, local PW depts & NGOs; Stormwater Coordinator; EPA | Meeting agenda | Possible issue problems/solutions discussed. Restoration practioners agree to do written case studies outlining/documenting issues/problems being encountered. Recognitions that restoration and permitting/regulatory community need to work together to ID issues and solutions. (Status: 1) Develop an issues paper (see 9/10/2012 paper) that outlines issues based on case studies and inputs from: MD WIP; DNR; DC DOE; SRF; and N27 & N43) | Overview: Issues related to local implementation of WIPs have emerged. Issues regarding federal permitting of restoration projects have been raised as one of several concerns or as a barrier to WIP BMP implementation. The financing of these projects was raised as EPA is attempting to provide financial workshops, funding and technical service providers to address financing concerns. Meeting goal: 1) Intended as opportunity to ID possible WIP implementation issues or obstacles to constructively address. 2) Gather input to develop statement of the problem. | Julie Winters
2012-09-10 | Background paper developed by EPA | Background paper | RECOMMENDATIONS 7) CBPO, EAID, and WPD should work collaboratively and insure that interpretations of the CWA that conflict with TMDL WIP implementation are efficiently, effectively, and constructively addressed in a timely manner. Status: not done. 8) Streamline permitting process. Status: some limited steps taken between 2012 and 2015. 9) Interpret existing N27 and 43 with regional guidance or work with ACE and stakeholders to develop RGP for CB watershed to cover stream/wetland/RSC projects. Status: ACE did N27 guidance/ drafted RGP; see 3/18/2013 status update on action items document. 10) Develop pre-application process and tool to assist restoration practioners in application process, including pre-app consultation opportunities. Status: ACE did diagram; see 3/18/2013 status update on action items document. 11) Include other regulators (FWS and ACE) in subsequent meetings. Status: completed immediately. | CHACTERIZING PROBLEM 1) Drivers for stream/wetland restoration projects are jurisdictions TMDL WIP commitments; attached to paper. 2) MD input deck - attached to paper - for Phase II WIP includes 1,575,537 feet, or approximate 300 miles of urban stream restoration state-wde by 2017. 3) AACO, MD claims can not achieve WIP allocation targets without stream restoration/stream-floodplain wetland reconnections/RSC BMPs. 4) Recognition that science supporting stream restoration is new and evolving. Rosgen method widely recognized and accepted. Recognition that alternative approaches may be more appropriate in urban context. EXAMPES OF RESTORATION PERMITTING RELATED ISSUES 5) Attached to paper: practioners case studies from DNR, DC DOE, SRF. NOTE: personality issues emerge as a possible part of the problem. CONSIDERATIONS FOR SOLUTIONS 6) Consider: streamlined permitting process; clarification of N27 for application to urban stream restoration in CB region; clarification of N43; develop a regional general permit for CB watershed; incorporate recommendations from CBP expert panel on stream restoration projects and model credit for removal rates; clarify eligibility of practices for funding under 319, state revolving fund, Chesapeake Bay and other federal funds; evaluate if stream restoration should be considered as a green infrastructure practice; and clarify 402 NPDES storm water issues. | Julie Winters
2012-09-18 | EPA internal meeting: CBPO/EAID/WPD | Meeting agenda & summary | 1) EAID agreed to engage the ACE to explore doing and RGP. Status: completed. 2) CBPO was to review grant awards to see if JP meeting could happen. Status: completed in January 2013. 3) CBPO stream restoration expert BMP panel to develop definitions for urban and non-urban stream restoration projects. Status: completed. 4) Nick DiPasquale to communicate with stakeholder stating that EPA is working on the issue. Status: completed; see 9/26/2012 email from Nick to stakeholders. | Meeting goal: Identify win-win solutions for implementation of the mission-critical CWA responsibility under Region 3's purview. Summary: Recognition that TMDL led to more demands on 402/319/404 programs; EAID raised questions on the validity of science supporting RSCs (only)/emphasized utilizing upland restoration/and thought it worthwhile to ID criteria for those project better suited for RSC; CBPO noted that if both RSC or stream restoration projects and upland restoration were ecologically feasible, upstream project shouldn't be in lieu of stream restoration. EAID doesn't recognize full range of stream restoration techniques and is primarily focused on RSC. EAID believes many RSC failed and contribute to the impairment. RSC are one just one component of stream restoration projects that jurisdictions have committed to in their WIPs; agreement on the science and monitoring, baseline data, site selection guidelines, and accountable parties. EAID raised the concept of doing a RGP for categories of in stream projects designed specifically for the purpose of nutrient and sediment reduction. | Nick DiPasquale
2012-10-26 | Meeting: EPA & ACE (Balti) | Meeting summary | Status: Meeting between ACE, CBPO, EAID, WPD, expanded to include FWS scheduled for 1/24/2013. | Meeting between ACE and CBPO to discuss 404/402 approvals for stream/wetland restoration and stormwater management projects. 1. ACE believes N27 is still a viable vehicle for stream restoration permitting and does not believe a RGP is necessary. 2. ACE strongly supports pre-application meetings; one venue are the JE meetings. 3. ACE indicated a willingness to work with both CBPO and EPA's WPD and EAID in developing a site selection criteria, especially for RSC. 4. ACE agreed to look for additional guidance to serve as a guide or model for preparing alternatives analysis, as well as provide a copy of the directions for the application which might provide some additional guidance. 5. The next step will be to convene a meeting among staff from ACE (Balti), CBPO, EAID, and WPD to discuss the issues and explore options for improving the permitting process for restoration projects. ACE recommended including MDE wetlands and waterways staff at this meeting to vet issues with state permitting of restoration projects. 6. ACE also acknowledged that it might be helpful to set up a second meeting with agency staff and the local, state, and NGO reps that brought these issues to our attention to discuss options for addressing their concerns and providing better guidance and direction. 7. Executive Order 13604 was mentioned and copies provided to meeting participants. EO 13604 directs federal agencies to improve performance of federal permitting and review of infrastructure projects. | Nick DiPasquale
2012-11-28 | Meeting: Habitat GIT | Meeting agenda & summary | Status: meeting summary issue items status is as follows. 1) Issue - regulatory intent - many regulatory vehicles were meant to deal with impairment projects, not restoration projects. Solution: Consider specific track for restoration projects. (STATUS: Initially, regulatory agencies (federal and state) were not in favor of separate tracks, and this recommendation was dropped. However, some discussion on this topic in MD has resumed with the new administration) 2) Issue - Time to get permits is an issue - you might lose ULO, funds, or projects. Solution: Consider a specific track for restoration projects. Status: Initially, regulatory agencies (federal and state) were not in favor of separate tracks, and this recommendation was dropped. However, some discussion on this topic in MD has resumed with the new administration. 3) Issue - Process issues like using the right words on applications, increasing workload for regulatory agencies and anticipated backlog due to TMDL, completeness and quality of applications, standards and rigor of information and data required for voluntary restoration projects (vs. other types of projects; e.g., mitigation or development). Solution; improve applicant training, provide opportunity for pre-apps, obtain clarity on requirements to sure there is adequate assessment; justify site selection; bifurcated permit process. Status: the pre-application meeting concept has been encouraged, and the number of pre-app meetings has increased. Pre-app meetings have helped in many situations, but are not a solution for all issues. MDE was to provide additional checklists to guide applicants’ - we need to check on the status. Formal applicant trainings may/may not have been added, should check with fed/state agencies to see if they have. Bifurcated permit process – initially regulatory agencies did not favor. Some discussion on this topic has resumed (see above). 4) Issue - Appropriate Use of Nationwide 27 and possible regional conditions. Clarify specifics. Status: On 7/1/2015 ACE/Baltimore issued Chesapeake Bay TMDL RGP, and they continue to also administer N27 for their district. Additionally, ACE/Norfolk administers a N27 for their district. 5) Issue - Habitat conversion issue (streams to wetlands and vice versa) and habitat trade-off issues - how to deal with some trade-offs in cases of net biological uplift. Solution: Rely on science; find consensus on what we know, and what we don't know (for areas of scientific research); Status: Group has met to identify areas of scientific/knowledge gaps, and come up with a “pooled monitoring” effort to link the scientific and regulatory entities to fill in those gaps. Currently led by the Trust and focused in MD but could be expanded to include other Chesapeake Bay jurisdictions. 6) Issue - Idea of avoiding waters of the US. Solution: Develop clear definitions (e.g., for streams) and guidance, and make it less case by case. Status: New WOTUS rule has affected this – it is pending to as still letting impacts of new WOTUS settle out. | Agenda Purpose: Reduce the amount of time to get permits approved for habitat restoration projects Topics: Regulatory perspectives (ACE/Balti, 404, VMRC, and MDE); practioners perspectives via presented case studies (Steve Strano/NCRS, Erik Michelson/SRF, Jana Davis/CBT, Serena McClain/American Rivers, and Rich Starr/FWS); discussion to identify solutions Next Steps Letter from Habitat GIT to Director, CBP/EPA summarizing the meaningful dialogue at this 11/28/2012, meeting between regulators and practioners about the permitting process for habitat restoration projects within the CB watershed. Meeting Summary 1) Issue - regulatory intent - many regulatory vehicles were meant to deal with impairment projects, not restoration projects. Solution: Consider specific track for restoration projects. 2) Issue - Time to get permits is an issue - you might lose ULO, funds, or projects. Solution: Consider a specific track for restoration projects. 3) Issue - Process issues like using the right words on applications, increasing workload for regulatory agencies and anticipated backlog due to TMDL, completeness and quality of applications, standards and rigor of information and data required for voluntary restoration projects (vs. other types of projects; e.g., mitigation or development). Solution; improve applicant training, provide opportunity for pre-apps, obtain clarify on requirements to sure there is adequate assessment; justify site selection; bifurcated permit process. 4) Issue - Appropriate Use of Nationwide 27 and possible regional conditions. Clarify specifics. 5) Issue - Habitat conversion issue (streams to wetlands and vice versa) and habitat trade-off issues - how to deal with some trade-offs in cases of net biological uplift. Solution: Rely on science; find consensus on what we know, and what we don't know (for areas of scientific research). 6) Issue - Idea of avoiding waters of the US. Solution: Develop clear definitions (e.g., for streams) and guidance, and make it less case by case. | Jeff Horan, Chair Jana Davis, Co-chair Jennifer Greiner, Coordinator Hanna Martin, Staffer
2012-11-30 | Information sharing: AACO PPT | PPT | Working to demonstrate need for stream restoration as BMP for use in meeting TMDL and other CBP program goals. Status: ongoing dialogue. | Documents experience with headwater stream erosion: incised channels; accelerative sediment transport; phosphorus contribution; lost ground water hydrology; and loss of floodplain/wetland services Goals of aquatic ecosystem restoration: stabilize channels; reduce sediment/phosphorus; reconnect floodplain, and restore: ground water hydrology/aquatic ecosystems/fish passage & habitat/waterfowl habitat/designated uses | Ron Bowen
2012-12-17 | Stream restoration expert panel | Report | Panel recommended: 1) Four general protocols to define the pollutant load reductions associated with individual stream restoration projects. 2) Examples to show users how to apply each protocol in the appropriate manner, along with several important qualifying conditions and environmental considerations for stream restoration projects to ensure these produce functional uplift for local streams. 3) stream restoration credits be limited to five years, although credits can be renewed based on a field inspection that verifies the project still exists, is adequately maintained, and is operating as designed. Status: all three completed | Panel report addresses: 1) Specific definitions of what constitutes effective stream restoration in the context of any nutrient or sediment credit, and defines the qualifying conditions under which a local stream restoration project may be eligible to receive the credit. 2) Assesses whether existing CBP approved removal rate is suitable for qualifying stream restoration projects, or whether a new protocol needs to be developed to define improved rates. 3) Defines the proper units that local governments will use to report retrofit implementation to the states to incorporate into the CBWM. 4) Determines whether to recommend an interim removal rate be established for one or more classes of stream restoration practices prior to the conclusion of the research for the WIP planning purposes. 5) Recommends procedures for reporting, tracking, and verifying any recommended stream restoration credits over time. | WQ GIT Coordinator
2012-12-18 | Issue paper: USDA NRCS | Issue paper | (Status: No known follow up addressed; should be addressed). | Issue paper outlining permitting of agricultural BMP and wetland restoration activities in MD. Highlights follow. - Ag BMPs planned/implemented in or near waters of the State and require permits/authorizations when impacting wetlands, streams, and floodplains. - Permitting addressed by variety of agencies/authorities, these are reviewed and summarized in this issue paper. - Recurring issue of regulatory uncertainty occurs in the determination of streams and floodplains in the coastal plain. - Paper builds case and calls for action to address: ~ Regulatory certainty on jurisdiction determination of streams and floodplains. ~ A streamlined process for implementation of wetland restoration, shallow water area development, and other AG BMPs within waters of the State on AG lands. ~ More flexibility in the limits of disturbance allowed in the these waters to implement activities that improve environmental quality. - Paper offer potential solutions: ~ Adopt/adapt procedure for stream identification. ~ Special general permit. ~ Risk class system. ~ Utilize existing waterways regulations. ~ Expand definition of Ag activity. | Steve Strano
2013-01-04 | Meeting: Habitat GIT | Letter | Status: the following summarizes the status (as of 7-13-2015) of the items recommended in the 1/4/2013 Habitat GIT letter to the MB. A. Consult Proactively: Regulatory representatives emphasized the need for restoration project managers to engage the regulatory agencies early in the application process by taking advantage of the pre-application consultation process. Status: Pre-application meetings have been further encouraged and are happening more, though do not solve all issues B. Create Clear Application and Review Processes: Develop clear guidance and processes to assist potential applicants in preparing effective applications that are responsive to the regulatory requirements. We suggest permit agencies: 1. Develop written site, design, and construction selection criteria so applicants are not preparing proposals for projects that permit writers will not likely permit. Status: CHECK WITH REGULATORY AGENCIES TO GET SPECIFICS ON WHAT THEY CHANGED 2. Develop a written process flowchart that clearly delineates primary, secondary, and even tertiary steps in the permitting process. Status: CHECK WITH REGULATORY AGENCIES TO GET SPECIFICS ON WHAT THEY CHANGED 3. Develop permit application checklists specifically for certain types of restoration projects to ensure applicants submit complete applications. Status: CHECK WITH REGULATORY AGENCIES TO GET SPECIFICS ON WHAT THEY CHANGED – I know Bill Seiger was working on this for MDE 4. Identify problematic terminology that may trigger unintended and unnecessary requirements. Status: CHECK WITH REGULATORY AGENCIES TO GET SPECIFICS 5. Define criteria that would allow and encourage innovative projects to get permitted, specifically function-based assessment and monitoring requirements, responsibility in the event of a failure, etc. Status: MDE working with FWS (Rich Starr) on function-based pyramid 6. Compile an inventory of technical resources and specialists available to assist applicants in preparing complete and meaningful applications. Status: Unknown 7. Identify a principal Point of Contact (POC) for the regulatory agencies (and if possible lead agency) to ensure smooth flow of accurate information and communication with the applicant. Status: Unknown 8. Provide training opportunities for permit applicants on these issues. Status: Unknown if specific training opportunities were ever developed. Need to check with MDE We suggest restoration practitioners: 1. Utilize pre-application consultations to increase understanding of project outcomes. Status: Pre-apps are becoming more common. 2. Follow checklist and guidance from permitting agencies to ensure submittal of complete permit applications. Status: Unknown – check to see if new checklists were produced by regulatory agencies 3. Develop projects with a goal of achieving ecological uplift through restoration while limiting conflicts with other resource requirements. Status: Certainly acknowledgement of other resource requirements is becoming more common 4. Identify a principal Point of Contact (POC) for the applicant to ensure smooth flow of accurate information and communication with the permitting agencies. Status: Unknown – probably this already happens 5. Consider function-based science and enhanced monitoring to validate innovative restoration techniques. Status: MDE and FWS working together to develop function-based assessment process. In addition, methods of maximizing effectiveness of monitoring have been discussed extensively over the past 2 years, including the concept of concentrating or pooling monitoring effort to answer specific questions as opposed to measuring every project. C. Clarify Definitions and Manage Trade-offs: Significant uncertainty centers around definitions of habitat types and trade-offs among types (i.e. stream vs. ditch vs. swale and ephemeral vs. intermittent vs. perennial). Additional processes need to be developed to assure timely integration of all necessary resource inputs. Status: The pooled monitoring effort aims to quantify some of these trade-offs. Process improvements to integrate – discussion now occurs at pre-app meetings, but no official process has been identified (Check this language with regulatory folks) D. Pursue Options to Expedite Review of Restoration Projects: 1. Consider expediting the review of restoration projects that use common practices (e.g., ditch plugging), especially when these practices are implemented by resource agencies in degraded landscapes. These efficiencies can be provided through a number of regulatory vehicles, such as general permits (e.g., Nationwide 27), regional letters of authorization, regional conditions for general permits, and memoranda of understanding. Status: Unknown. Will regional general permit address this? 2. Consider a new approach or “restoration lens” applied to applications for restoration projects submitted by resource agencies rather than grouping them with development projects under the same review process. Status: Initially, regulatory agencies (federal and state) were not in favor of separate tracks, and this recommendation was dropped. However, some discussion on this topic in MD has resumed with the new administration) 3. We recommend that regulatory agencies and key practitioners coordinate to prepare additional guidance and cross training on regulatory requirements, innovative restoration approaches, and designs for all pertinent staff and other relevant stakeholders. Outreach and information should be made clearer and accessible. Status: Discussion about an annual forum has occurred, but not yet carried out. Will ultimately by tied with pooled monitoring effort. 4. For NGO and local projects, we also may want to consider agency co-sponsorship of projects to help facilitate appropriate use of general permits and broaden the array of eligible projects. Status: Unknown E. Validate with Science: 1. Both regulators and practitioners agreed that a permit pre-application tool that standardizes the level and type of data needed would be useful for all. Status: MDE and FWS working together on function-based assessment tool, but this will likely not fully address this issue. 2. Costs associated with monitoring should be taken into consideration, such that those costs alone do not serve as a barrier. Several meeting participants voiced the concern that permit application requirements should not be more rigorous for restoration projects than they are for development projects. Status: pooled monitoring effort is intended to help with this issue, by answering regulatory questions in another way, but to date no specific action here until pooled monitoring effort starts producing answers. 3. We suggest the consideration of developing new processes or new forums to continuously apply advances in science and new tools to the regulatory and restoration process. Status: Discussion about an annual forum has occurred, but not yet carried out. Will ultimately by tied with pooled monitoring effort. F. Increase Understanding through Training and Education: We suggest that regulatory agencies and key practitioners coordinate to prepare additional guidance and cross training on regulatory requirements, restoration approaches, and designs for all pertinent staff and other relevant stakeholders Status: Unknown. Much discussion about cross-training has occurred, but no formal efforts that we know of have occurred or been planned. | The Habitat GIT letter, with the following content, was transmitted on January 4, 2013, to the Chair of the Management Board. A. Consult Proactively: Regulatory representatives emphasized the need for restoration project managers to engage the regulatory agencies early in the application process by taking advantage of the pre-application consultation process. B. Create Clear Application and Review Processes: Develop clear guidance and processes to assist potential applicants in preparing effective applications that are responsive to the regulatory requirements. We suggest permit agencies: 1. Develop written site, design, and construction selection criteria so applicants are not preparing proposals for projects that permit writers will not likely permit. 2. Develop a written process flowchart that clearly delineates primary, secondary, and even tertiary steps in the permitting process. Develop permit application checklists specifically for certain types of restoration projects to ensure applicants submit complete applications. 3. Identify problematic terminology that may trigger unintended and unnecessary requirements. 4. Define criteria that would allow and encourage innovative projects to get permitted, specifically function-based assessment and monitoring requirements, responsibility in the event of a failure, etc. 5. Compile an inventory of technical resources and specialists available to assist applicants in preparing complete and meaningful applications. 6. Identify a principal Point of Contact (POC) for the regulatory agencies (and if possible lead agency) to ensure smooth flow of accurate information and communication with the applicant. 7. Provide training opportunities for permit applicants on these issues. We suggest restoration practitioners: 1. Utilize pre-application consultations to increase understanding of project outcomes. 2. Follow checklist and guidance from permitting agencies to ensure submittal of complete permit applications. 3. Develop projects with a goal of achieving ecological uplift through restoration while limiting conflicts with other resource requirements. 4. Identify a principal Point of Contact (POC) for the applicant to ensure smooth flow of accurate information and communication with the permitting agencies. 5. Consider function-based science and enhanced monitoring to validate innovative restoration techniques. C. Clarify Definitions and Manage Trade-offs: Significant uncertainty centers around definitions of habitat types and trade-offs among types (i.e. stream vs. ditch vs. swale and ephemeral vs. intermittent vs. perennial). Additional processes need to be developed to assure timely integration of all necessary resource inputs. D. Pursue Options to Expedite Review of Restoration Projects: 1. Consider expediting the review of restoration projects that use common practices (e.g., ditch plugging), especially when these practices are implemented by resource agencies in degraded landscapes. These efficiencies can be provided through a number of regulatory vehicles, such as general permits (e.g., Nationwide 27), regional letters of authorization, regional conditions for general permits, and memoranda of understanding. 2. Consider a new approach or “restoration lens” applied to applications for restoration projects submitted by resource agencies rather than grouping them with development projects under the same review process. 3. We recommend that regulatory agencies and key practitioners coordinate to prepare additional guidance and cross training on regulatory requirements, innovative restoration approaches, and designs for all pertinent staff and other relevant stakeholders. Outreach and information should be made clearer and accessible. 4. For NGO and local projects, we also may want to consider agency co-sponsorship of projects to help facilitate appropriate use of general permits and broaden the array of eligible projects. E. Validate with Science: 1. Both regulators and practitioners agreed that a permit pre-application tool that standardizes the level and type of data needed would be useful for all. 2. Costs associated with monitoring should be taken into consideration, such that those costs alone do not serve as a barrier. Several meeting participants voiced the concern that permit application requirements should not be more rigorous for restoration projects than they are for development projects. 3. We suggest the consideration of developing new processes or new forums to continuously apply advances in science and new tools to the regulatory and restoration process. F. Increase Understanding through Training and Education: We suggest that regulatory agencies and key practitioners coordinate to prepare additional guidance and cross training on regulatory requirements, restoration approaches, and designs for all pertinent staff and other relevant stakeholders. | Jeff Horan, HGIT Chair Nick DiPasquale, MB Chair
2013-01-23 | Field tour hosted by DNR | Field tour | Status: ongoing dialogue. | The purpose of the field tour was to familiarize senior level managers from federal and state regulatory and resource agencies on the application of RSCs -- 1) dry channel and 2) wet channel. Severn sites visited: Chestertown, Centerville, Kirwin's Creek, Aurora Hills, Central Sanitation, Howards Branch, and Clement's Creek. | Kevin Smith
2013-01-24 | Meeting: EPA (CBPO/WPD/EAID)/ACE(Balti)/FWS | Meeting agenda and summary next steps | Status Action items: All action items were completed, compiled and distributed in 3/25/2015 "Action Item Status & Revised Meeting Summary from 1/24/2015 Stream/Wetland Restoration Permitting Processing Meeting". 1) Provide copy of 1/4/2013 Habitat GIT letter to Nick DiPasquale (EPA/Winters). 2) Screen the WIP and two year milestones input decks to ID restoration projects or commitments to do BMPs that require permits from ACE (EPA/Bisland). 3) Clarify communication protocol and streamline the method for sending the appropriate guidance back to potential permit applicants; ACE will contact applicant regarding submittal of application for Chestertown project (ACE/Anderson). 4) Provide watershed resources registry link (EPA/Spanalo). 5) Improve N27 permit application instructions by developing NWP27 checklist to facilitate determinations of eligibility under NWP27 (ACE/Bachur). 6) Develop a simple flow chart within two weeks on the permit application process/post on ACE web site (ACE/Seib). 7) Collaborate with grant makers/Bay Funders Network to clearly divine the monitoring (pre/post) requirements; provide NFWF and CBT's grant agreement language (pertaining to monitoring requirements) to this group (EPA/Bisland). 8) EPA to incorporate as a grant requirement for pre-application meeting; and the resulting preliminary ACE feedback on potential regulatory feasibility of the proposed restoration project and potential suggestions on alternative that could make the project more feasible (EPA/Bisland). 9) Hold a meting between this group of federal contacts and members of the Expert Panel to discuss the findings of report: Recommendations of the Expert Panel to Define Removal Rates for Individual Stream Restoration Projects (EPA/Winters). 10) Hold session at both the Bay Partners Stormwater Retreat (April 2013), and at the Chesapeake Watershed Forum (September 2013) to reach the restoration project practioners community to do outreach on the permit process and to encourage early/pre-application communication with ACE (ACE & EPA/Winters). 11) Provide 2012 National Fish and Wildlife (NFWF) request for proposal (RFP) that contains the links to geographic targeting maps (EPA/Winters). | Meeting purpose: 1) ID common goal for permitting of stream/wetland restoration projects. 2) ID win-win solutions for each organization to streamline permitting of stream/wetland restoration projects. 3) ID/agree on path/process/timeline to streamline permitting process, and deliver the highest level of public service, to facilitate stream/wetland restoration. Principles guiding this effort: 1) Protection/restoration of CB watershed is driver. 2) The science of stream/wetland restoration is evolving; restoration efforts are critical part of adaptive management; and work will be based on most recent science (as accepted by scientific community). 3) Mutual recognition that we want to avoid decisions that result in unintended environmental and policy consequences. Meeting agenda topics: 1) introductions; 2) background/need for stream/wetland restoration permit discussion; 3) EPA revised grant guidance; 4) permit streamlining/"Lean" government; 5) regulatory review process/need for a clearly articulated process for applicants; 6) alternatives analyses guidelines; 7 pre/post project monitoring; 8) post project maintenance; 9) financial assurances; 10) responsibilities for permitee upon project failure; and 11) summary/next steps. Action items: Eleven action items generated. | Julie Winters
2013-03-01 | HGIT STAC workshop proposal on designing sustainable stream restoration projects within the CB watershed | STAC workshop proposal | Status: See final report issued on 5/26/2015. | Direct quotes of title and objective from the proposal are as follows. Stated title: "Designing Sustainable Stream Restoration Projects within the Chesapeake Bay Watershed". Stated Objective: "Create agreement among practioners, regulators and scientists on a common language and methods for designing sustainable stream restoration projects that improve the functional elements of stream health to address water quality, climatological impacts, physical and biological components within the stream and adjacent riparian zone." | Jeff Horan, Chair HGIT
2013-03-12 | Meeting on Restoration and Regulation held at MDE - Attended by 100 people from regulatory and restoration communities | Meeting agenda | Status: meeting summary was issued on 5/24/2013. | Agenda 1) Purpose and need section of permit application, ID issues and any hurdles, and propose solutions. 2) Hydrology and hydraulics section of the permit application, discuss when and why this section is required, and address applicant concerns. 3) Alternatives analysis section discussing what types and depth of information are/should be needed as part of the alternatives analysis under certain circumstances, ID issues and any hurdles, and propose solutions. 4) Additional Supporting documentation needs and requirements beyond that ID'd during first three discussions. 5) What happens in cases of benefits tradeoffs - panel discussion. 6) Other issues/proposed solutions 7) Summary, wrap up and next steps. | Jana Davis
2013-03-25 | Status update on 1/24/2013 meeting action items | Summary compilation document | Compilation of all action item documentation from the 1/24/2013 meeting between EPA/ACE/FWS. Status: summary document containing all action items completed and distributed. | Document provides in one place all of the responses and follow up documents for each of the eleven actions items from the 1/24/2013 meeting between EPA/ACE/FWS. | Julie Winters
2013-05-24 | Meeting summary: 3/12/2013 CBT/MDE restoration and regulation forum | Meeting summary | Status: the following is a summary status of the six items (and the related sub-items) from the 3/12/2013 meeting, as captured in the 5/28/2013 meeting summary. 1) Clarification of permit requirements. a. Website - Getting basic information to permit applicants: Status: MDE has made some changes and will continue to make additional changes to the “How do I get a wetlands and waterways permit” section of their website. b. Checklists – Status: As of 2013, both MDE and Army Corps were producing checklists to make very clear what an applicant has to submit as part of the initial permit process, and how much detail needs to be in each section. E.g., Bill Seiger is working on a specific checklist for the H&H section of the permit application. NEED TO CHECK ON WHERE THEY ARE WITH THIS c. Alternatives analysis - There were a lot of questions about the alternatives analysis section of the permit application; what constitutes a complete enough alternatives analysis and when one is required. Status: As of 2013, MDE agreed to provide more guidance on this front. NEED TO CHECK ON UPDATE d. Monitoring - Need was discussed to better clarify what the requirements for monitoring are, and that perhaps some consistency could be discussed (though see big picture suggestion for monitoring below) Status: The conversation on the monitoring front has centered on concentrating monitoring efforts on answering key questions as opposed to collecting unfocused data everywhere. See below on pooled monitoring approach. 2) Pre-application and JE meetings - Getting feedback before too long in the process. STATUS: Pre-app meetings are happening with greater frequency, and helping, though not solving all issues, especially where there is disagreement about trade-offs, practice type, etc. a. MDE, EPA, and the Army Corps will provide additional clarification about what applicants should bring to pre-application meetings. Status: UNKNOWN _ have to check with MDE b. Applicants who have long-term goals to implement many projects, like county governments implementing their WIPs or other applicants with a watershed focus, might consider requesting a “scoping” pre-application meeting in which a suite of project sites are presented, and together, regulatory agencies can provide early input and guidance. Status: These kinds of meetings have begun to happen, and are helpful for regulatory agencies to get jurisdictions’ big picture goals. 3) Optimizing/triaging/improving speed of permitting for restoration projects. a. Projects in a WIP: The restoration community requested that MDE consider the WIPs/MS4 analysis, which already has sign-off by both MDE and DNR, as a beginning basis of the alternatives analysis in the permit application, potentially fulfilling some requirements of the alternatives analysis of a permit application in cases in which a project appears in a WIP/MS4 permit. However, some issues pertaining to the alternatives analysis may still persist. Status: Follow Up Note: After this meeting, MDE Wetlands and Waterways Program staff further evaluated some WIPS and MS4 watershed restoration plans in the context of contributing to the alternatives analysis required for permits, and found the plans’ suitability in addressing requirements was variable. MDE would be available to meet with local jurisdictions to discuss how, in general these plans would be used in permit review and reduce additional information requests. b. Projects at a smaller scale Status: Unknown c. Projects that connect a floodplain with minimal alteration of existing vegetative communities and do not increase flood risk to adjacent property owners without their permission. Status: Unknown 4) Monitoring, a new proposal for pooled monitoring. a. A general consensus emerged from the meeting, reflected from multiple sectors, that rather than require some level of monitoring beyond an inexpensive rapid assessment on each individual project, which may be data collection using different techniques of different parameters, instead we consider a system in which monitoring is focused to fully address specific questions. This idea needs to be fully explored with regulatory agencies and a process fully developed. Status: This effort has begun, in the form of the pooled monitoring effort and the Restoration Research funding opportunity led by the Trust. At present focused in MD, but hopefully will expand. b. All monitoring data should be collected in one place, and should be consistent enough that it makes sense in one place – a clearinghouse, a repository. Status: Not yet initiated. Value of existing data is debated; some think could be very useful and therefore worth this effort. MDE does currently store MS4 data. Individual project permit data are not stored in a repository. c. Perhaps a funding source can be identified to pay for additional monitoring that is guided by a panel. Status: Completed step 1 and ongoing. Regulatory and practitioner communities polled for top questions. Trust, DNR, and EPA currently funding a first round as of 2015. d. A panel would get together to discuss the restoration questions that need to be addressed to which this pooled monitoring effort would be applied, and questions of methodology and analysis. Status: Completed step 1 and ongoing. Regulatory and practitioner communities polled for top questions. Trust, DNR, and EPA currently funding a first round as of 2015. e. We need to study innovative practices. Status: Completed step 1 and ongoing. Trust, DNR, and EPA currently funding a first round as of 2015. Other funding sources can be and are focused on innovative practices as well. f. We need to study failures and learn from them (and not pretend they don’t exist). Status: Not yet formally addressed. Would propose a forum in which the sole topic is failures. 5) Innovation. Status: Not specifically tackled, yet. a. Innovation should be encouraged to identify better practices, more efficient practices, and advance restoration goals faster. b. MDE will not allow innovative projects that may have adverse impacts on one set of resources without monitoring, and perhaps without the designer in the field during construction. c. We need to have reproducibility of results. 6) Scientists and Regulators meeting - Regulatory agencies indicated an interest in and need for the restoration and scientific communities to get new information about practices and outcomes to them. Status: Discussion about an annual forum has occurred, but not yet carried out. Will ultimately by tied with pooled monitoring effort. NEXT STEPS: 1) Clarification and training – MDE and the Corps will continue to work on clarifying needs in certain parts of the application, including building the checklists, and will then offer training to the restoration community. Status: Have to check in with MDE and Corps on what changes they made since 2013. 2) Pooled monitoring Discussion – a group from the community representing each sector should meet to discuss this idea and how it would work. Status: Completed step 1 and ongoing. A group including practitioners, MS4s, Army Corps, EPA, FWS, MDE, DNR met over 2014 to articulate a framework. Trust, DNR, and EPA currently carrying out a first round as of 2015. 3) Research questions needs discussion – a group from the community representing each sector should meet to articulate research into outcomes of practices, methodology, and data analysis Status: Completed step 1. Regulatory and practitioner communities polled for top questions. Trust, DNR, and EPA currently funding a first round as of 2015. 4) Regenerative stormwater conveyances discussion– We stayed away from this specific topic during this meeting, but many agreed that the community, all sectors, need a meeting to hash out what we know about this practice, what we don’t know, the trade-off issues, and how we’re going to have answered what we don’t know about the practice. Status: Several relatively informal discussions have occurred among regulatory and practitioner communities. A full forum in which this issue is hashed out should occur. 5) Getting science to regulators – We need to set up at least one session, and consider a system, to bring to regulators new science information that has recently emerged. Status: Discussion about an annual forum has occurred, but not yet carried out. Will ultimately by tied with pooled monitoring effort. | The following is a summary of the 3/12/2013 meeting. 1) Clarification of permit requirements. a. Website - Getting basic information to permit applicants: MDE has made some changes and will continue to make additional changes to the “How do I get a wetlands and waterways permit” section of their website. b. Checklists – both MDE and Army Corps are producing checklists to make very clear what an applicant has to submit as part of the initial permit process, and how much detail needs to be in each section. E.g., Bill Seiger is working on a specific checklist for the H&H section of the permit application. c. Alternatives analysis - There were a lot of questions about the alternatives analysis section of the permit application; what constitutes a complete enough alternatives analysis and when one is required. MDE has agreed to provide more guidance on this front. d. Monitoring - Need was discussed to better clarify what the requirements for monitoring are, and that perhaps some consistency could be discussed (though see big picture suggestion for monitoring below). 2) Pre-application and JE meetings - Getting feedback before too long in the process. a. MDE, EPA, and the Army Corps will provide additional clarification about what applicants should bring to pre-application meetings. b. Applicants who have long-term goals to implement many projects, like county governments implementing their WIPs or other applicants with a watershed focus, might consider requesting a “scoping” pre-application meeting in which a suite of project sites are presented, and together, regulatory agencies can provide early input and guidance. 3) Optimizing/triaging/improving speed of permitting for restoration projects. a. Projects in a WIP: The restoration community requested that MDE consider the WIPs/MS4 analysis, which already has sign-off by both MDE and DNR, as a beginning basis of the alternatives analysis in the permit application, potentially fulfilling some requirements of the alternatives analysis of a permit application in cases in which a project appears in a WIP/MS4 permit. However, some issues pertaining to the alternatives analysis may still persist. Follow Up Note: After this meeting, MDE Wetlands and Waterways Program staff further evaluated some WIPS and MS4 watershed restoration plans in the context of contributing to the alternatives analysis required for permits, and found the plans’ suitability in addressing requirements was variable. MDE would be available to meet with local jurisdictions to discuss how, in general these plans would be used in permit review and reduce additional information requests. b. Projects at a smaller scale c. Projects that connect a floodplain with minimal alteration of existing vegetative communities and do not increase flood risk to adjacent property owners without their permission. 4) Monitoring , a new proposal for pooled monitoring. a. A general consensus emerged from the meeting, reflected from multiple sectors, that rather than require some level of monitoring beyond an inexpensive rapid assessment on each individual project, which may be data collection using different techniques of different parameters, instead we consider a system in which monitoring is focused to fully address specific questions. This idea needs to be fully explored with regulatory agencies and a process fully developed. b. All monitoring data should be collected in one place, and should be consistent enough that it makes sense in one place – a clearinghouse, a repository. c. Perhaps a funding source can be identified to pay for additional monitoring that is guided by a panel. d. A panel would get together to discuss the restoration questions that need to be addressed to which this pooled monitoring effort would be applied, and questions of methodology and analysis. e. We need to study innovative practices. f. We need to study failures and learn from them (and not pretend they don’t exist). 5) Innovation. a. Innovation should be encouraged to identify better practices, more efficient practices, and advance restoration goals faster. b. MDE will not allow innovative projects that may have adverse impacts on one set of resources without monitoring, and perhaps without the designer in the field during construction. c. We need to have reproducibility of results. 6) Scientists and Regulators meeting. Regulatory agencies indicated an interest in and need for the restoration and scientific communities to get new information about practices and outcomes to them. NEXT STEPS: 1) Clarification and training – MDE and the Corps will continue to work on clarifying needs in certain parts of the application, including building the checklists, and will then offer training to the restoration community. 2) Pooled monitoring Discussion– a group from the community representing each sector should meet to discuss this idea and how it would work. 3) Research questions needs discussion– a group from the community representing each sector should meet to articulate research into outcomes of practices, methodology, and data analysis. 4) Regenerative stormwater conveyances discussion– We stayed away from this specific topic during this meeting, but many agreed that the community, all sectors, need a meeting to hash out what we know about this practice, what we don’t know, the trade-off issues, and how we’re going to have answered what we don’t know about the practice. 5) Getting science to regulators – We need to set up at least one session, and consider a system, to bring to regulators new science information that has recently emerged. | Jana Davis
2013-07-12 | Teleconference of Stream Restoration Expert Panel check in on "6 month test drive | Agenda | Status: the following is a summary status of the next steps taken. - Jeff Hartranft for PA DEP will present monitoring results from a legacy sediment removal project at Big Spring Run to the Panel. Refinements to the protocols for legacy sediment removal projects will be considered. - Protocol revisions will be complete by the end of December. - Appendix F to be completed this winter that addresses modeling concerns. - Key protocol improvement will be presented to the WQ GIT early 2014 for final approval - User training? | Agenda - Review of 6 month test drive process. - Summary of results of test drive. - Panel discussion of suggested revisions based on the test drive. - Next Steps. | Stream/Sediment Coordinator (Stack/Fraley-McNeal)
2013-07-16 | Meeting/summary: stakeholder/regulatory stream/wetland restoration project permitting - 70 attending, of which 55 in person and 15 on phone | Meeting agenda and summary | Meeting follow-up: - Explore ACE leading an effort with other state/federal co-regulators to: 1) conduct the field triage necessary to ID a significant group of projects for which permitting can be expedited; and 2) agree upon the mechanism for permitting that is first set. - ACE, EPA and jurisdiction work collaboratively to determine if county/municipal WIPs can satisfy the need for alternatives analysis. - Address the (continues to be an ongoing issue) methods to b used for providing clarity of feedback from the pre-application discussions. - Consider the true lifecycle of a restoration project, from inception, pre-application, design, construction, completion, maintenance, and ongoing monitoring, rather than just counting only the permit application period clock as the measure of whether a project is moving through the system at the acceptable pace. - Explore further the lessons learned from the PA Big Spring Run restoration and determine if successes can be applied to other PA projects or projects across the entire watershed. - ACE and EPA/EAID to identify proper contact to participate as a member of the Habitat GIT. - Consider having the ACE join the FWS/MDE effort to develop a guide on "Stream Assessment, Design, Design Review, and Monitoring Guidelines." Status: unknown for any of the items listed. | Meeting synopsis: On 7/16/2013, the EPA (CBP/EAID/WPD) & ACE hosted a meeting with a very broad group of interested stakeholders to 1) follow up on the federal actions and activities to streamline project permitting, and 2) have dialogue and receive feedback on their restoration efforts. Meeting agenda: 1) Federal contact debrief on completed actions/products. 2) ACE reviews permitting tools. 3) Habitat GIT debriefs on efforts related to permitting restoration projects. 4) Update from CBPO's stream/sediment coordinator on model and expert panel technical/science work supporting stream/wetland restoration. 5) Update from MDE on restoration/regulation discussions. 6) MDE & FWS partner to develop stream assessment, design, review and monitoring guidelines. 7) DNR provides lessons from March 2013 site tours of restoration sites. 8) Restoration practioners feedback. 9) Next steps. | Nick DiPasquale
2014-01-27 | Site Tour of stream/wetland restoration sites. Hosted by EPA/EAID for Regional Administrator | Site toured summary one-pagers, and summary funding data | Status: no known follow up nor actions. | EPA/EAID selected several stream/wetland restoration project sites in Anne Arundel County to show to the Regional Administrator through site visits. The sites were: Four Seasons; Crofton; Riva Road; Cabin Branch; Clements Creek; and Carriage Hills. Participants included: EPA: Garvin, Pomponio, McNally (for Capacasa), DiPasquale, Corbin, and Miller. DNR: Gill, and Dawson. MDE: Kearney, and Seiger. ACE/Baltimore: Jordan, and Pace. | Nick DiPasquale
2014-01-24 | Guidance document prepared by CBP stream/sediment coordinator | Guidance document | Status: Guidance contains the following sections. Part 1: the need for verification. Part 2: key definitions for stream restoration project verification. Part 3: background on verification of stream restoration projects. Part 4: guidance for verifying stream restoration projects. | CBP stream/sediment coordinator prepared guidance for verifying stream restoration projects. | Stream/Sediment Coordinator (Law)
2014-01-27 | Study - DC required to conduct yellow boy study | Note to file | Status: unknown. | DC contacts report to CBPO that EAID was forcing them to conduct a yellow boy (iron) study in order for a restoration permit to be considered beyond the pre-application discussion. Study was at a significant and unbudgeted cost to DC (~$30,000) | Nick DiPasquale and Julie Winters
2014-02-14 | Public notice from ACE/Balti for comment period on restoration permit for Clements Creek confluence (Severn River Keeper) | Joint public notice from ACE/Balti and MDE | Status: unknown. | "The purpose of this joint public notice is to announce that the U.S. Army Corps of Engineers (COE) and the Maryland Department of Environment (MDE) have received and are evaluating a joint permit application as described below for the Department of the Army authorization pursuant to Section 404 of the Clean Water Act (33 U.S.C. 1344) and State authorization pursuant to Title 5, Subtitle 5 (Waterway Construction) and Title 5, Subtitle 9 (Nontidal Wetlands) of the Environmental Article, Annotated Code of Maryland. ..... In Clements Creek, north of Alice Court, in Annapolis, Anne Arundel County, Maryland." | ACE/Balti: Dinne, and MDE" Flint
2014-03-05 | Training on Stream Function Pyramid funded by EPA provided by FWS; approximately 40 trainees | Training | Status: training completed. | Training session titled: "Application of the Stream Functions Pyramid Framework to Regenerative Design". Agenda: - Issues and challenges. - Stream function pyramid framework (SFPF). - Changes to SFPR measurement methods and performance standards to assess regenerative design approach. - Tour regenerative design site and two impaired reaches. - Function-based goals and objectives and restoration potential. - Function-based restoration project process. - Predict functional lift and restoration potential for two impaired sites. - Discuss application of SFPF moving forward. | EPA: DiPasquale, FWS: Starr
2014-05-06 | STAC workshop on stream restoration design; approximately 70 attendees | Agenda | Status: See final report issued on 5/26/2015. | Workshop objective "Create agreement among practioners, regulators and scientists on a common language and methods for designing sustainable stream restoration projects that improve the functional elements of stream health to address water quality, climatological impacts, physical and biological components within the stream and adjacent riparian zone." Agenda Track 1: Setting the stage - stream functions. Track 2: Organization of functions into a framework, objectives, assessment parameters, measurement methods, and performance standards. Track 3: Application of stream function pyramid framework. Track 4: "Strawman" function-based stream restoration project process. Track 5: Setting goals and objectives and identifying problems. Track 6: Selection of function-based assessment parameters. Track 7: The determination potential/functional uplift and constraints/limiting factors. Track 8: Synthesis session: research needs and next steps. | STAC: Gardner; Stream/Sediment Coordinator: Law
2014-05-14 | Federal agency FY2014 action plan - Executive Order 13508 | Executive Order 13508 - Combined FY2014 Action Plan Report and FY2013 Progress Report - Strategy for Protecting and Restoring the Chesapeake Bay Watershed | Status: Milestones and and related other key actions are expected to be incorporated into the management strategy workplans; this step is pending and to date the actual milestones and key actions have not been specifically and directly addresses, however some steps in the general direction have been taken. The 3/2015 reports these items to be ongoing. | Milestones and action items in report: - 2014-2015 Water Quality Outcome Milestone: federal permitting agencies to work with resource agencies to develop and implement permitting streamlining measures under CWA Section 404, which would cover TMDL implementation activities proposed in waters of the US that are designated to reduce nutrient and sediment pollution that promote innovation and are consistent with sound science, ecosystem principles, applicable laws and regulations, and habitat restoration goals of the CB Executive Order. Such measure may include the use of Categorical Exclusions, RGPs, and other mechanisms available under Section 404 of the CWA. - Stream Health Outcome: Improve the health of streams so 70 percent of sampled streams throughout the Chesapeake watershed rate fair, good or excellent, as measured by the Basin-wide BIBI, by 2025. Baseline: 45 percent of sampled stream sites are rated fair, good or excellent. - 2014-2015 Stream Restoration Outcome Milestones: -- Host STAC Workshop "Designing Sustainable Stream Restoration Projects with the CB Watershed" .... Workshop and Habitat GIT will develop recommendations, based on workshop outcomes, to recommend how the science can be used adaptively to promote innovation and expedite the regulatory permitting process in the pre-application phase. -- Update status of stream health through 2012 and develop progress to provide future updates. The STAR will update the indicator through 2012 through the CBP monitoring team. The STAR will work with the stream health workgroup to consider enhancements to the indicator determine frequency of updates based on data available from states. -- Federal permitting agencies to deliver timely feedback under the CWA section 404 and Fish and Wildlife Coordination Act during pre-application consulting regarding: site selection, design, and construction criteria for innovative restoration projects, including function-based assessment and monitoring requirements, responsibility in event of a failure, etc. -- Federal resource and permitting agencies to collaborate on an expedited permit review track, based on science recommendation from the STAC workshop above, for restoration projects that utilize common practices, and are implemented by resource agencies working in degraded landscapes. | Jim Edward
2014-05-15 | Meeting on restoration monitoring and research needs: regulatory perspective. Held at ACE/Baltimore and 50 people from regulatory community attended | Meeting summary | Recommendations: The 25 questions that were research oriented were then crafted into testable hypotheses by a subset of this group, and prioritized into a top 8 through vetting. Status: Pooled monitoring research questions were developed and a request for proposals was generated/released on 12/1/2014, awards were announced on 6/10/2015. Please see related entries on this spreadsheet. | The attendees, regulatory staff at various federal and state agencies, produced a list of about 40 questions they routinely have about restoration projects or practices in several categories. These questions were further divided into those that could be answered through research/monitoring, and those that were policy oriented. The 25 questions that were research oriented were then crafted into testable hypotheses by a subset of this group, and prioritized into a top 8 through vetting. | Jana Davis
2015-05-16 | Public notice from ACE/Balti for comment period and public hearing on proposed TMDL RGP | Public notice | Status: Public notice for comment period and public meeting issued and meeting held (6/19/2014), and SPN15-43 - Issuance of the CB TMDL RGP for a five year period was issued on 7/1/2015. | "The purpose of this public notice is to solicit comments from the public and announce the scheduling of a U.S. Army Corps of Engineers, Baltimore District public hearing regarding the proposed total maximum daily load regional general permit." | Bill Seib
2014-06-19 | ACE/Balti public hearing | Public hearing | Status: public hearing was held. | The public hearing was held by ACE/Balti to hear/record public testimony on the proposed total maximum daily load regional general permit. | Robert Pace
2014-12-01 | RFP release: on restoration research questions | Request for proposals (RFP) | Status: results of RFP successful proposal announced on 6/10/2015. Ten applicants responded to the call, and four were chosen to address questions pertaining to RSC nutrient and sediment removal efficiencies, impact of building stream restorations in the wet vs. dry, impact of region and stream construction technique on biological response, and how stable physically certain stream restoration practices are. Successful proposal selected were VA Polytechnical and State University; Straughan Environmental, Inc.; Smithsonian Institution; and UMCES. | The Chesapeake Bay Trust led a group of regulatory, restoration, practitioner, and MS4 individuals to craft a call to answer the 8 top questions posed by the regulatory community (with input from the practitioner community). | Jana Davis
2015-05-26 | STAC workshop final report on designing sustainable stream restoration projects with in the Chesapeake Bay watershed | STAC workshop final report | Status: Summary recommendations from workshop report are as follows. The Chesapeake Bay Program's (CBP) Habitat Goal Implementation Team (GIT) convened this workshop to discuss the facilitation of effective stream restoration projects within the Bay watershed that can create the functional lift needed to restore Bay health, and not focus solely on nutrient and sediment reductions. Key to this successful outcome is generating an understanding and agreement on the major elements of stream functions that will allow stream restoration practitioners, researchers, and the regulatory community to implement sustainable stream restoration projects. The workshop proposed a Function-based Stream Restoration Project Process to generate discussion that formed the basis for the key workshop findings and recommendations. 1. Resoundingly, workshop participants stressed the need for stream restoration projects to be part of an overall watershed strategy for the Chesapeake Bay. The context of the watershed occurs at two different stages of stream restoration projects. First, a broad-scale watershed planning effort provides a prioritized set of recommended upland and in-stream projects for restoration, or assessments used for alternative site analysis. Examples of watershed plans include: EPA 319 watershed planning guidance (EPA 2008), TMDL implementation plans, and watershed implementation plans (WIPs). The second type of watershed assessment determines watershed characteristics and limiting factors that may influence the proposed project area after the stream project site is selected, and will play a significant role in determining the restoration potential of the stream reach. This can be accomplished by establishing the overall health of the watershed and identifying constraints to establishing the cause and effect relationship between the watershed and the proposed restoration site. Specifically, determining whether the link between watershed health and contributing factors to the proposed site are degradation issues. Results of the reach-level function-based assessment will be used in combination with the watershed assessment to assist in the development of restoration plan alternatives. 2. An interested party, such as the CBP‟s Stream Health Workgroup, should adopt the proposed Function-based Stream Restoration Project Process outlined in this report as a starting point to develop a unified process and work with the Partnership to facilitate development of the proposed guidance. The guidance documents and checklists developed by the U.S. Fish and Wildlife Service (USFWS) under contract with Maryland Department of the Environment (MDE) may serve as a template to begin these discussions since these documents follow the Function-based Stream Restoration Project Process presented and discussed at the workshop. In addition, the Pennsylvania Department of Environmental Protection (PADEP) has developed similar methodologies to integrate stream functions into their approval process. The organization that advances the adoption of a function-based process should coordinate with these existing efforts. There was general agreement from workshop participants that a science-based, methodological process is needed to clearly define project goals and objectives that lead to the identification of measurement parameters to evaluate the restoration of stream functions. The function-based process would include a watershed assessment (previously described) to identify the limits and opportunities to restore identified stream functions. 3. Workshop participants identified areas for which monitoring efforts may enhance stream restoration science and implementation. For example, there is a need to develop a baseline list of critical stream functions and assessment parameters to monitor the effectiveness of stream restoration to support the programmatic goal of the Chesapeake Bay TMDL, which is the driver for many stream restoration projects in the watershed. Participants recommended developing a monitoring consortium or framework that would pool monitoring resources and address key research issues such as critical stream functions, intermediate functional standards, continuum of risk, and at-risk or non-functioning performance standards, among others. The adoption of a pooled monitoring approach would allow researchers, practitioners, and the regulatory agencies to collaboratively review monitoring needs to evaluate restored or enhanced stream functions. During the summer and fall of 2014, an ad-hoc committee represented by regulatory agencies (U.S. Army Corp of Engineers [USACE], MDE, USFWS), state and resource agencies (Maryland State Highway Administration [SHA]), and stream organizations ([Maryland Stream Restoration Association (MSRA]) was coordinated and lead by the Chesapeake Bay Trust to explore and begin development of a pooled monitoring approach. Data generated from Big Spring Run, PA (PADEP 2013) may also advance the development of performance levels for stream geomorphic functions. Overall, monitoring data generated from stream restoration projects should provide the potential to demonstrate restored steam functions. Participants agreed that the existing monitoring needs required by permits were not necessarily sufficiently robust to assess the full breadth of stream functions (e.g., current monitoring focus on stream stability; how well is this rock vane performing?). It was also acknowledged that permit monitoring requirements are prescribed based on the presence/absence of aquatic resource tradeoffs and may not require monitoring data beyond stream stability. Pooled monitoring to address specific research questions should be pursued. 4. It is recommended that the Urban Stormwater Workgroup and Stream Health Workgroup coordinate efforts to develop guidance (e.g., via an expert panel) to align how the restoration/enhancement of stream functions translates to nitrogen, phosphorus, and sediment „credit‟. The CBP recently approved recommendations to credit stream restoration projects along with guidance to verify and report stream restoration as a best management practice (BMP). This guidance would discuss how stream restoration BMP protocols1 fit within a functional framework for stream restoration project design, as well as verification guidance2 such that post-construction assessments can verify that the project is meeting minimum performance standards to warrant use of either the general interim pollutant reduction rates or the reduction rates related to one of the four specific protocols approved by the expert panel. | Workshop objective "Create agreement among practioners, regulators and scientists on a common language and methods for designing sustainable stream restoration projects that improve the functional elements of stream health to address water quality, climatological impacts, physical and biological components within the stream and adjacent riparian zone." Report of the STAC workshop issued by STAC on 5/26/2015. | STAC: Gardner; Stream/Sediment Coordinator: Law
2015-06-10 | Press announcement from CBT on restoration research RFP results | Press announcement | Status: Ten applicants responded to the call, and four were chosen to address questions pertaining to RSC nutrient and sediment removal efficiencies, impact of building stream restorations in the wet vs. dry, impact of region and stream construction technique on biological response, and how stable physically certain stream restoration practices are. Successful proposal selected were VA Polytechnical and State University; Straughan Environmental, Inc.; Smithsonian Institution; and UMCES. | On 6/10/2015, CBT, in partnership with DNR and EPA, and with input from MDE, FWS, and other agency and technical partners, announced four recipients of its new collaborative Restoration Research Grant Program. | Jana Davis
2015-06-30 | Stream health management strategy provided to the MD | Management strategy | Status: Final stream health management strategy posted to CBP website. It is explicit in 2014/2015 Executive Order action plan that actions and milestones are to be included in the biennial plans that result from the management strategies. | Vital habitats goal: "Restore, enhance and protect a network of land and water habitats to support fish and wildlife, and to afford other public benefits, including water quality, recreational uses and scenic value across the watershed." Stream health outcome: "Continually improve stream health and function throughout the watershed. Improve health and function of 10 percent of stream miles above the 2008 baseline for the Chesapeake Bay watershed." This outcome is to be tracked through improvements in the Chesapeake Bay-wide Indicator of Biotic Integrity (Chessie-BIBI). The Chessie BIBI is derived using individual state benthic macroinvertegrate data collected based on a common methodology agreed to by the Bay Program's Nontidal Monitoring Workgroup. Five strategies: 1) ID an appropriate suite of metrics to measure the multiple facets of stream health to complement the baywide Chessie BIBI. 2) Provision of adequate funding and technical resources to support functional lift in stream restoration projects, in addition to nutrient and sediment reduction. 3) : ….State and federal agencies shall ensure the the participation of location communities in support of activities that advance project implementation. Ongoing coordination with stream restoration stakeholders needs to be improved to identify and remove barriers providing a clearly defined path to expedite the submittal and review of permit applications, whether the proposed activity is for marginal streams, impaired streams, or for credit in the Bay TMDL. 4) Develop and promote holistic stream restoration design guidelines that identifies the level of degradation and improvement of stream functions and key stressors/factors limiting potential uplift. 5) : Work with Chesapeake Bay Partners to include the Enhancing Partnering, Leadership and Management GIT, to enhance the capacity of local governments, organizations and landowners of beneficial stream restoration and maintenance practices. | Stream health workgroup; co-chairs: FWS/Star, and CB stream/sediment coordinator/Law
2015-07-01 | Public notice from ACE/Balti to Issue the CB TMDL RGP for five year period | CB TMCL RGP | Status: 7/1/2015 Issuance of the Chesapeake Bay Total Maximum Daily Load Regional General Permit (Bay TMDL RGP) for a five year period. | 7/1/2015 Issuance of the Chesapeake Bay Total Maximum Daily Load Regional General Permit (Bay TMDL RGP) for a five year period. SUBJECT: Issuance of the Chesapeake Bay Total Maximum Daily Load Regional General Permit (Bay TMDL RGP) for a five year period. The purpose of this special public notice is to inform you that the Baltimore District, U.S. Army Corps of Engineers is issuing the Chesapeake Bay Total Maximum Daily Load Regional General Permit (Bay TMDL RGP) authorizing activities in waters of the U.S., including jurisdictional wetlands, that are part of an acceptable watershed strategy, such as a Chesapeake Bay TMDL Watershed Implementation Plan (WIP), whose purpose is to identify implementation activities needed to meet nutrient and sediment load reduction targets in accordance with the Chesapeake Bay TMDL. For a full description of the types of activities authorized by the Bay TMDL RGP, the applicable waters, and the permit conditions, please see the attached Bay TMDL RGP. In accordance with 33 CFR 325.5(c), the proposed Bay TMDL RGP authorizes the work described herein, pursuant to Section 10 of the Rivers and Harbors Act of 1899 (33 U.S.C. 403) and/or Section 404 of the Clean Water Act (CWA) (33 U.S.C. 1344). Applicable waters include nontidal waters and nontidal wetlands in the Chesapeake Bay watershed within the State of Maryland, the District of Columbia, and certain military installations in northern Virginia within the regulatory geographic boundaries of the Corps (i.e., Fort Belvoir, Fort Myer, and the Pentagon). All activities eligible for authorization under the Bay TMDL RGP must meet all terms and eligibility criteria, limitations, and general conditions specified in the Bay TMDL RGP. In order for the Bay TMDL RGP to be valid, a person or entity seeking verification under the Bay TMDL RGP must obtain all other Federal, state and/or local authorizations required by law prior to commencement of such work in waters of the U.S. Activities that do not comply with the provisions of the Bay TMDL RGP may require authorization under an alternative permit type (e.g. ., State Programmatic General Permit, Nationwide Permit, or Individual Permit). The Bay TMDL RGP provides a streamlined form of Department of the Army authorization for certain recurring activities that are similar in nature, have minimal individual and cumulative adverse effects on the aquatic environment, and satisfy other public interest review factors. A copy of the Bay TMDL RGP is attached and may also be found on the Baltimore District Regulatory website at: http://www.nab.usace.army.mil/Missions/Regulatorv.aspx The Bay TMDL RGP is effective as of July 01, 2015. The Bay TMDL RGP will expire on June 30, 2020 unless suspended or revoked. | Bill Seib
2016-12-30 | ICPRB projects/proposals to support stream health management | Project summary | Status: project in progress July 2015-December 2016. Products: final report, outreach through the Potomac River Basin Drinking Water Source Protection Partnership (DWSPP). | Title: An Assessment of Forest Protection Opportunities and Potential Reductions in Sediments, Nutrients, and Total Organic Carbon in the Freshwater Potomac River Watershed Objectives: 1) Evaluate the relationship between forest cover and source water quality in the form of nutrients, sediments and total organic carbon near Potomac water supply intakes for the Washington DC region. 2) Determine water quality changes near Fairfax Water, Washington Aqueduct, and WSSC’s Potomac intakes by preserving varying degrees of existing, upstream forested lands 3) Conduct an initial assessment of the impact of water quality changes on treatment costs 4) Use the results to develop recommendations for source water protection activities Geographic Region: Potomac mainstem and tributaries in the upper basin Motive: Source water protection is increasingly seen as an important component of a multi-barrier approach to providing high-quality drinking water. Source water protection may include activities to protect or restore forests. The ICPRB project complements efforts led by the American Water Works Association to link watershed condition and water treatment costs for utilities using surface water from forested watersheds as a water supply. Funding: Water Research Foundation, US Endowment for Forestry and Communities, District of Columbia Water, Fairfax Water, Washington Aqueduct, Washington Suburban Sanitary Commission | Claire Buchanan, Heidi Moltz, and Karin Bencala
2017-12-30 | ICPRB projects/proposals to support stream health management | Project summary | Status: project in progress FY2016-2017. Products: Maps, spreadsheets, manuscript for publication. | Title: The Effects of Impervious Cover on Stream Flow under Various Watershed Conditions in the Potomac Basin Objectives: 1) Characterize flow alteration (departure from a baseline condition) in the Potomac basin at the HUC12 level 2) Quantify the impacts of impervious surface cover on stream flow 3) Determine if impervious surface impacts are intensified by certain watershed characteristics (slopes, precipitation regimes, soil types, etc.) Geographic Region: Middle and upper Potomac River basin (excludes Coastal Plain ecoregion) Motive: Assist state and local decision-makers in forecasting and managing the negative impacts of impervious areas on stream flow patterns. Funding: CWA Section 106 grant (98339412) | Claire Buchanan and Heidi Moltz
2016-09-30 | ICPRB projects/proposals to support stream health management | Project summary | Status: project in progress January 2015-September 2016. Products: database, spreadsheets, report. | Title: 2015/2016 Update and Refinement of the “Chessie BIBI” Indicator of Stream Health Objectives: 1) Update and refine the existing Chesapeake basin-wide index of biotic integrity for stream macroinvertebrates, or “Chessie BIBI” 2) Incorporate genus-level metrics into the index if warranted 3) Make the procedure for calculating the index simpler and more accessible to users 4) Develop a “2008 baseline” against which the progress in restoring stream health (trends) can be measured Geographic Region: Chesapeake Bay basin Motive: Refine Chessie BIBI with genus-level metrics; expand characterization of stream reference conditions to include watershed features; assess stream biological condition across jurisdictional boundaries. Funding: CBP 117 grant (96305701) | Claire Buchanan
2017-12-30 | ICPRB projects/proposals to support stream health management | Project summary | Status: project in progress FY2016-FY2017. Products: maps of non-tidal streams and rivers in Chesapeake Bay basin with a) inherent potential for filamentous algae growth (September 30, 2016) and b) actual excess filamentous algae growth (March 31, 2017), report. | Title: Filamentous Algae Project Objectives: 1) Use hypotheses identified in ICPRB FY15 literature review (includes the WVDEP alkalinity/hardness hypothesis) to analyze available water quality data and map USEPA Region 3 streams and rivers with chemical conditions that potentially favor algae growth 2) Continue to obtain locational information about filamentous green algal blooms from state agency field personnel, water suppliers, river guides, and others 3) Assemble map of observed algal distribution with a goal of “testing” hypotheses against empirical information Geographic Region: Central Appalachian, Ridge & Valley, and Piedmont ecoregions of USEPA3 region Motive: Develop a better understanding of the inherent potential for filamentous algae growth in regional flowing waters, and their links to nutrient pollution Funding: CWA Section 106 grant (98339412) | Claire Buchanan, and Gordon Michael Selckmann