## (Goal Name) Workplan
Outcome: Blue Crab
Goal:
Outcome: By 2025, …
Long term Target: 300 x by 2025
2 year Target: 75 by 2016
Management Approach 1:
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Conduct detailed assessments and prepare construction designs | Technical assistant - establish metrics and standards requirements | STAC, STAR | n/a | Oct. 2015 | n/a - staff | n/a | Permitting requirements, funding
| Design assessment tool | Partner x | n/a | Dec. 2015 | n/a - staff | n/a
| Conduct 75 assessments and 45 construction designs | Jurisdiction x | Counties: x, y, z | Apr. 2016 | 150000 | 50000
|  | Jurisdiction x | For more information www.xgrants.gov | Jul. 2016 |  | 25000
|  | Jurisdiction x | X River | Jul. 2016 |  | 50000
Totals | [5 empty] | 125000
gap $25,000
2. Develop a pilot project to improve outreach and develop tools targeted toward diverse populations who subsistence fish in areas of concern. | Develop communication tools | Diversity Action Team, Toxics workgroup, Comm. Workgroup | TBD | Jul. 2016 | 2000 | 2000 | Targeting Comm. & Outreach
| Pilot test in 5 locations |  |  |  | 8000 | 8000
Totals | [5 empty] | 10000
3. Improve monitoring programs to better measure and explain progress toward x. | STAC/STAR collaboration to reduce model uncertainty by integrating related information to better assess and communicate progress. | STAR STAC Partner x | n/a | Mar. 2016 | 310000 | 310000
Totals | [5 empty] | 310000
4. Find ways to create and expand employment opportunities to under-represented individuals and communities. | Form an ad hoc employment workgroup to make recommendations on best approaches for increasing employment and professional engagement. | X (lead) | n/a | Dec. 2015
| In 2015, evaluate all existing diversity programs to determine if there is a need to develop a strategy for improvement. | Diversity Action Team | n/a | Dec. 2015
| Improve existing and develop new environmental career opportunity outreach programs at 3 universities and 5 community college systems. | X (lead) | X County, X State | Dec. 2016 | 18000 | 13000
Totals | [5 empty] | 13000
gap $5,000
Management Approach 2:
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. xyz…
Total
2. xyz…
Total
Management Approach 3:
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. xyz…
Total
2. xyz…
Total
Management Approach 4:
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. xyz…
Total
2. xyz…
Total
**Note: As a member of the Chesapeake Executive Council and a signatory to the Chesapeake Bay Watershed Agreement, the Chesapeake Bay Commission (CBC) functions as the legislative arm of the Chesapeake Bay Program working within Maryland, Pennsylvania and Virginia and at the federal level to identify specific Bay management concerns requiring intergovernmental coordination and cooperation. CBC makes recommendations to the federal, state and local governments on legislative and administrative actions necessary to effectuate coordinated and cooperative management for the Bay watershed. The Commission will work collaboratively with Bay Program partners to identify legislative, budgetary and policy needs to advance the key actions identified in this outcome and to anticipate those needed in the future. The CBC’s work is supported by the annual appropriations of its three member states totaling $675,000 and is, on occasion, supplemented by project-specific grants.