## CRP & CREP
CREP ROLES AND RESPONSIBILITIES
FSA | NRCS | DOF | SWCD
OFFER and CPO DEVELOPMENT
ALL AGENCIES--Recruit enrollment of new CREP offers.
Accept offer for CRP/CREP on form CRP-2C.
Determine producer and land eligibility.
Provide CRP-2C to NRCS for CPO development. Provide CRP-2C to SWCD for budget planning. | Obtain CRP-2C from FSA and consult with producer to begin CPO development. |  | Obtain CRP-2C from FSA for budgeting purposes.
For applications that will involve tree or shrub planting, provide the following to DOF: CRP-2C; map showing location of site; soil map.
For tree planting practices: conduct field visit to determine resource concerns and need and feasiblity of CRP/CREP practices. Discuss and plan the CRP/CREP and other practices that may be needed.
| Layout and stake the area to be included in the program. | Begin developing tree planting plan.
Return CRP-2C to FSA for Measurement Service.
Perform Measurement Service.
Edit CLU in MIDAS to derive official CREP fields and acres.
Complete and finalize CRP-2C and return to NRCS, including CREP field and acreage measured to the .01.
Inform producer that the offer was acceptable using form letter CRP-23. |  | Develop Tree Planting Plan (DOF Form 75), including map. Provide Tree Planting Plan and map to NRCS and participant.
Complete and finalize CPO package.
CONTRACT APPROVAL and PRACTICE IMPLEMENTATION
Complete CRP-1 and obtain all required signatures. | Provide CPO package, including plan map, CPA-052, DOF plan & map, job sheets, and engineering designs to participant and FSA.
Complete eligbility documentation.
Complete CCC-770 prior to contract approval and document DD reviews.
Review and approve CRP-1 and CPO. Provide a copy of CRP-1 to SWCD. |  |  | Obtain CRP-1 from FSA.
Notify producers of approved CRP-1 using form letter CRP-24.
Issue cost-share documents and obtain producer signature(s).
Provide a copy of CRP-1 and cost-share documents to SWCD partners. |  |  | Obtain a copy of CRP-1 and cost-share documents from FSA.
Assist participant with practice installation.
Conduct a post-planting inspection to determine that seedlings were planted according to plan.
Assist producer with follow up spraying, coordinating with contractors, if needed.
Document inspection on DOF Form 83 and provide Form 83 to NRCS.
Certify completion/installation of all practices/components on FSA-848B in accordance with 2-CRP par. 508. Provide DOF form 83 to FSA.
Complete cost-share documents and issue cost-share payments. Provide a copy of payment information to SWCD. NOTE: If the practice is not installed according the NRCS standard, require corrective action before issuing payment. |  |  | Issue cost-share payment to producer.
PRACTICE MAINTENANCE AND MANAGEMENT
Re-inspect the site toward the end of the second growing season. Assist with subsequent follow up spraying based on plan.
Document results of Form 84. Review recommendations for maintenance with producer, including replanting. **WHAT IF LOW SURVIVAL?** Do another plan??
Provide Form 84 to NRCS.
Provide results of DOF re-inspection, Form 84, to FSA.
Address practice failure (i.e. <70% survival) in accordance with 2-CRP par. 493 B. Provide cost-share for re-establishment when appropriate.
Issue PIP to producer after practice is established. NOTE: For tree planting practices, the practice is considered established if there is > 70% survival at the end of year 2.
Conduct annual status reviews.
Conduct annual spotchecks per 2-CP.
Follow up on cases of noncompliance. IMPORTANT: Notify SWCD when contracts are terminated and collections are required.
Track mid-contract management.
Issue annual rental payments in October.