## Healthy Watersheds Workplan
Potential Priorities are highlighted in yellow
Outcome: Healthy Watersheds
Goal: Healthy Watersheds
Outcome: One-hundred percent of state-identified healthy waters and watersheds remain healthy.
Long term Target: all remain healthy in perpetuity
2 year Target: Not applicable to this outcome
Management Approach 1: Tracking Healthy Waters and Watersheds
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Continue gathering inventory of healthy waters and watersheds
Review and incorporate National Water Quality Assessment Program data and information. | Retrieve data and compare with State-identified Healthy waters and watersheds | USGS, CBPO GIS Staff | Chesapeake Bay Watershed | Current - Dec 2017 | Tracking: Inventory of Healthy Watersheds
Healthy waters and watersheds in DC | Identify healthy watersheds | DOEE - Water Quality Division | DC | Continuous
| Assess existing watersheds |  |  | Every other year
Healthy waters and watersheds in MD | Update the baseline mapping of state-identified Tier II healthy waters and watersheds. | MDE | Statewide | 1/1/2016, ongoing with new data and possible corrections
| Explore a science-based process to potentially include additional healthy watersheds for protection as needed (e.g., for drinking water protection, sturgeon habitat). | MDE, DNR | Statewide | 2017-03-01
NYSDEC Division of Water maintains and regularly updates an inventory of high quality waters statewide | Water quality is monitored by collecting physical, chemical and biological samples from surface, groundwaters sediment, and organism across the state each year. | NYSDEC Division of Water Bureau of Water Assessment | State Wide | On Going | Tracking: Inventory of Healthy Watersheds
Continue gathering inventory of Healthy Waters in PA | Continue to regularly update DEP's publicly-accessible list of surface water segments where data has been evaluated to indicate the designation/existing uses of a waterbody. These are found on DEP's website: www.dep.state.pa.us (keyword: water quality) [Designated or existing uses classified as Exceptional Value or High Quality are the basis for identifying PA's healthy waters.] | PA DEP | Statewide | Ongoing | Tracking: Inventory of Healthy Watersheds
Totals
2. Develop vulnerability information
Develop and implement a methodology to establish climate related goals and baselines for individual Chesapeake Bay Agreement Management Strategies such as the Healthy Watersheds Management Strategy. | Compile existing climate change vulnerability research and data, including available assessment products and tools. | STAR; Climate Resiliency Workgroup | Chesapeake Bay Watershed | 2017-12-17 | Tracking: How are healthy watersheds doing? Vulnerability informaiton, prioritization for protection.
| Work with the Climate Resiliency Workgroup to refine Climate Resiliency Analysis Decision Making matrix and recommend implementation process for applying matrix analysis and decision-making process to other Management Strategies such as the Healthy Watersheds Management Strategy. | Climate Resiliency Workgroup |  |  | Cross-cutting programmatic gap
Forecast land development scenarios | USGS will complete its Chesapeake Land Change Model so improved forecasts can be provided of areas where development will increase so states can assess the vulnerability of healthy watersheds and develop strategies to continue their protection. | CBPO and USGS | Chesapeake Bay Watershed | Current - Dec 2017 | Tracking: How are healthy watersheds doing? Vulnerability information, assessment information
Utilize sea level rise/storm surge assessments | Review and incorporate findings from the North Atlantic Coast Comprehensive Study: Resilient Adaptation to Increasing Risk. This refers to Appendix A, Engineering. | USACE, Maintain Healthy Watersheds GIT, and CBPO GIS Team | Chesapeake Bay Watershed | Current - Dec 2017 | Tracking: How are healthy watersheds doing? Vulnerability information, assessment information
Incorporate Energy Development Trends research into vulnerability assessment | Review and incorporate findings from the TNC study | TNC, Maintain Healthy Watersheds GIT, and CBPO GIS Team | PA and NY | 2017-12-01 | Tracking: How are healthy watersheds doing? Vulnerability information, assessment information
| Review and incorporate findings from USGS Shale Gas Development Study. | USGS, Maintain Healthy Watersheds GIT, and CBPO GIS Team | PA portion of the watershed | 2017-12-01 | Tracking: How are healthy watersheds doing? Vulnerability information, assessment information
Incorporate resiliency study | Review and incorporate findings from Habitat and Resiliency TNC study | TNC, Maintain Healthy Watersheds GIT, and CBPO GIS Team |  |  | Tracking: How are healthy watersheds doing? Vulnerability information, assessment information
Incorporate Resource Conservation Opportunity Areas | Incorporate the North Atlantic Landscape Conservation Cooperative work which identified RCOA's (Resource Conservation Opportunity Areas). This work is a roll-up of map layers that include climate resiliency information as well as development and other stressor information, to help managers hone in on the areas of greatest conservation (and restoration) opportunities for terrestrial and aquatic wildlife habitat. (see northatlanticlcc.org under "Projects") | USFWS, Maintain Healthy Watersheds GIT, and CBPO GIS Team |  |  | Tracking: How are healthy watersheds doing? prioritization for protection, assessment information
[From Land Use Methods and Metrics Development Workplan] Quantify impact of land conversion on healthy watersheds and habitats | Vulnerability to land conversions, both historical and future projections | CBPO, USGS, and LUWG | State-identified healthy watersheds | 2017-12-01 | Tracking: How are healthy watersheds doing? prioritization for protection, assessment information
| Impact (relates to tracking health) |  |  | TBD
Develop vulnerability information for healthy waters and watersheds in Maryland | Phase 1: Develop and implement basic analysis tools and methodology to characterize vulnerability of healthy watersheds to specific, future high-level risks. Initial process to include watershed attributes such as impervious cover, forest cover, capacity status, and growth modeling analysis. | MDE, MDP, DNR | Statewide | 2016-01-01 | Tracking: How are healthy watersheds doing? Vulnerability informaiton, prioritization for protection.
| Phase 2: Further develop and apply tools and methods to characterize vulnerability of healthy watersheds to specific, future high-level risks. Tools may additionally consider watershed condition, urban growth proximity/pressure, energy development trends, water demand forecasts, invasive species threats, upstream activities, land ownership type and plans, current transportation access, future transportation infrastructure plans, and other factors. | MDP, MDE, DNR | Statewide | 2018-01-01
| Translate vulnerability analysis into quantifiable attributes/chacteristics/factors, that can be used to determine a given watershed's ability to absorb additional impacts. Phase 1 risk analysis has identified 44 Tier II watersheds that are at risk of losing "healthy" status. | MDE, DNR | Statewide | 2016-07-01
Totals
3. Prioritize Protection
Assess protected status of healthy watersheds | TBD through cross-GIT tracking group. | Maintain Healthy Watersheds GIT |  |  | Tracking: How are healthy watersheds doing? Vulnerability informaiton, prioritization for protection.
Compile and publish bi-annual Chesapeake Bay Protected Lands Dataset | 1) Compile primary source datasets from authoratative partners | CBP GIS Team, NPS, Others? | Chesapeake Bay Watershed | Bi-annually (Next dataset Spring 2016)
| 2) Work towards continually tracking and refine/improve tracking process for protected lands data. | CBP GIS Team | Chesapeake Bay Watershed | Ongoing | Tracking: How are healthy watersheds doing? Vulnerability informaiton, prioritization for protection.
3) Overlay data with Healthy Watersheds and other partner conservation goals above to report on progress.
Prioritize protection for healthy waters and watersheds in Maryland | Collaborate with other goal teams to compile information on State and Federal land protection priorities and determine overlap with high-risk healthy watersheds for additional protective measures when appropriate. This complements the Land Conservation Goal. Additional prioritization approaches may consider vulnerability, ecological, and other factors. | MD DNR, MDE, MDP, Habitat Goal Implementation Team | Statewide | 2018-01-01 | Tracking: How are healthy watersheds doing? Vulnerability informaiton, prioritization for protection.
Totals
4. Maintain and expand assessment activities and information
Catalogue monitoring and modeling gaps for 4-5 select CB Agreement Management Strategies, including the Healthy Watersheds Management Strategy. | Work with STAR to to determine current and future monitoring needs by geography, habitat type, and BMP and outline gaps at Workgroup or GIT level. | STAR | Chesapeake Bay Watershed | 2017-12-01 | Coordination of modeling; Complexity of monitoring program
Cross-GIT Tracking | Form a cross-GIT tracking workgroup to work on: healthy watershed metrics, analyses of plans/protocol for determining status of each watershed in succeeding years, assessements of watershed protection priority, and exploring a method to track "marginally" healthy waters and watersheds. | Maintain Healthy Watersheds GIT in collaboration with STAR and other GITs such as Fisheries GIT and Habitat GIT | N/A |  | Tracking: How are healthy watersheds doing? Vulnerability informaiton, prioritization for protection.
Landscape-scale assessments | Working with the Appalachian LCC’s Landscape Conservation Design process and with stakeholders within Pennsylvania, further refine the initial Landscape Conservation Design produced in September 2015. This refinement would include conducting multi‐scale assessments to help further refine the model results by identifying additional model input and to test the information against the ability of land and resource managers to use and incorporate the LCD data into their programs to assist decision-making. | EPA | PA | February 2016 - February 2017 | Federal leadership: provide scientific, technical and policy tools to identify and protect healthy watersheds
Review results of high resolution imagery assesments to determine how to incorporate results for healthy watershed assesmwnt. | Monitor progress of key actions related to high resolution imagery processing and work with LUWG to determine how data can be incorporated into a healthy waters and watershed tracking framework. | Healthy Watersheds GIT Staff, CBP GIS Team, Land Use Workgroup | Chesapeake Bay Watershed |  | Tracking: How are healthy watersheds doing? prioritization for protection, assessment information
Track forest cover | Track forest cover in HUC 8 watersheds (or smaller) and provide regular updates on forest gain/loss. | USFS | Chesapeake Bay Watershed |  | Tracking: How are healthy watersheds doing? prioritization for protection, assessment information
Apply Brook Trout Habitat Assessment tools to identify key high value brook trout habitat to conserve and those areas that are considered marginal and in need of restoration | Conduct GIS assessments of priority catchment to conserve | CBP GIS Team, Habitat GIT | Chesapeake Bay Watershed |  | Tracking: How are healthy watersheds doing? prioritization for protection, assessment information | Habitat/Brook Trout
Identify project opportunities for ecosystem restoration or other USACE mission areas | USACE, NFWF, and state partners will conduct the Chesapeake Bay Comprehensive Water Resources and Restoration Plan to identify project opportunities for ecosystem restoration and other USACE mission areas utilizing healthy watershed inventories, land cover datasets, and other data. | USACE, NFWF, Bay States | Chesapeake Bay Watershed | January 2016 - January 2018 | Federal leadership: provide scientific, technical and policy tools to identify and protect healthy watersheds
Expand assessment activities and information for forests and forest conservation | Produce baseline information on forest cover using new high-resolution data. | FWG, CBP | Chesapeake Bay Watershed | 2017-12-01 | Federal leadership: provide scientific, technical and policy tools to identify and protect healthy watersheds
| Create a new Chesapeake Bay Watershed map of priority forests to conserve for water quality. | FWG, CBP |  |  | Tracking: How are healthy watersheds doing? prioritization for protection, assessment information
| Conduct an analysis of offset requirements from a range of four afforestation scenarios coupled with protecting all large forest patches in areas most vulnerable to development. | USGS, FS, CBP |  |  | Tracking: How are healthy watersheds doing? prioritization for protection, assessment information
Fort Dupont Watershed Restoration NFWF Grant Project | Conduct Environmental Assessment in the Fort Dupont watershed that will include incorporating opportunities to implement low impact development activities in the public right of way, investigate the impact of targeted stream restoration work, and look at the feasibility for wetland restoration. In additon, conduct pre-restoration monitoring to determine baseline conditions. | DC Department of the Environment | Fort Dupont Watershed, Washington, D.C. | 5 year effort | Tracking: How are healthy watersheds doing? Also potential inventory for new healthy watersheds in DC prioritization for protection, assessment information
Monitor Progress in Maryland | Develop a long-term strategy for sustainable monitoring of existing healthy watersheds. | DNR, MDE | Statewide | 2017-01-01 | Federal and State leadership: provide scientific, technical and policy tools to identify and protect healthy watersheds
| Expand stream monitoring in order to identify new healthy watersheds. | DNR, MDE | Statewide | 2018-01-01
| Integrate relevant data into the Bay Program’s new tracking framework. | DNR, MDE | Statewide | ongoing
Maintain and expand assessment activities in PA | Continue to track the Managing Communities metric as a performance measure to evaluate how well municipalities protect their forested watersheds through the use of forest protection ordinances, dedicated staff, and forest management planning. | PA DCNR Bureau of Forestry | Bay-wide | Ongoing | Federal and State leadership: provide scientific, technical and policy tools to identify and protect healthy watersheds
Totals
Management Approach 2: Local Leadership - strengthen local commitment and capacity to protect their healthy watersheds
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Outreach, including: effectively conveying information on the status of healthy watersheds to local stakeholders | Work collectively to improve outreach strategies, and better "get the word out" across multiple Management Strategies to determine the best approaches and methods for reaching key stakeholders | Maintain Healthy Watersheds GIT in coordination with Local Goverment Advisory Committee (LGAC), Local Leadership workgroup, HW GIT and others | Chesapeake Bay Watershed | January 2016 - May 2016 | Local Leadership: Local commitment and capacity to protect healthy watersheds
| Presentations about watershed protection at community events and meetings | DOEE | DC | current -
| Work with schools on watershed restoration education and implementation projects | DOEE | DC | current -
| Partner with NGOs to coordinate protection and communication efforts (This goal is not S.M.A.R.T. yet) | DNR, MDE, MDP | Statewide
| Develop and implement communications to local communities to support integration of healthy watershed protection into local comprehensive plans. | DNR, MDE, MDP | Statewide | 2017-01-01
| Develop and implement outreach to communities to support directing some pollution reduction/mitigation activities (E.g. preservation, riparian buffer initiatives, reforstation, etc.) planned for large-scale TMDL development watersheds that contain healthy (sub)watersheds. | MDE | At least one of the following: Upper Choptank, Upper Chester, Patuxent River Middle, Patuxent River Lower, Gwynns Falls, Lower CHoptank, Marshyhope Creek | 2022-01-01
| Continue to utilize state and national Environmental Education Curriculums such as Watershed Education, PA Land Choices, and Project WET to train teachers (formal and non-formal) and community leaders about clean water, sustainable land use practices, and watershed protection. | PA DCNR | PA | Ongoing
Totals
2. Identify the various tools that may be used, primarily by local governments, to protect healthy watersheds | Gather, summarize and place on the Chesapeake Bay Program website or other locations as determined in the Local Leadership Management Strategy approach for improving transfer of knowledge to locals, existing studies and reports on the costs, benefits and effectiveness of both local and state level land use policy options, incentives and planning tools. | Maintain Healthy Watersheds GIT through Land Use Options and Local Leadership Management Strategies | Chesapeake Bay Watershed and other areas that serve as models | January 2016 - December 2017 | Local Leadership: Local commitment and capacity to protect healthy watersheds
| Finalize and implement guidance to protect healthy watersheds. Explore the necessity for updated antidegradation regulations. | MDE | Statewide | 2018-01-01 | Local Leadership: Local commitment and capacity to protect healthy watersheds
| Include healthy watershed protection in the Watershed Resources Registry, an existing multi-agency restoration and preservation targeting tool. | DNR | Statewide | 2016-01-01 | Local Leadership: Local commitment and capacity to protect healthy watersheds
| Add healthy watershed protection as a factor in growth offset policies. | DNR, MDE, MDP | Statewide | 2017-01-01 | Local Leadership: Local commitment and capacity to protect healthy watersheds
| Support local green space planning and protection by incorporating conservation methods into other planning efforts (ex.- State Planning Board, county comprehensive plans, and local zoning ordinances) | PA DCNR, DEP, State Planning Board, local governments | Bay-wide | Ongoing | Local Leadership: Local commitment and capacity to protect healthy watersheds
| Healthy Watersheds TMDL Pilot Project Forestland Retention Study (Rappahanock River Basin) - Phase 2 | TBD | VA and PA | 2015-2016 | Local Leadership: Local commitment and capacity to protect healthy watersheds
Total
3. Leverage Funding | Use FWS grant programs like North American Wetlands Conservation Act grants, National Coastal Wetlands Conservation grants, and Section 6 Endangered Species Recovery Land Acquisition grants to leverage non-federal funds | FWS | Chesapeake Bay Watershed | FY2016 | Federal and State leadership: provide scientific, technical and policy tools to identify and protect healthy watersheds
| Incorporate healthy watershed protection into the RFPs and scoring tools used to award federal and state water quality grants. | DNR, MDE | Statewide | 2017-01-01
| Work with counties and municipalities to prioritize the use of open space funding under Act 13 to protect healthy watersheds. | PA DCNR | Bay-wide | Ongoing
| Establish Healthy Watersheds Initiative as special funding category in Growing Greener (Environmental Stewardship) funding. Entities may apply for funding of projects directed at curtailing threats to waters designated as Exceptional Value, High Quality, and Class A Wild Trout. | PA DEP | Bay-wide | Ongoing
Totals
Management Approach 3: Federal and State Leadership
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Leverage Funding | Use FWS grant programs like North American Wetlands Conservation Act grants, National Coastal Wetlands Conservation grants, and Section 6 Endangered Species Recovery Land Acquisition grants to leverage non-federal funds | FWS | Chesapeake Bay Watershed | FY2016
| Secure Watershed Protection Grants | DOEE | DC | current -
| Continue to work with NRCS to prioritize Farm Bill program funding to benefit forested watershed lands through programs such as EQIP, CSP, Healthy Forests, and others | PA DEP, DCNR | Bay-wide | Ongoing
Totals
2. Implement new or improve existing policy/programs/research | Reinstitute the Mid-Atlantic Highlands Action Program | FWS, EPA R3 | Blue Ridge, Ridge & Valley, & Appalachian Plateau in VA, WV, MD, & PA | FY2016 | Federal and State leadership: provide scientific, technical and policy tools to identify and protect healthy watersheds
| Continue integrating healthy watershed protection into EPA water programs. Thus far EPA has made progress on integrating protection in the 319 program, 303(d) program and into source water protection. | EPA
| Share information on newly launched Healthy Watersheds Consortium Grant and annual opportunities for states and others to submit proposals for subgrants | EPA HQ
| Engage with federal agencies other than EPA (such as FERC and DOT) to leverage opportunities within those agencies so that they can set the stage for state and local governments to further healthy watershed protection. | Maintain Healthy Watersheds GIT, EPA Chesapeake Bay Program, EPA Region 3, FERC, DOT | Chesapeake Bay Watershed | January 2016 - January 2018
| Continue to manage USACE reservoirs and recreational facilities to protect, preserve, and restore significant ecological resources by managing natural resources in a healthy and sustainable condition, fostering healthy lands and waters by balancing public uses and needs, and providing public outdoor recreational opportunities. | USACE | Chesapeake Bay Watershed | Ongoing
Riversmart Homes Program | Educational and implementation program for homeowners to reduce stormwater runoff and increase tree canopy on private properties. | DC Department of the Environment | Washington, D.C. | current -
Tree Plantings | Increase tree canopy through street tree and other public property plantings. | DDOT Urban Forestry Administration | Washington, D.C. | current -
Public Space LID | Work with DDOT and NPS to maximize LID retrofits in targeted public space areas | DOEE | DC | current -
Open Space Conservation Plan | The Plan addresses open space conservation through the purchase of land, based on four critical priorities; Promoting Outdoor Recreation; Addressing Climate Change; Ensuring Clean Water, Air and Land for a Healthy Public and Vibrant Economy; and Protecting, Using and Conserving Our Natural Resources and Cultural Heritage. | NYSDEC / NYS OPRHP /NYSDAM / NYSDOT / NY Counties / EFC | State Wide | On Going
Dairy Comprehensive Nutrient Management Plan and engineer designs for CNMP related practices Funding Program | Address potential environmental impacts from dairy farms below 300 cows through the development or updating of a Comprehensive Nutrient Management Plan (CNMP). Further address the environmental impacts of small and medium dairies by providing partial funding for certain engineering services related to the development of Best Management Practices (BMPs) | NYSDEC / Cornell University PRO-DAIRY | State Wide | Currently funded through 2018
Implement new or improve existing policy/programs/research in PA | Explore implementation of a statewide Forest Conservation Easement Program to protect healthy watersheds with clean water or safe drinking water funding. | PA DCNR, DEP | Bay-wide | 2016-17
| Establish a PA Riparian Forest Buffer Leadership Team | DCNR and DEP; PA state and local agencies, nonprofits, other stakeholders | Bay-wide | 2016
| Utilize existing Stream ReLeaf program for tracking buffer implementation | DEP and partners | Statewide | 2016-17
| Expand knowledge and access to Stream ReLeaf system in order to capture all existing buffers | DEP and partners | Statewide | 2016-17
Totals
Management Approach 4: Support State-based efforts
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Provide a valued forum for mutual learning and exploration | Continue meeting 2-4 times a year and at meetings continue hosting Case Study presentations related to healthy watershed protection/tracking | Maintain Healthy Watersheds GIT | N/A | Jan 2016 - Dec 2017 | Local leadership / Supporting State based efforts
| Provide leadership as GIT Chair, Vice-Chair, Coordinator and Staff | TNC, MDP, USGS and CRC (respectively) | N/A
| Host Youth Fair for Environmental Education | DOEE, DCPS, DCPCS, Non-profits | Anacostia Park | 2016-05-01
| Continue to participate in the Bay Programs's GIT4. | MDE, MDP, DNR | Statewide | 2018-07-01
| Hold a PA Riparian Forest Buffer Summit including all interested PA Bay stakeholders, led by the Riparian Forest Buffer leadership team | DCNR and DEP | Bay-wide | 2016
Total
2. Develop information resources and support communications | Provide messages and resources to CBP Communications staff | Maintain Healthy Watersheds GIT |  |  | Local leadership / Supporting State based efforts
| Share presentations, slides, pictures, graphics, to help partner agency staff prepare presentations, reports, etc. with effective healthy watersheds messages | Maintain Healthy Watersheds GIT
| RiverSmart Homes Flyer Distribution | DOEE | DC | current -
| Increase communication so that federal programs and agencies are more protective of state-identified healthy watersheds. | MDE, DNR, MDP | Statewide
| Develop public outreach strategy that considers landowners' interests and values and encourages participation | DCNR and DEP | Statewide | 2017
Total
3. Promote the science | Continue o work with the Chesapeake Bay Program and partners to quantify and incorporate conservation practices into the Chesapeake watershed modeling efforts and to explore how land use protections might be used to quantify future pollutant load reduction incentives for land conservation. | Maintain Healthy Watersheds GIT and Protected Lands group |  |  | Federal and State Leadership, local leadership and supporting state based efforts
Total
Work collaboratively with Bay Program partners to identify legislative, budgetary and policy needs to advance the goals of the Chesapeake Bay Agreement. We will, in turn, pursue action within our member state General Assemblies and the United States Congress. (Per CBC Resolution #14-1) | Work with GIT to consider policy changes or legislative actions identified by the GIT. | CBC | PA, MD, VA | Ongoing | Political climate and budgets
Total
**Note: As a member of the Chesapeake Executive Council and a signatory to the Chesapeake Bay Watershed Agreement, the Chesapeake Bay Commission (CBC) functions as the legislative arm of the Chesapeake Bay Program working within Maryland, Pennsylvania and Virginia and at the federal level to identify specific Bay management concerns requiring intergovernmental coordination and cooperation. CBC makes recommendations to the federal, state and local governments on legislative and administrative actions necessary to effectuate coordinated and cooperative management for the Bay watershed. The Commission will work collaboratively with Bay Program partners to identify legislative, budgetary and policy needs to advance the key actions identified in this outcome and to anticipate those needed in the future. The CBC’s work is supported by the annual appropriations of its three member states totaling $675,000 and is, on occasion, supplemented by project-specific grants.
Acronym Guide
AACC – Anne Arundel Community College
ACFHP - Atlantic Coast Fish Habitat Partnership
ACJV – Atlantic Coast Joint Venture
AgNPS – AGricultural Non-Point Source Pollution Model
Appalachian LCC - Appalachian Landscape Conservation Cooperative
ASTSWMO – Association of State and Territorial Solid Waste Management Officials
BayFAST/CAST/MAST/VAST – Federal Assessment Scenario Tool/Chesapeake AST/Maryland AST/Virginia AST
BDJV – Black Duck Joint Venture
BKT – Brook trout
BMP – Best Management Practice
CAC – CBP Citizens’ Advisory Committee
CAFO – Concentrated Animal Feeding Operation
CB – Chesapeake Bay
CBC – Chesapeake Bay Commission
CBF – Chesapeake Bay Foundation
CBIBS – Chesapeake Bay Interpretive Buoy System
CBIG – Chesapeake Bay Implementation Grants
CBP – Chesapeake Bay Program
CBPO – Chesapeake Bay Program Office
CBRAP – Chesapeake Bay Regulatory and Accountability Program grants
CBSAC – Chesapeake Bay Stock Assessment Committee
CBSSC – Chesapeake Bay Sentinel Site Cooperative
CBT – Chesapeake Bay Trust
CCWC – Choose Clean Water Coalition
CEAP – Conservation Effects Assessment Project
Chessie BIBI – Chesapeake Bay Basin-wide Index of Biotic Integrity
CNMP – Comprehensive Nutrient Management Plan
CNU – Christopher Newport University
CRC – Chesapeake Research Consortium
CREP – Conservation Reserve Enhancement Program
CSN – Chesapeake Stormwater Network
CWA – Clean Water Act
DAT – CBP Diversity Action Team
DC – District of Columbia
DCNR – Pennsylvania Department of Conservation and Natural Resources
DE – Delaware
DEP – Department of Environment
DE DNREC – Delaware Department of Natural Resources and Environmental Control
DNR –Department of Natural Resources
DoD – Department of Defense
DOEE – Dist. Of Columbia Department of Energy and Environment
DOF – Department of Forestry
DOT – Department of Transportation
DST – Decision support tool
DU – Ducks Unlimited
EC – Chesapeake Executive Council
EJ SCREEN – Environmental Justice Screening and Mapping Tool
EO Strategy – Executive Order 13508 Strategy for Protecting and Restoring the Chesapeake Bay Watershed
EJ – Environmental Justice
EL – Environmental Learning
ELCSS – Environmental Literacy Challenge for Systemic Sustainability
ERP – Elizabeth River Partnership
EPA – Environmental Protection Agency
Ex Comm - Executive Committee of the Sustainable Fisheries GIT
FERC – Federal Energy Regulatory Commission
FOD – Chesapeake Bay Program Federal Office Directors
FTE – full time employee
FWG – Forest Work Group
FWS – Fish and Wildlife Service
GIS – Geographic Information System
GIT – CBP Goal Implementation Teams
GMU – George Mason University
GSA – General Services Administration
HBCUs – historically black colleges and universities
HSCD – EPA Hazardous Site Cleanup Division
HWGIT – Healthy Watershed Work Group
ICPRB – Interstate Commission on the Potomac River Basin
IPC – Interfaith Partners for the Chesapeake
LCC – Landscape Conservation Cooperatives
LGAC – CBP Local Government Advisory Committee
LL – Local Leadership
LU – Land Use
LUWG – Land Use Work Group
MATOS - Mid-Atlantic Telemetry Observing System
MB – CBP’s Management Board
MD - Maryland
MDE – Maryland Department of Environment
MDSG – Maryland Sea Grant
MOU – Memorandum of Understanding
MSP – Math Science Partnership
MS4 – Municipal Separate Storm Sewer System
MWCOG – Metropolitan Washington Council on Governments
MWEEs – Meaningful Watershed Educational Experiences
MWS – Master Watershed Stewards
NAAQS – National Ambient Air Quality Standards
NALCC - North Atlantic Landscape Conservation Cooperative
NATA – National Air Toxics Assessment
NCBO – NOAA Chesapeake Bay Office
NGO – Non-government organization
NEIEN – National Environmental Information Exchange Network
NERR – Chesapeake Bay National Estuarine Research Reserve
NFWF – National Fish and Wildlife Foundation
NOAA – National Oceanic and Atmospheric Administration
NP – National Parks
NPDES – National Pollutant Discharge Elimination System
NRCS – Natural Resources Conservation Service
NPS – National Park Service
NYS DEC – New York State Department of Environmental Control
ODU – Old Dominion University
ORES – Oyster Reef Ecosystem Services
ORP – Oyster Recovery Partnership
OSSE – Office of the State Superintendent of Education
PA – Pennsylvania
PA DEP – Pennsylvania Department of Environmental Protection
PCB – polychlorinated biphenyl
PMP -- Pollution Minimization Plan
PRFC – Potomac River Fisheries Commission
PSC – CBP’s Principles' Staff Committee
QA – quality assurance
RFB – Riparian Forest Buffer
RMNs - Regional Monitoring Networks
SAV – Submerged Aquatic Vegetation
SERC - Smithsonian Environmental Research Center
SHWG – Stream Health Work Group
SRBC -- Susquehanna River Basin Commission
STAC – CBP Scientific and Technical Advisory Committee
STAR – CBP Scientific and Technical Assessment Research team
TCW – Toxics Contaminants Workgroup
TEA - Tidewater Ecosystem Assessment Division of MD DNR
TMDL – Total Maximum Daily Load
TNC – The Nature Conservancy
TSCA – Toxic Substance Control Act
UMBC – University of Maryland Baltimore County
UMCES – University of Maryland Center for Environmental Science
UMCES-CBL – University of Maryland Center for Environmental Science-Chesapeake Biological Lab
UMD – University of Maryland
USACE – U.S. Army Corps of Engineers
USDA – U.S. Department of Agriculture
USFWS – U.S. Fish and Wildlife Service
USFS – U.S. Forest Service
USGS – U.S. Geological Survey
UVA – University of Virginia
VA – Virginia
VCU – Virginia Commonwealth University
VA CZM – Virginia Coastal Zone Management
VBOE – Virginia Board of Education
VDGIF – Virginia Department of Game and Inland Fisheries
VIMS – Virginia Institute of Marine Science
Virginia DEQ – Virginia Department of Environmental Quality
VMRC – Virginia Marine Resources Commission
WG – work group
WIP – Watershed Implementation Plan
WQN - Water Quality Network