## Water Quality Workplan
Outcome: 2017 WIP, 2025 WIP and Water Quality Standards Attainment and Monitoring Outcomes
Goal: Water Quality
Outcome: 2017 WIP, 2025 WIP and Water Quality Standards Attainment and Monitoring
Long term Target: 100% by 2025
2 year Target: 60% by 2017
Management Approach 1: Phase I WIPs, Phase II WIPs, and Two-year Milestones
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. BMP Verification
Totals
2. Provide support for continued BMP implementation, tracking and reporting on agricultural lands
Totals
3. Provide support for continued BMP implementation, tracking and reporting in the urban stormwater sector
Totals
4. Guide development of jurisdictions’ trading and offset programs
Totals
5. Continue with Wastewater Treatment Plant & Septic upgrades and enhancements
Totals
5. Provide permit and enforcement oversight across all sectors
Totals
Management Approach 2: Enhancing Monitoring
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Continue work to improve temporal and regional patterns in water quality criteria attainment in tidal and non-tidal waters. | Summarize patterns in water-quality criteria attainment over time in tidal waters from 1985-2014 | CBP Monitoring Team; UMCES | Tidal water areas of the Chesapeake Bay Watershed | June, 2016
| Provide an update describing temporal and regional patterns in water quality standards attainment of dissolved oxygen, water clarity/SAV and chlorophyll. | CBP Monitoring Team; UMCES | Chesapeake Bay Watershed and jurisdictions | December, 2016
| Publish a new Ambient Water Quality Criteria Technical Addendum that provides updated guidance on water quality standards attainment assessment methods for the tidal bay jurisdictions | CBP Monitoring Team; USGS | Tidal water areas of the Chesapeake Bay Watershed jurisdictions | December, 2016
| Implement new process for quantifying trends in tidal water-quality parameters. The new process incorporates advances in methods to provide more information on trends in water-quality patterns over time. | UMCES/EPA, MD DNR, VADEQ | Tidal water areas of the Chesapeake Bay Watershed | Annually in 2016/2017
Total
2. Conduct Lower Susquehanna River Integrated Sediment and Nutrient Monitoring Program | Water quality results attained from 2 of the 6 high flow events assessed in April 2015 will be submitted to the CBP to be included in the 2017 CB Mid Point Assessment | MD DNR, UMCES, USGS, with Exelon | Lower Susquehanna River, Conowingo Dam | 2017
| Monitor any high flow event of greater than 100,000 cfs at Conowingo Dam occurring before May 30, 2016 |  |  | On/before May 30, 2016
| Develop alternative monitoring plans to gather sufficient information to inform Conowingo impacts on Bay water quality standards now that it has reached "dynamic equilibrium" in the event than less that 6 high flow events occur before May 30, 2016 |  |  | On/before May 30, 2016
Total
3. Coordinate the CBP non-tidal water-quality network | The partners in the network will collect nutrient and sediment samples from over 125 sites throughout the watershed. | USGS, EPA, MD DNR, VA DEQ, DEREC, WV DNR, PA, DC, DC, NY, SRBC | Non-tidal water areas of the Chesapeake Bay watershed | 2016-2017
| The USGS will work with the partners to compile quality assure the information to update loads and trends. | USGS, EPA, MD DNR, VA DEQ, DEREC, WV DNR, PA, DC, DC, NY, SRBC |  | 2016-2017
| USGS will completely update the reporting of loads to the Bay and trends of nutrients and sediment loads in the watershed; revised products will be prepared to communicate these results. | USGS |  | 2016
Total
4. Addressing gaps in monitoring programs | Expand upon the water quality-focused Building Environmental Intelligence report to a new process to address additional monitoring needs associated with the 2014 Chesapeake Bay Agreement. Integrate the role of Citizen Science to address gaps in water quality-related monitoring and assessment needs. Work with partners and Management Board to consider and attempt to implement recommendations. | CBP Monitoring Team | Chesapeake Bay Watershed and jurisdictions | 2016-2017
| Coordinate and integrate Citizens Monitoring effort funded by the Chesapeake Bay Program. Develop high quality citizens monitoring programs to assess water quality standards. Target areas where implementation will potentially show progress. | CBP monitoring team, Alliance for the Chesapeake Bay (ACB), Isaac Walton League | Chesapeake Bay Watershed and jurisdictions
| Develop strategy to target shallow water monitoring program with limited resources. Incorporate all spatially and temporally intensive monitoring results into Bay water quality standards attainment. | MD DNR, CBP monitoring team | Shallow water areas of the Chesapeake Bay Watershed
Total
Management Approach 3: Bay TMDL Midpoint Assessment
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Develop and apply new approaches for quantifying and explaining water-quality trends in tidal waters. | Test watershed factors influencing water-quality trends in tidal waters. | CBP monitoring team, UMCES, USGS and other academic partners | Tidal water areas of the Chesapeake Bay Watershed | 2016-2017
Total
2. Explain the drivers of water-quality trends in the watershed. | Release of a report and communication products regarding nitrogen sources and transport processes in smaller agricultural and urban watersheds. | USGS, JHU, CBP modeling team | Agricultural and urban watersheds in the Chesapeake Bay Watershed | 2016-2017
| Compare observed and expected trends in the watershed and relation to management actions. |  | Chesapeake Bay Watershed and jurisdictions
| Improve knowledge of sediment and nitrogen sources and residence times. |  | Chesapeake Bay Watershed and jurisdictions
| Improve knowledge of the water-quality functions of created and restored nontidal wetlands. |  | Created and restored non-tidal wetlands in the Chesapeake Bay Watershed
| Support efforts to improve the understanding of tidal water response to changes in watershed loads. |  | Chesapeake Bay Watershed
Total
3. Provide information to enhance the CBP watershed models. Results of these studies will be used to prepare and calibrate the Phase 6 model in 2016. (USGS, working with CBP modeling team) | Develop a new land-cover data set for the CBP watershed model. | USGS | Chesapeake Bay Watershed and jurisdictions | 2016
| Enhance the CBP watershed model using USGS measured loads for calibration as well as SPARROW model, groundwater models and other science findings. |  | Chesapeake Bay Watershed and jurisdictions
| Examine the impact of Susquehanna reservoirs on changes in nutrient and sediment transport to Chesapeake Bay. |  | Susquehanna reservoirs and Chesapeake Bay Watershed and jurisdictions
| Better utilize monitoring data to assess progress and explain observed changes in nutrients and sediment in response to management practices. |  | Chesapeake Bay Watershed and jurisdictions
Total
4. Release beta and final version of the Phase 6 Watershed Model | Incorporate data inputs, such as BMP efficiencies and land use/land cover | Modeling Workgroup, WQGIT, WQGIT Workgroups | n/a | Oct. 2015 - October 2016 | n/a - staff |  | Improved Technical Information; Response of Water Quality Conditions to Management Practices
| Conduct STAC peer reviews | STAC, Modeling Workgroup | n/a | Winter/Spring 2016 | n/a - staff
| Run key scenarios and refine modeling tools as appropriate | Modeling Workgroup, Bay jurisdictions, CBPO Modeling Team | n/a | January 2016 - September 2016 | n/a - staff
1. xyz…
5. Develop Phase III WIP Expectations | Release Phase III WIP Stakeholder Assessment | Institute of Environmental Negotiation; WQGIT; Bay Jurisdictions | n/a | December 2015 / January 2016 | $100,000 (assessment) | $100,000 (assessment) | Implementation of Practices; Technical Information; Response of Water Quality Conditions to Management Practices
Develop Phase III WIP Action Plan
| Provide Phase III WIP Expectations | EPA; PSC; MB; WQGIT; WQGIT Workgroups; Bay Jurisdictions | n/a | Jun. 2017 | n/a - staff | n/a
Total
6. Collection of Local Land Use Data | Outreach to local Bay jurisdictions | Land Use Workgroup | n/a | 2013 - 2016 | n/a - staff | n/a | Improved Technical Information
| Establish contract with Chesapeake Conservancy | Chesapeake Conservancy; PSC | n/a | Fall 2015 - Spring 2016 | ~$1,000,000 | ~$1,000,000
| Rolling partnership review of land use data | Bay state and local jurisdictions; Land Use Workgroup | n/a | August 2015 - July 2016 | n/a - staff | n/a
| Improving National Wetlands Inventory Data | FWS; PADEP | n/a (although priority for PA) | November 2015 - May 2016 | TBD | TBD
| Incorporation of data into Phase 6 modeling tools | Land Use Workgroup; Modeling Workgroup | n/a | May 2015 - September 2016 | n/a - staff | n/a
| Total |  |  |  |  | ~$1,000,000
**Note: As a member of the Chesapeake Executive Council and a signatory to the Chesapeake Bay Watershed Agreement, the Chesapeake Bay Commission (CBC) functions as the legislative arm of the Chesapeake Bay Program working within Maryland, Pennsylvania and Virginia and at the federal level to identify specific Bay management concerns requiring intergovernmental coordination and cooperation. CBC makes recommendations to the federal, state and local governments on legislative and administrative actions necessary to effectuate coordinated and cooperative management for the Bay watershed. The Commission will work collaboratively with Bay Program partners to identify legislative, budgetary and policy needs to advance the key actions identified in this outcome and to anticipate those needed in the future. The CBC’s work is supported by the annual appropriations of its three member states totaling $675,000 and is, on occasion, supplemented by project-specific grants.