| Current Schedule w/30 Day Simultaneous MB/Public Input Period |  |
| --- | --- |
| June 2015 | - 30 - Final MSs completed |
| July | - TBD EC Meeting |
| August | - 13 MB call |
| September | - 17 MB meeting |
| October | - 1 - GITs: Draft workplans due - Oct 5 – Nov. 5: 30-day public input period (simultaneous w/MB review) - 15 – MB call |
| November | - 5 – Close public input - 5 – Nov 30 GITS – three week to review, summarize MB/public input, make edits to drafts - 12 – MB - All-day Special Session - 30– GITs send revised workplans to MB (in prep of Dec. 10 mtg.) |
| December | - 10 - MB meeting - review public comments, discuss hot issues and final workplans - Dec 10—Jan 7 - MB-4 wk review of revised drafts. |
| January 2016 | - 7 – MB send comments to GITs - 14- MB meeting – fatal flaw discussion - (15 - Two-yr. WIP milestones due) - 14-21 fatal flaw review/resolve any outstanding issues - 21 – 28 Formatting 30 - Workplans final, post on web |