## (Goal Name) Workplan
Outcome:
Goal: Restore, enhance and protect a network of land and water habitats to support fish and wildlife, and to afford other public benefits, including water quality, recreational uses and scenic value across the watershed.
Outcome: By 2025, restore historical fish migratory routes by opening 1,000 additional stream miles, with restoration success indicated by the presence of Alewife, Blueback Herring, American Shad, Hickory Shad, American Eel and/or Brook Trout. The Fish Passage Workgroup is dedicated to restoring connectivity to creek, stream and river habitats for migratory fish through dam removal and fish passage projects. While the Fish Passage workgroup is primarily focused on blockage removals that benefit diadromous species, the group acknowledges the benefits of dam removal to resident species. As such, Brook Trout was added to the Fish Passage strategy target species list.
Long term Target: open an additional 1000 miles by 2025
2 year Target: open 132 miles by 2018
Management Approach 1: During the period 2011-2025, restore historical fish migratory routes by opening 1,000 additional stream miles, with restoration success indicated by the presence of Alewife, Blueback Herring, American Shad, Hickory Shad, American Eel and/or Brook Trout.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Continue dam removal activities in the Chesapeake Bay | Remove Bloede Dam | MD DNR, NOAA, USFWS, American Rivers | Ilchester, MD | 2017-12-01 | 9500000 | NOAA, USFWS (through DOI and NFWF) | Lack of incentives for dam owners; the ability to achieve change through fish passage projects is largely limited by a lack of resources
| Various dam removal planning, design and implementation projects - many project are in a feasibility study phase where there are no immediate milestones during 2016-2017 | Fish Passage Workgroup | Varies | Varies | Variable | Variable
2. Project Development via Incentive Programs | MD DNR will pursue a dam removal incentive program to provide tax incentives to private owners who allow dam removal. | MD DNR | State of Maryland | 2017-12-01 | Variable ($25,000-$150,000 range TBD) | State of Maryland | Requires state legislation and funding to be allocated for this purpose
3. Coordinate dam removal activites with the state Dam Safety Programs | Establish or continue relationships with state dam safety programs | Fish Passage Workgroup | Entire Chesapeake Bay Region | 2017-12-01 | no cost | States of Maryland, Virginia and Pennsylvania
Totals
Management Approach 2: Document return of fish to opened stream reaches by establishing the presence or absence of target species at a select number of projects within the Chesapeake Bay watershed.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Monitor NOAA funded dam removal projects for the presence/absence of target fish species (Tier I monitoring) | All NOAA funded dam removals will be monitored | NOAA, funding recipients | At dam removal sites | Ongoing | variable | NOAA | Presence/Absence monitoring is required for all NOAA funded projects
Total
2. Conduct Tier II monitoring on select dam removals (Currently, the Patapsco River monitoring is the only river designated as a Tier II site by NOAA). | Conduct Tier II monitoring on the Patapsco River | NOAA, American Rivers, MD DNR, UMBC, USGS, USFWS | Patapsco River near Ellicott City, MD | Ongoing | 1000000 | NOAA, USFWS | NOAA will fund this activity as a project task for each removal
3. Conduct target species monitoring of select dam removals in VA (+/- and relative abundance) | Boat electrofishing upstream of Harvell Dam removal on the Appomattox River | VDGIF | Appomattox River in Petersburg, VA | Ongoing | variable | VDGIF (SWG) | Dependent on continued availabiity of funding for fish passage technician crew
| Boat electrofishing upstream of Embrey Dam removal on the Rappahannock River | VDGIF | Rappahannock River near Fredericksburg, VA | Ongoing | variable | VDGIF (SWG)
4. Conduct target species counts at technical fishways in VA | Continue Annual American Shad count at Boshers Vertical Slot Fishway | VDGIF | Boshers Dam in Henrico County on James River near Richmond, VA | Ongoing | variable | VDGIF (SWG)
5. Conduct target species monitoring (+/- and relative abundance) at road culverts in VA | Continue annual backpack electrofishing at Claiborne Run nature-like fishway (herring) | VDGIF | Rappahannock tributary: Claiborne Run in Stafford County, VA | Four more of five consecutive years | variable | VDGIF (SWG)
| Continue annual backpack electrofishing at White Oak Run pool and weir fishway (herring) | VDGIF | Rappahannock tributary: White Oak Run in Stafford County, VA | Ongoing | variable | VDGIF (SWG)
6. Juvenile Alosine surveys in VA | Determine origin (hatchery vs wild) of American Shad juveniles on the James River | VDGIF | Upstream and downstream of Boshers Dam on the James River | Ongoing (as long as stocking continues) | variable | VDGIF (SWG) | Dependent on continued funding for stocking American Shad fry in the upper James (and for technician crew)
3. Continue eDNA research on river herring presence and absence |  | SERC
Total
Management Approach 3: Use the Chesapeake Bay Fish Passage Tool that was completed by the workgroup to implement high priority dam removal and fish passage projects.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Continue using the Chesapeake Bay Fish Passage Tool to implement high priority dam removal and fish passage projects. | In addition to the high priority dam removal projects already identified by the Chesapeake Fish Passage Tool, the workgroup will also identify high priority watersheds in PA, VA and MD to focus fish passage efforts. | Fish Passage Work Group | Entire Chesapeake Bay region | 2016-02-01 | 0 | 0 | The ability to achieve change through fish passage projects is largely limited by a lack of resources.
| Conduct culvert and bridge assessments in high priority subwatersheds to determine extent of fish blockages due to road and rail infrastructure. Add information to the Chesapeake Fish Passage Tool. | USFWS, NOAA, Maryland, Virginia and Pennsylvania, American Rivers | Entire Chesapeake Bay region | 2017-12-01 | 120000 | CBT, CBP, NFWF
| Work with the Bay Program to formally accept the new method for the miles openend metric to the "upstream functional network" definition | Fish Passage Work Group | Entire Chesapeake Bay region | 2015-12-17 | no cost
Total