## CBP Goal Implementation Team

## Enhanced Partnering, Leadership, and Management

## Meeting Agenda

Date: February 3, 2015

Time:  1:00pm – 3:00pm

Location: Conference Call, Room 303 at CBPO

Call-in:  866-299-3188

Code: 410-267-5731

Adobe Connect Link: https://epa.connectsolutions.com/git6/

| Members In Attendance: Greg Allen, EPA; Matt Fleming, MD DNR; Tim Roberts, EPA. Greg Barranco, EPA; Mike Foreman, VA DCR, Chair; John Schneider, DE DNREC. Russ Baxter, VA SNR; Mary Gattis, ACB (LGAC Liaison); Ben Sears, NY DEC. Carin Bisland, EPA, vice-Chair; Kirk Havens, VIMS (STAC Liaison); Doreen Vetter, EPA. Jessica Blackburn, ACB (CAC Liaison); Carl Hershner, VIMS; Samantha Watterson, CRC. Bevin Buchheister, CBC; Jackie Lendrum, NY DEC; Kristen Wolf, PA DEP. Diane Davis, DC DOE; Mike Mason, EPA; Andy Zemba, PA DEP. Kevin Debell, EPA; Reggie Parrish, EPA. Sarah Diebel, DOD; Jennifer Pauer, WV DEP. |  |  |
| --- | --- | --- |
| Agenda Item, Discussion Lead and Desired Outcome | # Time | # Background Docs, Notes, and Action Items |
| Introductions (Discussion Lead: Mike Foreman) | 1:00-1:05 | Summary of Action Items from January Meeting: - Complete: A doodle poll will be sent to Governance Document action team volunteers to set the first meeting date. - Complete: GIT members are asked to review the management approach section and prioritize the 7 management actions, linking them to prioritized factors influencing. Provide feedback to Reggie by January 13. - Complete: Anyone interested in being a part of the workgroup to finalize the MS by drafting, reviewing, or tracking the progress should contact Reggie by January 13. - Complete: Any other comments/feedback on the current draft MS can be sent to Reggie ASAP so that it can be incorporated for discussion at MB retreat on January 15-16. - Complete: The Evaluator Function Workgroup will be scheduling a meeting to reconsider their path forward based on the bill. Anyone interested in joining can contact Greg Allen. |
| Management Strategy Development Updates (Discussion Lead: Mike Foreman) - CBP Management Strategy release timeline. - Communications Workgroup binning exercise on 2/5 from 9:45am - 11am. - Requests for TetraTech support are due by 2/6/15. | 1:05-1:20 | - Management Strategy Timeline for Public Release - 2015 01 22 Management Strategy Support Request |
| Local Leadership Management Strategy Updates (Discussion Lead: Reggie Parrish) - Status update on planned steps for completing the management strategy. - Update on GIT Funding project award. | 1:20-1:50 | - Current draft Local Leadership Management Strategy |
| Independent Evaluator Function Update (Discussion Lead: Greg Allen) - Updates on progress made in reacting to the Chesapeake Bay Accountability and Recovery Act. | 1:50-2:05 | - https://www.congress.gov/bill/113th-congress/senate-bill/1000 |
| Governance Document Action Team Updates (Discussion Lead: Greg Allen) - Updates on progress made in developing options for the Governance Document revisions. | 2:05-2:20 |  |
| Planning for CBP Annual Performance Review (Discussion lead: Greg Allen) - Per Management Board charge, GIT6 will facilitate the planning of this annual meeting. - Discussion of logistics and objectives of the meeting. | 2:20-2:50 |  |
| Action Items, Wrap-up, Next Meeting (Discussion Lead: Mike Foreman) | 2:50-3:00 | - Next Meeting: Tuesday, March 3. |