## Original 2017
GIT | GIT Needs from STAR | Timeline | Completed Y/N | Urgency/Comments | STAR workgroup
Climate Resiliency | 4 workgroups for Climate monitoring | 2017-12-01 | Y
| Outline Gaps for Climate Monitoring | 2017-12-01 | Y
| Explore Citizen monitoring for climate | TBD | Y
| ID Costs for climate monitoring gaps | 2017-12-01 | Y
| ID agencies for monitoring gaps | 2017-12-01 | Y
| ID overlap in monitoring and modeling efforts | 2017-12-01 | Y
| Assess multi-scale climate assessments | 2017-12-01 | Y
| synthesize research on sea level, precip, temp trends | 2017-12-01 | Y
| Assess climate change influence on flow, temp, WQ in streams | 2016-2017 | Y
| Develop climate indicators | 2017-12-01 | Y
| Ocean Acidification |  | Y
| Protocol support and development of indicators | Ongoing
| Impacts of SLR, coastal storms, increased temperatures and extreme events on BMPS (maintenance, shelf life, etc) | Ongoing
Sustainable Fisheries | ID healthy habitat criteria | 2017-06-01 | ongoing | Fish habitat workshop April 2018
| ID spatial tools and datasets to map ranges and stressors | 2017-06-01 | ongoing | Fish habitat workshop 2018
| Convert fish and habitat survey data to spatial datasets | 2017-12-01 | ongoing | Fish habitat workshop April 2018
| Explore options for monitoring programs to cover range of species | Early-Mid 2016 | Ongoing | citizen science pilot for forage in 4 tribs; need support to continue
| Determine feasibility of phytoplankton and zooplankton monitoring | Mid 2016 | N | need clear assessment of utility from sci and managers
| Develop shallow water monitoring survey proposal for gaps | Mid 2016 | Ongoing | citizen science pilot for forage in 4 tribs; need support to continue
| Forage fish indicator |  | ongoing | projects completed; part of new wrkpln
| Pair WQ data with living resources data |  | N | might be part of fish habtiat workshop
| Improved fish habitat maps |  | ongoing | Fish habitat workshop April 2018
| Oyster indicator development |  | Y
| Shoreline indicator development |  | ongoing | GIT funded project for 2018
| Updating blue crab stock assessment |  | Y | CBSAC/DNR making some upodates but still determining need for benchmark assessment
| Oyster monitoring |  | ongoing | GIT funded project for 2018
Habitat | Wetland: Expand USC wetland mapping model | 2017 | No | Check with Melissa Yearick
| Wetland: Wetland Acres reporting to NEIEN | Ongoing | In Progress | Check with Jeff Sweeney; Most Urgent | Status and Trends
| Wetland: QA/QC of wetland data | Ongoing | No | On hold pending WWG leadership change
| Stream Health: Input for indicator development beyond Chessie BIBI | 2020 | No | Most Urgent | Status and Trends | info coming out of workshop
| Stream Health: support for reporting progress for Chessie BIBI | ongoing | No | Most Urgent | Status and Trends and Monitoring | funding needed f
| Stream Health: interaction with Healthy Watershed GIT tracking current status of streams | 2020 | No |  | Status and Trends and Monitoring | Addressed by Renee's project
| Brook Trout: funding for brook trout monitoring | Ongoing | No | Urgent | Monitoring
| Brook Trout: New Indicator (3-5 year occupancy census) | Ongoing | Yes, indicator chosen; EBTJV 5-year occupancy census. Might need assistance preparing #s. | Most Urgent | Status and Trends and Monitoring | Shorterm assessment; followup with Brook Trout Team | Laura and Paige
| Black Duck: Development of habitat-based indicator | 2019 | Needs more discussion. | Most Urgent | Indicators WG | SRS review
| Stream Health: The relations between implementing practices to reduce nutrient and sediment and improving stream health conditions. | 2018-19 | Ongoing | Urgent | work with epa phase 3 workteam under WQGIT and Emily T. | cobenefit; stream health protocol developed by Army Corps Engineer
| Stream Health/Fish Habitat: Relation between stream habitat, water temperature to brook trout and other important recreational species (such as small mouth and largemouth bass). | 2020 |  | Urgent | modeling and monitoring
| Brook Trout: Expand spatial-temporal groundwater model to rest of Chesapeake Bay Watershed to predict groundwater influence in headwater streams. | 2018-19, High Priority | No | Most Urgent | modeling and monitoring
| Stream Health/Fish Habitat?: The effect of toxic contaminants, bacteria, and parasites on freshwater fish populations and implications for human consumption. | 2020 |  | Urgent | WQ GIT / Toxics
| Stream Health: Relation of streambank stability and erosion rates and impacts on sediment loads and fish habitats | 2020 |  | Medium | work with epa phase 3 workteam under WQGIT and Emily T.
| SAV: Climate variability and SAV habitat availability (using 1 meter resolution land cover) | 2019-20 |  | Medium | modeling and land use wg | work with rich support of staff
Water Quality | WQ Criteria Attainment patterns summary | June, 2016
| Update in patterns in WQ standards attainment DO, clarity/SAV and chlorophyll | December, 2016
| Publish WQ Criteria Tech Addendum | December, 2016
| Implement new process to quantify trends in tidal WQ parameters | Annually in 2016/2017
| WQ results attained from 2 of 6 high flow events for mid point assessment | 2017
| Monitor high flow events at Conowingo | On/before May 30, 2016
| Conowingo impacts on WQ monitoring plans | On/before May 30, 2016
| 125 sites of nutrient and sediment samples | 2016-2017
| Update loads and Trends USGS | 2016-2017
| USGS to update reporting/communicating of loads to Bay | 2016
| expand on BEI report for add'l monitoring needs | 2016-2017
Incorporate Citizen Science Monitoring for WQ standards
develop targeted shallow water monitoring strategy
| Test watershed factors influencing WQ trends in tidal waters | 2016-2017
| Release report/communication of nitrogen sources | 2016-2017
Compare observed and expected trends in watershed
Improve knowledge of sed and N sources
Use WQ data to assess PA's progress
WQ functions of wetlands
Improve understanding of tidal water response to load changes
| Develop land cover dataset | 2016
Enhance watershed and SPARROW model
Examine Susquehanna reservoirs' impact on N and sed transport
Assess N and sed response to management practices
| Incorporate BMP efficiencies and land cover/use | Oct. 2015 - October 2016
| Conduct STAC peer reviews | Winter/Spring 2016
| Run scenarios and modeling tools | January 2016 - September 2016
Healthy Watersheds | Work with STAR team to identify and incorporate key datasets related to watershed health and vulnerability indicators for incorporation into the Tetra Tech PHWA GIT funding project. | 2018 - 2019 | in progress |  | Laura Free and indicators workgroup
| Post TT PHWA GIT funding project work with HW GIT staff to assess results and begin to determine appropriate tracking framework for potential HW sustainability indicator. | 2019 and behond | N |  | Indicators workgroup
| Compile and publish bi - annual CBP Protected Lands dataset: STAR can help to communicate the completion and availablility of the dataset as well as help to coordinate additional analysis to meet the needs of CBP teams. | Spring 2018 | in progress
| Determine a way to identify and track "mariginally healthy" waters and watersheds. Shared data gap with Stream Health workgroup |  | N
Stewardship | Public access sites and potential effects from climate change (sea-level rise and flooding)
Use results from stewardship index to help model relations of human attitudes/behaviors toward consumption, restoration and conservation.
Diversity Indicator Target/Goal for 2025 using American Community Survey Data (Overlaying state Demographic and Economic census block data over Chesapeake Bay Watershed)
Note on B2: CRCStaffers: Work with 4-select Workgroups to determine current and future monitoring needs by geography, habitat type, and BMP and outline gaps at Wokrgroup or GIT level.
Note on B3: CRCStaffers: Outline gaps for watershed scale monitoring effort, including gaps related to monitoring of non-climate stressors that could exacerbate climate impacts to Chesapeake Bay habitat or BMPs.
Note on B4: CRCStaffers: Explore the use of citizen-based monitoring networks.
Note on B5: CRCStaffers: Identify costs associated with closing monitoring gaps.
Note on B6: CRCStaffers: Identify agencies/organizations through which commitments could be sought to fund or participate in filling monitoring gaps.
Note on B7: CRCStaffers: Identify geographical overlap in monitoring and modeling efforts to explore opportunities for cost saving efficiencies and integration of priorities to include climate factors.
Note on B8: CRCStaffers: Assess international, national, regional and state-level (DE, MD, PA, WV, VA, NY, DC) climate change assessments.
Note on B9: CRCStaffers: Synthesize latest scientific research on sea level and water level trends; precipitation and evapotranspiration; and temperature change in both air and water
Note on B10: CRCStaffers: Assess effects of climate change on flow, temperature, and waterquality in streams of the Bay watershed. Work will build off USGS analysis examining changes in flow and temperatures in streams. USGS will be working with fish biologists on implications for freshwater populations and will also be looking at potential approaches to assess effects on nutrient and sediment loads. (listed under Modeling workgroup)
Note on B11: CRCStaffers: Work with STAR and STAC to recommend and establish performance metrics and/or indicators to assess Climate Resiliency Goal and Outcome implementation
Note on B12: CRCStaffers: Ocean Acidification: discussed at Dec 2016 STAR meeting to be added as potential STAC workshop or STAR meeting focus
Note on B15: CRCStaffers: Use the priority species habitat stressor analysis from management approach 1 to identify healthy habitat criteria for species.
Note on B16: CRCStaffers: Identify spatial tools and datasets that can be utilized to map the seasonal ranges of priority species habitats and stressors identified under management approaches 1 and 2.
Note on B17: CRCStaffers: Convert existing fish and habitat survey data for priority species to spatial datasets where needed.
Note on B18: CRCStaffers: Explore options to modify existing monitoring programs that will reduce costs and cover a range of species. This is captured in an undergraduate project by Jeremy Carton (exploring benthic and pelagic sampling gear for use in citizen science projects) and in the FY16 GIT-funded Citizen Science project which features a similar pilot study, which will be informed by Jeremy’s project to gauge the feasibility of introducing forage sampling into a Chesapeake Bay-wide citizen monitoring effort.
Note on B19: CRCStaffers: Work with partners to evaluate the feasibility of restarting phytoplankton and zooplankton monitoring. Had a discussion on the feasibility and need of restarting phytoplankton and zooplankton monitoring with Forage Action Team at September Quarterly meeting.
Note on B20: CRCStaffers: Develop a proposal for shallow-water monitoring survey(s) that address identified gaps
Note on B22: CRCStaffers: Provided at Dec STAR 2016 meeting. PT Comment: Need more direction here.
Note on B23: CRCStaffers: Develop improved fish habitat maps (convene a meeting in which STAR, GIS, and fish habitat team members develop these maps using recent data sources) STAR can maybe start that conversation. It was discussed at Dec 1 STAR meting that this might be the first step to focus on.
Note on B24: CRCStaffers: Discussed at Dec STAR 2016 meeting
Note on B25: CRCStaffers: Discussed at Dec 2016 STAR meeting
Note on B26: CRCStaffers: Discussed at Dec 2016 STAR meeting as a need, although the workgroup is looking outside CBP to address
Note on B27: CRCStaffers: Discussed at Dec 2016 STAR meeting as a need, although the workgroup is looking outside CBP to address
Note on B43: CRCStaffers: Summarize patterns in water-quality criteria attainment over time in tidal waters from 1985-2014
Note on B44: CRCStaffers: Provide an update describing temporal and regional patterns in water quality standards attainment of dissolved oxygen, water clarity/SAV and chlorophyll.
Note on B45: CRCStaffers: Publish a new Ambient Water Quality Criteria Technical Addendum that provides updated guidance on water quality standards attainment assessment methods for the tidal bay jurisdictions
Note on B46: CRCStaffers: Implement new process for quantifying trends in tidal water-quality parameters. The new process incorporates advances in methods to provide more information on trends in water-quality patterns over time.
Note on B47: CRCStaffers: Water quality results attained from 2 of the 6 high flow events assessed in April 2015 will be submitted to the CBP to be included in the 2017 CB Mid Point Assessment
Note on B48: CRCStaffers: Monitor any high flow event of greater than 100,000 cfs at Conowingo Dam occurring before May 30, 2016
Note on B49: CRCStaffers: Develop alternative monitoring plans to gather sufficient information to inform Conowingo impacts on Bay water quality standards now that it has reached "dynamic equilibrium" in the event than less that 6 high flow events occur before May 30, 2016
Note on B50: CRCStaffers: The partners in the network will collect nutrient and sediment samples from over 125 sites throughout the watershed.
Note on B51: CRCStaffers: The USGS will work with the partners to compile quality assure the information to update loads and trends.
Note on B52: CRCStaffers: USGS will completely update the reporting of loads to the Bay and trends of nutrients and sediment loads in the watershed; revised products will be prepared to communicate these results.
Note on B53: CRCStaffers: Expand upon the water quality-focused Building Environmental Intelligence report to a new process to address additional monitoring needs associated with the 2014 Chesapeake Bay Agreement. Integrate the role of Citizen Science to address gaps in water quality-related monitoring and assessment needs. Work with partners and Management Board to consider and attempt to implement recommendations.
Note on B54: CRCStaffers: Coordinate and integrate Citizens Monitoring effort funded by the Chesapeake Bay Program. Develop high quality citizens monitoring programs to assess water quality standards. Target areas where implementation will potentially show progress.
Note on B55: CRCStaffers: Develop strategy to target shallow water monitoring program with limited resources. Incorporate all spatially and temporally intensive monitoring results into Bay water quality standards attainment.
Note on B56: CRCStaffers: Test watershed factors influencing water-quality trends in tidal waters.
Note on B57: CRCStaffers: Release of a report and communication products regarding nitrogen sources and transport processes in smaller agricultural and urban watersheds.
Note on B58: CRCStaffers: Compare observed and expected trends in the watershed and relation to management actions.
Note on B59: CRCStaffers: Improve knowledge of sediment and nitrogen sources and residence times.
Note on B60: CRCStaffers: Utilize empirical, historical and current water quality data to assess Pennsylvania's progress towards meeting goals.
Note on B61: CRCStaffers: Improve knowledge of the water-quality functions of created and restored nontidal wetlands.
Note on B62: CRCStaffers: Support efforts to improve the understanding of tidal water response to changes in watershed loads.
Note on B63: CRCStaffers: Develop a new land-cover data set for the CBP watershed model.
Note on B64: CRCStaffers: Enhance the CBP watershed model using USGS measured loads for calibration as well as SPARROW model, groundwater models and other science findings.
Note on B65: CRCStaffers: Examine the impact of Susquehanna reservoirs on changes in nutrient and sediment transport to Chesapeake Bay.
Note on B66: CRCStaffers: Better utilize monitoring data to assess progress and explain observed changes in nutrients and sediment in response to management practices.
Note on B67: CRCStaffers: Incorporate data inputs, such as BMP efficiencies and land use/land cover
Note on B68: CRCStaffers: Regarding MA3 KA4. Release beta and final version of the Phase 6 Watershed Model
Note on B69: CRCStaffers: Regarding MA3 KA4. Release beta and final version of the Phase 6 Watershed Model

## Climate
Protocol support and development of indicators
Impacts of SLR, coastal storms, increased temperatures and extreme events on BMPS (maintenance, shelf life, etc)

## Stewardship
Stewardship
Public access sites and potential effects from climate change (sea-level rise and flooding)
Use results from stewardship index to help model relations of human attitudes/behaviors toward consumption, restoration and conservation.
Diversity Indicator Target/Goal for 2025 using American Community Survey Data (Overlaying state Demographic and Economic census block data over Chesapeake Bay Watershed)

## HealthyWatersheds
GIT | GIT Needs from STAR | Timeline | Completed Y/N | Timeline | STAR workgroup
Healthy Watersheds | Work with STAR team to identify and incorporate key datasets related to watershed health and vulnerability indicators for incorporation into the Tetra Tech PHWA GIT funding project. | 2018 - 2019 | in progress |  | Laura Free and indicators workgroup
| Post TT PHWA GIT funding project work with HW GIT staff to assess results and begin to determine appropriate tracking framework for potential HW sustainability indicator. | 2019 and behond | N |  | Indicators workgroup
| Compile and publish bi - annual CBP Protected Lands dataset: STAR can help to communicate the completion and availablility of the dataset as well as help to coordinate additional analysis to meet the needs of CBP teams. | Spring 2018 | in progress
| Determine a way to identify and track "mariginally healthy" waters and watersheds. Shared data gap with Stream Health workgroup |  | N

## Habitat
Habitat
GIT | GIT Needs from STAR | Timeline | Completed Y/N | Urgency/Comments | STAR workgroup
Habitat | Wetland: Expand USC wetland mapping model | 2017 | No | Check with Melissa Yearick
| Wetland: Wetland Acres reporting to NEIEN | Ongoing | In Progress | Check with Jeff Sweeney
| Wetland: QA/QC of wetland data | Ongoing | No | On hold pending WWG leadership change
| Stream Health: Input for indicator development beyond Chessie BIBI | 2020 | No
| Stream Health: support for reporting progress for Chessie BIBI | ongoing | No
| Stream Health: interaction with Healthy Watershed GIT tracking current status of streams | 2020 | No
| Brook Trout: funding for brook trout monitoring | Ongoing | No | Urgent | Monitoring
| Brook Trout: New Indicator (3-5 year occupancy census) | Ongoing | Yes, indicator chosen; EBTJV 5-year occupancy census. Might need assistance preparing #s. | Most Urgent | Indicators WG
| Black Duck: Development of habitat-based indicator | 2017 | Needs more discussion. | Most Urgent | Indicators WG
GIT Modeling Needs from STAR
| Stream Health: The relations between implementing practices to reduce nutrient and sediment and improving stream health conditions. | High
| Stream Health/Fish Habitat: Relation between stream habitat, water temperature to brook trout and other important recreational species (such as small mouth and largemouth bass). | High
| Brook Trout: Expand spatial-temporal groundwater model to rest of Chesapeake Bay Watershed to predict groundwater influence in headwater streams. | 2018-19, High Priority | No | Most Urgent
| Stream Health/Fish Habitat?: The effect of toxic contaminants, bacteria, and parasites on freshwater fish populations and implications for human consumption. | High |  |  | WQ GIT / Toxics
| Stream Health: Relation of streambank stability and erosion rates and impacts on sediment loads and fish habitats | Medium
| SAV: Climate variability and SAV habitat availability (using 1 meter resolution land cover) | Medium