## Draft Table
Oyster Restoration Outcome | Continually increase finfish and shellfish habitat and water quality benefits from restored oyster populations. Restore native oyster habitat and populations in 10 tributaries by 2025 and ensure their protection.
Factor | Gap | Management Approach | Work Plan Action | Responsible Party | Critical Action
e.g.: Use Conflict: Limited financial resources | e.g.: Fish Passage Workgroup will need more than $20 million in project implementation funds in order to meet Outcome | e.g.: Prioritize dam removal projects to ensure the strategic investment of public funds | e.g.: Identify high-priority watersheds in MD, PA and VA in which to focus fish passage efforts | e.g.: Fish Passage Workgroup | e.g.: X
Public Engagement | Need to engage with the public to develop and implement restoration efforts in Maryland and Virginia. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE | X
|  |  | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC | X
|  |  | WP Action (1.4): Continue collecting data to quantify ecosystem services on restored reefs. | NOAA, VIMS, UMD, UMCES, VCU, SERC, MD and VA Interagency Teams | X
|  |  | WP Action (1.5): Track oyster restoration efforts by community groups and efforts in other locations in the Chesapeake Bay. | MD DNR, DoD | X
|  | Management Approach (3): Future Protection. | WP Action (3.1): Maryland, Virginia and the Potomac River Fisheries Commissions natural resources law enforcement agencies will continue to implement and assess the effectiveness of enforcement plans to address poaching. | MD DNR, VMRC, MD and VA Interagency Teams | X
|  | Management Approach (4): Approaches Targeted for Local Participation. | WP Action (4.1): Conduct outreach to the general public and to stakeholders near selected tributaries or candidate tributaries to inform them and obtain their feedback about restoration efforts . | MD and VA Interagency Teams, VMRC, MD DNR, Fisheries GIT | X
|  |  | WP Action (4.2): Promote stewardship and oyster restoration through oyster gardening programs. | MD DNR, , DoD, ORP, UMCES, CBF
Legislative Engagement at the Federal, State and/or Local Levels | Legislative actions and engagement can support the acquisition of necessary data and implementation of restoration efforts. | Management Approach (2): Securing support and resources. | WP Action (2.5): The Chesapeake Bay Commission will work collaboratively with the Bay Program partners to identify legislative, budgetary and policy needs to advance the goals of the Chesapeake Watershed Agreement. CBC will, in turn, pursue action within our member state General Assemblies and the United States Congress. See CBC Resolution #14-1 for additional information on the CBC’s participation in the management strategies. | CBC, MD and VA Interagency Teams | X
Government Agency Engagement at the Federal, State and/or Local Levels | Coordinated government efforts are needed to ensure the planning and implementation of restoration efforts. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE | X
|  |  | WP Action (1.2): Virginia Interagency Team continues restoration and monitoring in the three currently selected tributaries in Virginia. | Lynnhaven Team, USACE, Lafayette Team, Piankatank Team, VMRC, Virginia Interagency Team, | X
|  |  | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC | X
|  |  | WP Action (1.4): Continue collecting data to quantify ecosystem services on restored reefs. | NOAA, VIMS, UMD, UMCES, VCU, SERC, MD and VA Interagency Teams | X
|  |  | WP Action (1.5): Track oyster restoration efforts by community groups and efforts in other locations in the Chesapeake Bay. | MD DNR, DoD | X
| Government agency engagement is necessary to secure financial support, staff time and additional resources for restoration efforts. | Management Approach (2): Securing support and resources. | WP Action (2.1): Restoration partners will continue to meet with funding agencies and organizations to maximize available resources. | MD and VA Interagency Teams
|  |  | WP Action (2.2): Restoration partners will work collaboratively to promote efficient, streamlined permitting processes. | VA Interagency Team, Lafayette Team
|  |  | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
| Government agencies should provide adequate communication and transparency in the oyster restoration process. | Management Approach (4): Approaches Targeted for Local Participation. | WP Action (4.2): Promote stewardship and oyster restoration through oyster gardening programs. | MD DNR, , DoD, ORP, UMCES, CBF
Nongovernmental Organization Engagement | Nongovernmental organizations can support, advocate, and contribute to oyster restoration efforts. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE | X
|  |  | WP Action (1.2): Virginia Interagency Team continues restoration and monitoring in the three currently selected tributaries in Virginia. | Lynnhaven Team, USACE, Lafayette Team, Piankatank Team, VMRC, Virginia Interagency Team, | X
|  |  | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC | X
|  |  | WP Action (1.5): Track oyster restoration efforts by community groups and efforts in other locations in the Chesapeake Bay. | MD DNR, DoD | X
|  | Management Approach (2): Securing support and resources. | WP Action (2.1): Restoration partners will continue to meet with funding agencies and organizations to maximize available resources. | MD and VA Interagency Teams
|  |  | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
Partner Coordination | Coordinated efforts are needed for efficient and effective oyster restoration planning and practices. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE | X
|  |  | WP Action (1.2): Virginia Interagency Team continues restoration and monitoring in the three currently selected tributaries in Virginia. | Lynnhaven Team, USACE, Lafayette Team, Piankatank Team, VMRC, Virginia Interagency Team, | X
|  |  | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC | X
|  |  | WP Action (1.4): Continue collecting data to quantify ecosystem services on restored reefs. | NOAA, VIMS, UMD, UMCES, VCU, SERC, MD and VA Interagency Teams | X
|  | Management Approach (2): Securing support and resources. | WP Action (2.1): Restoration partners will continue to meet with funding agencies and organizations to maximize available resources. | MD and VA Interagency Teams
|  |  | WP Action (2.2): Restoration partners will work collaboratively to promote efficient, streamlined permitting processes. | VA Interagency Team, Lafayette Team
|  |  | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
|  |  | WP Action (2.5): The Chesapeake Bay Commission will work collaboratively with the Bay Program partners to identify legislative, budgetary and policy needs to advance the goals of the Chesapeake Watershed Agreement. CBC will, in turn, pursue action within our member state General Assemblies and the United States Congress. See CBC Resolution #14-1 for additional information on the CBC’s participation in the management strategies. | CBC, MD and VA Interagency Teams | X
| Collaboration is needed to ensure future protection of oyster reefs. | Management Approach (3): Future Protection. | WP Action (3.1): Maryland, Virginia and the Potomac River Fisheries Commissions natural resources law enforcement agencies will continue to implement and assess the effectiveness of enforcement plans to address poaching. | MD DNR, VMRC, MD and VA Interagency Teams | X
| Coordinated efforts are needed to communicate and engage with local populations on oyster restoration efforts. | Management Approach (4): Approaches Targeted for Local Participation. | WP Action (4.1): Conduct outreach to the general public and to stakeholders near selected tributaries or candidate tributaries to inform them and obtain their feedback about restoration efforts . | MD and VA Interagency Teams, VMRC, MD DNR, Fisheries GIT | X
|  |  | WP Action (4.2): Promote stewardship and oyster restoration through oyster gardening programs. | MD DNR, , DoD, ORP, UMCES, CBF
Use Conflict | Limited supply of oyster shell, restorable bottom, hatchery supply need to be considered in the planning and implementation of oyster restoration efforts. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE | X
|  | Management Approach (3): Future Protection. | WP Action (3.1): Maryland, Virginia and the Potomac River Fisheries Commissions natural resources law enforcement agencies will continue to implement and assess the effectiveness of enforcement plans to address poaching. | MD DNR, VMRC, MD and VA Interagency Teams | X
Scientific and Technical Understanding | Additional scientific and technical understanding is necessary to improve knowledge of oyster populations, environmental impacts, disease, harvest impacts, ecosystem services, and other valuable information regarding oysters in the Chesapeake Bay. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE | X
|  |  | WP Action (1.2): Virginia Interagency Team continues restoration and monitoring in the three currently selected tributaries in Virginia. | Lynnhaven Team, USACE, Lafayette Team, Piankatank Team, VMRC, Virginia Interagency Team, | X
|  |  | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC | X
|  |  | WP Action (1.4): Continue collecting data to quantify ecosystem services on restored reefs. | NOAA, VIMS, UMD, UMCES, VCU, SERC, MD and VA Interagency Teams | X
|  |  | WP Action (1.5): Track oyster restoration efforts by community groups and efforts in other locations in the Chesapeake Bay. | MD DNR, DoD | X
|  | Management Approach (2): Securing support and resources. | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
|  |  | WP Action (2.4): Explore availability and suitability of alernative substrates for use in reef restoration and hatchery. | MD DNR, UMCES, ORP
|  | Management Approach (3): Future Protection. | WP Action (3.1): Maryland, Virginia and the Potomac River Fisheries Commissions natural resources law enforcement agencies will continue to implement and assess the effectiveness of enforcement plans to address poaching. | MD DNR, VMRC, MD and VA Interagency Teams | X
Factors Influencing Success from Management Strategy
Low Population | Low populations of oysters contribute to a decreased spat set, and more vulnerable population. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE | X
|  |  | WP Action (1.2): Virginia Interagency Team continues restoration and monitoring in the three currently selected tributaries in Virginia. | Lynnhaven Team, USACE, Lafayette Team, Piankatank Team, VMRC, Virginia Interagency Team, | X
Resource Availability (shell/substrate, hatchery spat supply) | Reduced shell/substrate and hatchery spat set supply can limit restoration efforts. | Management Approach (2): Securing support and resources. | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
|  |  | WP Action (2.4): Explore availability and suitability of alernative substrates for use in reef restoration and hatchery. | MD DNR, UMCES, ORP
Enforcement | Enforcement is necessary to protect oyster restoration efforts from illegal harvest. | Management Approach (3): Future Protection. | WP Action (3.1): Maryland, Virginia and the Potomac River Fisheries Commissions natural resources law enforcement agencies will continue to implement and assess the effectiveness of enforcement plans to address poaching. | MD DNR, VMRC, MD and VA Interagency Teams | X
Oyster Resource Management (permitting, bottom leasing, designation of sanctuary areas) | Effective management is necessary to regulate permitting, bottom leasing, and designation of sanctuary areas. | Management Approach (1): Restoration planning and implementation. | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC | X
|  | Management Approach (2): Securing support and resources. | WP Action (2.2): Restoration partners will work collaboratively to promote efficient, streamlined permitting processes. | VA Interagency Team, Lafayette Team
|  |  | WP Action (2.4): Explore availability and suitability of alernative substrates for use in reef restoration and hatchery. | MD DNR, UMCES, ORP
Shell loss | Reduced shell/substrate and hatchery spat set supply can limit restoration efforts. | Management Approach (2): Securing support and resources. | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
|  |  | WP Action (2.4): Explore availability and suitability of alernative substrates for use in reef restoration and hatchery. | MD DNR, UMCES, ORP
Hard Bottom Availability | Reduced hard bottom availability can limit restoration efforts. | Management Approach (2): Securing support and resources. | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
|  |  | WP Action (2.4): Explore availability and suitability of alernative substrates for use in reef restoration and hatchery. | MD DNR, UMCES, ORP
Public Support | Public support is needed to make informed decisions regarding the designation, protection, and knowledge of oyster restoration efforts. | Management Approach (4): Approaches Targeted for Local Participation. | WP Action (4.1): Conduct outreach to the general public and to stakeholders near selected tributaries or candidate tributaries to inform them and obtain their feedback about restoration efforts . | MD and VA Interagency Teams, VMRC, MD DNR, Fisheries GIT | X
|  |  | WP Action (4.2): Promote stewardship and oyster restoration through oyster gardening programs. | MD DNR, , DoD, ORP, UMCES, CBF
Climate Change/Ocean Acidification | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Innovative Restoration Techniques | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Navigation | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Water Quality | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Spat set variability | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Connectivity | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified

## Full Table
Oyster Restoration Outcome | Continually increase finfish and shellfish habitat and water quality benefits from restored oyster populations. Restore native oyster habitat and populations in 10 tributaries by 2025 and ensure their protection.
Factor | Gap | Management Approach | Work Plan Action | Responsible Party | How do you track whether action is complete? | Expected Response | Lesson(s) Learned | Adaptation(s) Made or Recommended | Critical Action (Indicate with an X)
e.g.: Use Conflict: Limited financial resources | e.g.: Fish Passage Workgroup will need more than $20 million in project implementation funds in order to meet Outcome | e.g.: Prioritize dam removal projects to ensure the strategic investment of public funds | e.g.: Identify high-priority watersheds in MD, PA and VA in which to focus fish passage efforts | e.g.: Fish Passage Workgroup | e.g.: High-priority watersheds identified |  |  |  | e.g.: X
Public Engagement | Need to engage with the public to develop and implement restoration efforts in Maryland and Virginia. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE |  |  |  |  | X
|  |  | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC |  |  |  |  | X
|  |  | WP Action (1.4): Continue collecting data to quantify ecosystem services on restored reefs. | NOAA, VIMS, UMD, UMCES, VCU, SERC, MD and VA Interagency Teams |  |  |  |  | X
|  |  | WP Action (1.5): Track oyster restoration efforts by community groups and efforts in other locations in the Chesapeake Bay. | MD DNR, DoD |  |  |  |  | X
|  | Management Approach (3): Future Protection. | WP Action (3.1): Maryland, Virginia and the Potomac River Fisheries Commissions natural resources law enforcement agencies will continue to implement and assess the effectiveness of enforcement plans to address poaching. | MD DNR, VMRC, MD and VA Interagency Teams |  |  |  |  | X
|  | Management Approach (4): Approaches Targeted for Local Participation. | WP Action (4.1): Conduct outreach to the general public and to stakeholders near selected tributaries or candidate tributaries to inform them and obtain their feedback about restoration efforts . | MD and VA Interagency Teams, VMRC, MD DNR, Fisheries GIT |  |  |  |  | X
|  |  | WP Action (4.2): Promote stewardship and oyster restoration through oyster gardening programs. | MD DNR, , DoD, ORP, UMCES, CBF
Legislative Engagement at the Federal, State and/or Local Levels | Legislative actions and engagement can support the acquisition of necessary data and implementation of restoration efforts. | Management Approach (2): Securing support and resources. | WP Action (2.5): The Chesapeake Bay Commission will work collaboratively with the Bay Program partners to identify legislative, budgetary and policy needs to advance the goals of the Chesapeake Watershed Agreement. CBC will, in turn, pursue action within our member state General Assemblies and the United States Congress. See CBC Resolution #14-1 for additional information on the CBC’s participation in the management strategies. | CBC, MD and VA Interagency Teams |  |  |  |  | X
Government Agency Engagement at the Federal, State and/or Local Levels | Coordinated government efforts are needed to ensure the planning and implementation of restoration efforts. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE |  |  |  |  | X
|  |  | WP Action (1.2): Virginia Interagency Team continues restoration and monitoring in the three currently selected tributaries in Virginia. | Lynnhaven Team, USACE, Lafayette Team, Piankatank Team, VMRC, Virginia Interagency Team, |  |  |  |  | X
|  |  | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC |  |  |  |  | X
|  |  | WP Action (1.4): Continue collecting data to quantify ecosystem services on restored reefs. | NOAA, VIMS, UMD, UMCES, VCU, SERC, MD and VA Interagency Teams |  |  |  |  | X
|  |  | WP Action (1.5): Track oyster restoration efforts by community groups and efforts in other locations in the Chesapeake Bay. | MD DNR, DoD |  |  |  |  | X
| Government agency engagement is necessary to secure financial support, staff time and additional resources for restoration efforts. | Management Approach (2): Securing support and resources. | WP Action (2.1): Restoration partners will continue to meet with funding agencies and organizations to maximize available resources. | MD and VA Interagency Teams
|  |  | WP Action (2.2): Restoration partners will work collaboratively to promote efficient, streamlined permitting processes. | VA Interagency Team, Lafayette Team
|  |  | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
| Government agencies should provide adequate communication and transparency in the oyster restoration process. | Management Approach (4): Approaches Targeted for Local Participation. | WP Action (4.2): Promote stewardship and oyster restoration through oyster gardening programs. | MD DNR, , DoD, ORP, UMCES, CBF
Nongovernmental Organization Engagement | Nongovernmental organizations can support, advocate, and contribute to oyster restoration efforts. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE |  |  |  |  | X
|  |  | WP Action (1.2): Virginia Interagency Team continues restoration and monitoring in the three currently selected tributaries in Virginia. | Lynnhaven Team, USACE, Lafayette Team, Piankatank Team, VMRC, Virginia Interagency Team, |  |  |  |  | X
|  |  | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC |  |  |  |  | X
|  |  | WP Action (1.5): Track oyster restoration efforts by community groups and efforts in other locations in the Chesapeake Bay. | MD DNR, DoD |  |  |  |  | X
|  | Management Approach (2): Securing support and resources. | WP Action (2.1): Restoration partners will continue to meet with funding agencies and organizations to maximize available resources. | MD and VA Interagency Teams
|  |  | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
Partner Coordination | Coordinated efforts are needed for efficient and effective oyster restoration planning and practices. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE |  |  |  |  | X
|  |  | WP Action (1.2): Virginia Interagency Team continues restoration and monitoring in the three currently selected tributaries in Virginia. | Lynnhaven Team, USACE, Lafayette Team, Piankatank Team, VMRC, Virginia Interagency Team, |  |  |  |  | X
|  |  | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC |  |  |  |  | X
|  |  | WP Action (1.4): Continue collecting data to quantify ecosystem services on restored reefs. | NOAA, VIMS, UMD, UMCES, VCU, SERC, MD and VA Interagency Teams |  |  |  |  | X
|  | Management Approach (2): Securing support and resources. | WP Action (2.1): Restoration partners will continue to meet with funding agencies and organizations to maximize available resources. | MD and VA Interagency Teams
|  |  | WP Action (2.2): Restoration partners will work collaboratively to promote efficient, streamlined permitting processes. | VA Interagency Team, Lafayette Team
|  |  | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
|  |  | WP Action (2.5): The Chesapeake Bay Commission will work collaboratively with the Bay Program partners to identify legislative, budgetary and policy needs to advance the goals of the Chesapeake Watershed Agreement. CBC will, in turn, pursue action within our member state General Assemblies and the United States Congress. See CBC Resolution #14-1 for additional information on the CBC’s participation in the management strategies. | CBC, MD and VA Interagency Teams |  |  |  |  | X
| Collaboration is needed to ensure future protection of oyster reefs. | Management Approach (3): Future Protection. | WP Action (3.1): Maryland, Virginia and the Potomac River Fisheries Commissions natural resources law enforcement agencies will continue to implement and assess the effectiveness of enforcement plans to address poaching. | MD DNR, VMRC, MD and VA Interagency Teams |  |  |  |  | X
| Coordinated efforts are needed to communicate and engage with local populations on oyster restoration efforts. | Management Approach (4): Approaches Targeted for Local Participation. | WP Action (4.1): Conduct outreach to the general public and to stakeholders near selected tributaries or candidate tributaries to inform them and obtain their feedback about restoration efforts . | MD and VA Interagency Teams, VMRC, MD DNR, Fisheries GIT |  |  |  |  | X
|  |  | WP Action (4.2): Promote stewardship and oyster restoration through oyster gardening programs. | MD DNR, , DoD, ORP, UMCES, CBF
Use Conflict | Limited supply of oyster shell, restorable bottom, hatchery supply need to be considered in the planning and implementation of oyster restoration efforts. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE |  |  |  |  | X
|  | Management Approach (3): Future Protection. | WP Action (3.1): Maryland, Virginia and the Potomac River Fisheries Commissions natural resources law enforcement agencies will continue to implement and assess the effectiveness of enforcement plans to address poaching. | MD DNR, VMRC, MD and VA Interagency Teams |  |  |  |  | X
Scientific and Technical Understanding | Additional scientific and technical understanding is necessary to improve knowledge of oyster populations, environmental impacts, disease, harvest impacts, ecosystem services, and other valuable information regarding oysters in the Chesapeake Bay. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE |  |  |  |  | X
|  |  | WP Action (1.2): Virginia Interagency Team continues restoration and monitoring in the three currently selected tributaries in Virginia. | Lynnhaven Team, USACE, Lafayette Team, Piankatank Team, VMRC, Virginia Interagency Team, |  |  |  |  | X
|  |  | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC |  |  |  |  | X
|  |  | WP Action (1.4): Continue collecting data to quantify ecosystem services on restored reefs. | NOAA, VIMS, UMD, UMCES, VCU, SERC, MD and VA Interagency Teams |  |  |  |  | X
|  |  | WP Action (1.5): Track oyster restoration efforts by community groups and efforts in other locations in the Chesapeake Bay. | MD DNR, DoD |  |  |  |  | X
|  | Management Approach (2): Securing support and resources. | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
|  |  | WP Action (2.4): Explore availability and suitability of alernative substrates for use in reef restoration and hatchery. | MD DNR, UMCES, ORP
|  | Management Approach (3): Future Protection. | WP Action (3.1): Maryland, Virginia and the Potomac River Fisheries Commissions natural resources law enforcement agencies will continue to implement and assess the effectiveness of enforcement plans to address poaching. | MD DNR, VMRC, MD and VA Interagency Teams |  |  |  |  | X
Factors Influencing Success from Management Strategy
Low Population | Low populations of oysters contribute to a decreased spat set, and more vulnerable population. | Management Approach (1): Restoration planning and implementation. | WP Action (1.1): Maryland Interagency Team continues restoration and monitoring in the three currently selected tributaries in Maryland. | MD Interagency Team, University of MD, MD DNR, USACE |  |  |  |  | X
|  |  | WP Action (1.2): Virginia Interagency Team continues restoration and monitoring in the three currently selected tributaries in Virginia. | Lynnhaven Team, USACE, Lafayette Team, Piankatank Team, VMRC, Virginia Interagency Team, |  |  |  |  | X
Resource Availability (shell/substrate, hatchery spat supply) | Reduced shell/substrate and hatchery spat set supply can limit restoration efforts. | Management Approach (2): Securing support and resources. | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
|  |  | WP Action (2.4): Explore availability and suitability of alernative substrates for use in reef restoration and hatchery. | MD DNR, UMCES, ORP
Enforcement | Enforcement is necessary to protect oyster restoration efforts from illegal harvest. | Management Approach (3): Future Protection. | WP Action (3.1): Maryland, Virginia and the Potomac River Fisheries Commissions natural resources law enforcement agencies will continue to implement and assess the effectiveness of enforcement plans to address poaching. | MD DNR, VMRC, MD and VA Interagency Teams |  |  |  |  | X
Oyster Resource Management (permitting, bottom leasing, designation of sanctuary areas) | Effective management is necessary to regulate permitting, bottom leasing, and designation of sanctuary areas. | Management Approach (1): Restoration planning and implementation. | WP Action (1.3): Select additional tributaries in Maryland and/or Virginia for restoration. | MD and VA Interagency Teams, MD DNR, VMRC |  |  |  |  | X
|  | Management Approach (2): Securing support and resources. | WP Action (2.2): Restoration partners will work collaboratively to promote efficient, streamlined permitting processes. | VA Interagency Team, Lafayette Team
|  |  | WP Action (2.4): Explore availability and suitability of alernative substrates for use in reef restoration and hatchery. | MD DNR, UMCES, ORP
Shell loss | Reduced shell/substrate and hatchery spat set supply can limit restoration efforts. | Management Approach (2): Securing support and resources. | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
|  |  | WP Action (2.4): Explore availability and suitability of alernative substrates for use in reef restoration and hatchery. | MD DNR, UMCES, ORP
Hard Bottom Availability | Reduced hard bottom availability can limit restoration efforts. | Management Approach (2): Securing support and resources. | WP Action (2.3): Consider the concerns of shell budget and hatchery capacity and how to address future issues. | MD and VA Interagency Teams
|  |  | WP Action (2.4): Explore availability and suitability of alernative substrates for use in reef restoration and hatchery. | MD DNR, UMCES, ORP
Public Support | Public support is needed to make informed decisions regarding the designation, protection, and knowledge of oyster restoration efforts. | Management Approach (4): Approaches Targeted for Local Participation. | WP Action (4.1): Conduct outreach to the general public and to stakeholders near selected tributaries or candidate tributaries to inform them and obtain their feedback about restoration efforts . | MD and VA Interagency Teams, VMRC, MD DNR, Fisheries GIT |  |  |  |  | X
|  |  | WP Action (4.2): Promote stewardship and oyster restoration through oyster gardening programs. | MD DNR, , DoD, ORP, UMCES, CBF
Climate Change/Ocean Acidification | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Innovative Restoration Techniques | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Navigation | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Water Quality | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Spat set variability | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Connectivity | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified