Timeline for Outreach to GITs - DRAFT

| Activity | Jan 2016 | Feb 2016 | Mar 2016 | Apr 2016 | May 2016 | Jun 16 | Jul 2016 | Aug 2016 | Sep 2016 | Oct 2016 | Nov 2016 | Dec 2016 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Develop questionnaire for GITs to identify local engagement needs |  |  |  |  |  |  |  |  |  |  |  |  |
| Distribute questionnaire to GIT coordinators and obtain feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Review GIT feedback and conduct follow up sessions to clarify GIT needs |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify and implement early content delivery and engagement opps. |  |  |  |  |  |  |  |  |  |  |  |  |
| Review GIT needs and conduct multi-benefits analysis (review existing CBP efforts) |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop and present to LL Workgroup recommended content and delivery mechanisms for GIT information |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop and deliver content to achieve multiple benefits |  |  |  |  |  |  |  |  |  |  |  |  |

Timeline for Outreach to State and Regional Associations - DRAFT

| Activity | Jan 2016 | Feb 2016 | Mar 2016 | April 2016 | May 2016 | June 2016 | July 2016 | August 2016 | Sep 2016 | Oct 2016 | Nov 2016 | Dec 2016 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Develop a list of state and regional forums of local elected officials and contacts |  |  |  |  |  |  |  |  |  |  |  |  |
| Reach out to key contacts to identify key contact needs, avenues, opps (questionnaire) |  |  |  |  |  |  |  |  |  |  |  |  |
| Review feedback and follow up with key contacts for clarification |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify and implement early content delivery and engagement opps. |  |  |  |  |  |  |  |  |  |  |  |  |
| Review existing CBP content and delivery and conduct multi-benefits analysis (Mar – May) |  |  |  |  |  |  |  |  |  |  |  |  |