## (LU Methods & Metrics) Workplan
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | FMI: Deliverables | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Outcome: Land Use Methods & Metrics Development
Goal: Conserve landscapes to maintain water quality and habitst; sustain working forests, farms and maritime communities; and conserve lands of cultural, indigenous and community value.
Outcome: Develop a Chesapeake Bay watershed-wide methodology and local level metrics for characterizing rate of farmland, forest and wetland conversion, measuring the extent and rate of change in impervious surface coverage and quantifying the potential impacts of land conversion to water quality, healthy watershedes and communities. Launch a public awareness campaign to share this information with citizens, local governments, elected officials and stakeholders.
Long term Target: Continual monitoring of land use and change every 2-5 years
2 year Target: By 2016, develop methodology and local level metrics for measuring rate and extent of land conversion and quantify potential impacts to ecosystems and communities. Launch a public awareness campaign.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Deliverables | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Management Approach 1: Monitor the (rate of) conversion of forests, wetlands, and farmlands(, and the rate of impervious surfaces change).
Design a manual, stratified sampling approach at the county level and assess land cover change from high resolution imagery circa 2005-2013. -FMI: Why not ground stratified sampling in physical small to mid-sized watersheds and later relate findings back to counties? | Research stratification techniques | USGS, LUWG, UMBC Summer Intern Program | TBD | Summer 2016 | Report ~ " An overview of High Resolution Land Cover Stratified Sampling Techniques", LUWG Presentation.
| Design sampling framework | USGS, LUWG |  |  | Report: ~ "A High Resolution Land Cover Change Sampling Design for One County in the Cheapeake Bay Watershed"
| Implement sampling framework |  |  |  | GIS Rasters with attribute tables and Metadata, Report:~ " Implementation of a High Resolution Land Cover Change Sampling Design in One County of the Chesapeake Bay Watershed", LUWG presentation
Assess land use change throughout the entire Bay Watershed, at a 30 meter minimum mapping unit, from 1984-2011 using the P6 land use database and the MRLC National Land Cover Database (NLCD). | Work with CBP GIS Team to assign and completed task | CBPO (USGS), LUWG | Chesapeake Bay Watershed and intersecting Counties | end of Summer 2016 -FMI: Including QAQC? | GIS Rasters and attribute tables with Metadata, Report: "Summary of 1984-2011 Chesapeake Bay Watershed Land Use Change", LUWG presentation
Assess difference in high resolution land cover maps at the County level. for one prototype County. | Quantify changes in two high-res land cover maps representing different years. | CBPO, USGS, LUWG | Prince George's County, MD | end of Summer 2016 | GIS Rasters with Metadata, Report:~ "Quantifying High Resolution Land Cover Change Over Two Years, Observations, Recommendations, and Lessons Learned"
| Separate persistent from ephemeral change | CBPO, USGS, LUWG | Prince George's County, MD | end of Summer 2016 | GIS Rasters and attribute tables. Report: Findings to be included in above report.
| Quantify commission and omission errors. | CBPO, USGS, LUWG | Prince George's County, MD | end of Summer 2016 | Maps, Tables, Report: Findingsto be included in above report.
Conduct a literature review on high resolution land cover change methods. (Unfunded FY 2016 GIT Funding proposal) | Review literature of the science and technologies assiciated with remote sensing and image interpretation as well as consultation with remote sensing professionals | LUWG Staffer | N/A | end of Summer 2016 | Report: ~ " literature review on high resolution land cover change methods." LUWG Presentation?
Management Approach 2: Quantify the impacts of land conversion on water quality, healthy watersheds, and communities
Quantify impact of land conversion on: 1. Water quality (Explaining changes in nutrient and sediment that relate to monitored and modeled land conversion) -FMI1: At the County?/Basin?/HUC8?/Other level? -FMI2: No mention of ground water lag times, legacy soils, or stream geomorphology anywhere in this doc. | Work with USGS to explain change in WQ related to major source sectors (urban, agriculture) | USGS and LUWG (No state Geological Surveys?) | Chesapeake Bay Watershed | 2017-12-01 | Report: Findings and Recommendations, LUWG Presentation
| Work with CBPO to interpret Phase 6 sensitivity of WQ to land conversion | CBPO, USGS, and LUWG | Chesapeake Bay Watershed | 2017-12-01 | Report: Findings and Recommendations, LUWG Presentatio
Quantify impact of land conversion on: 2. Healthy Watersheds and Habitats | Vulnerability to land coversions, both historical and future projections | CBPO, USGS, and LUWG | State-identified healthy watersheds | 2017-12-01 | Report: Findings and Recommendations, LUWG Presentatio
| Impact (relates to tracking health) | CBPO, USGS, and LUWG | State-identified healthy watersheds | TBD | Report: Findings and Recommendations, LUWG Presentation
Quantify impact of land conversion on: 3. Communities | Set up an Action Team to define the metrics and assess the impacts to communities | LGAC and LUWG | Chesapeake Bay Watershed Counties | TBD | Goal Statement, Meeting Minutes and Action items.
| Work with Healthy Watersheds GIT and Land Use Options Evaluation Management Strategy team to link the results of land use methods and metrics anayses and results to determine how best to assist communities in reducing the rate of conversion (the Land Use Options Goal) | HWGIT, CAC, LGAC, CBP Communications team, and other CBP identified partners | Chesapeake Bay Watershed | TBD | Work Plan with meetings schedule, anticipated outcomes. White paper with analysis results and action plan.
Management Approach 3: Communicate results to public, elected officials, and to the Bay Program
Key Action** | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | FMI: Deliverables | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Link the results of the Land Use Methods and Metrics outcome and the Land Use Options Evaluation Workplan | Work with Healthy Watersheds GIT and Land Use Options Evaluation Management Strategy team to link the results of land use methods and metrics anayses and results to determine how best to assist communities in improving the character and reducing the rate of conversion (the Land Use Options Goal) | HWGIT, CAC, LGAC, CBP Communications team, and other CBP identified partners |  |  | Action plan/meeting schedule with anticipated outcomes, Synthesis document with recommendations for local, county and state interactions.
Chesapeake Bay Land Change website | Launch Phase 6 land use data website | USGS and CBPO (Web Team) |  | 2015-12-01 | Beta web site
| Testing, refinement, expansion | USGS and CBPO (Web Team) |  | 2017-12-01 | Published web site
| Develop land change forecasts | USGS and LUWG |  | Summer 2016 | Field tested web site with land change forecast data.
Note: This portion (Which?) of the outcome is outside the scope and expertise of the CBP GIS team and the LUWG.
**Note: As a member of the Chesapeake Executive Council and a signatory to the Chesapeake Bay Watershed Agreement, the Chesapeake Bay Commission (CBC) functions as the legislative arm of the Chesapeake Bay Program working within Maryland, Pennsylvania and Virginia and at the federal level to identify specific Bay management concerns requiring intergovernmental coordination and cooperation. CBC makes recommendations to the federal, state and local governments on legislative and administrative actions necessary to effectuate coordinated and cooperative management for the Bay watershed. The Commission will work collaboratively with Bay Program partners to identify legislative, budgetary and policy needs to advance the key actions identified in this outcome and to anticipate those needed in the future. The CBC’s work is supported by the annual appropriations of its three member states totaling $675,000 and is, on occasion, supplemented by project-specific grants.