## Slide 1
Timeline for 2017 Land Cover and Land Use Review/Refinement
April 2021 – February 2022
Apr – Jun 2021: Sector workgroups (AGWG, FWG, USWG, LUWG) review beta version of 2017 Land Use. Local government review of 2017 land cover continues for outstanding counties.
Jul – Nov 2021:
University of Vermont (UVM) corrects all land cover errors from local and expert review (e.g., over-classification of water, confusion between water and impervious) and produces land cover for counties adjacent to the Bay watershed.
UVM maps emergent tidal wetland land cover in Virginia and potential non-tidal wetlands in all jurisdictions outside PA (PA was done in 2016).
Conservation Innovation Center (CIC) continually evaluates and refines land use model code.
Dec 2021 – Jan 2022:
CIC re-runs 2017 land use on revised land cover and produces comparable 2013 land use for all 206 counties.
Feb 2022: LUWG approves 2013 and 2017 land use.

## Slide 2
Timeline for 2013 - 2017 Land Use Change Review for CAST-21
April – June 2021
Apr 26: WQGIT presented with information on the 2013-2017 land use change product, how it can be incorporated into CAST, and an overview of the decision that will be requested of the WQGIT during their May 24 call.
May 5 – May 17:
Sector workgroups (AGWG, USWG, FWG) review 2017 land use in prototype of CAST-21 with the 2017 land use currently in CAST-19 for the 14 test counties. The 2013-2017 mapped changes in land use will be available to inspect on Conservation Innovation Center’s (CIC) web application.
May 5: LUWG discusses 2013-2017 land use change data, methodology, and the comparison between CAST-19 and CAST-21.
May 20: LUWG meets to review comments from sector workgroups on the land use change data in CAST and on the CIC’s web application and makes recommendation to the WQGIT on use of the change data in CAST.
May 24: WQGIT decision: approval of method for using 2013 – 2017 land use change data in CAST as implemented in the 14 prototype counties.
Jun 30: CIC completes initial version of the 2013-2017 land use change dataset for all Bay watershed counties.