## LUWG_schedule
Land Use Workgroup Tasks |  |  | 2015 | [51 empty] | 2016
2015-01-05
Task # | Task Name | Lead | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep
 | time axis 2015-01-05 to 2016-09-26
1 | Phase 6 Land Use
1.01 | Draft Regional P6 Land Use Database | CBPO | bar: 2015-02-02 to 2015-03-23
1.02 | Draft Local P6 Land Use Database | CBPO & MDE | bar: 2015-02-02 to 2015-04-27
1.03 | Initiate P6 LU review with local jursidctions | LUWG | bar: 2015-03-30 to 2015-04-27
1.04 | Approve LU target loads | Modeling Workgrp | bar: 2015-05-11
1.05 | Utilize federal facility LU editor tool | Federal facilities | bar: 2015-05-04 to 2015-06-29
1.06 | Approve federal facility targets | MB & PSC | bar: 2015-07-06 to 2015-07-27
1.07 | Briefing on P6 Land Use Data | LUWG to PSC | bar: 2015-07-06 to 2015-07-27
1.08 | Review P6 Land Use Database | Jurisdictions | bar: 2015-05-04 to 2015-06-29
1.09 | Update, finalize, and approve P6 Land Use Database, v1 | LUWG, WQGIT | bar: 2015-07-06 to 2015-09-28
1.1 | Provide additional LU & LC data | Jurisdictions | bar: 2015-10-05 to 2016-05-30
1.11 | Incorporate additional LU & LC data & Finalize P6 Land Use v2 | CBPO | bar: 2016-06-06 to 2016-07-25
1.12 | Review final P6 Land Use Database, v2 | Jurisdictions | bar: 2016-08-01 to 2016-08-29
1.13 | Finalize P6 Land Use Database, v2 | CBPO | bar: 2016-09-05 to 2016-09-26
2 | Forecasting Land Use Change
2.01 | Complete future trend scenario | CBPO | bar: 2015-03-23 to 2015-04-27
2.02 | Review trend scenario | LUWG | bar: 2015-05-04 to 2015-06-29
2.03 | Identify alternative future scenarios | LUWG | bar: 2015-05-25; 2015-06-29
2.04 | Simulate alternative future scenarios | Claggett | bar: 2015-07-06 to 2015-08-31
2.05 | Review alternative future scenarios | Claggett | bar: 2015-09-07 to 2015-10-26
2.06 | Consider setting Phase III WIPs on future land use | WQGIT | bar: 2015-11-02 to 2015-11-30
2.07 | Decision: setting Phase III WIPs on future land use | bar: 2016-05-02 to 2016-05-30
3 | Land Use Metrics Outcome
3.01 | Clarify outcome intent and criteria | LUWG | bar: 2015-01-05 to 2015-01-26
3.02 | Develop draft management strategies | LUWG | bar: 2015-01-05 to 2015-02-23
3.03 | Review management strategies | Management Board | bar: 2015-03-02 to 2015-03-09
3.04 | Review management strategies | Jurisdicitons | bar: 2015-03-16 to 2015-04-06
3.05 | Respond to comments | LUWG | bar: 2015-04-13 to 2015-05-04