Management Strategy Timeline for Public Release

Jan. 30 – Revised management strategy posters uploaded to the CBP website

Feb. 2 –MB and Advisory Committee deadline for providing comments on preliminary drafts (send to Greg Barranco)

Feb. 2- Mar. 2 – GITs/workgroups refine draft strategies

Mar. 2 – GITs/workgroups send revised strategies to the MB for sufficiency review

March 6 – MB deadline for submitting fatal flaw comments to GITs/workgroups

Mar. 16 – Post/release management strategies public input

Apr. 20 – Public input period closes

May 4 – GITs/workgroups revise strategies and provide to MB for final review

June 15 – Final management strategies completed

Dec. 15 – First Biennial workplan due