## Slide 1: Update on GIT Funding FY 14, FY 15 and Beyond
Greg Allen EPA CBPO
September 30, 2015

## Slide 2: Discussion Outline
Look Back – FY 14
Update on FY 14 GIT projects
Current – FY 15
Funding amount and summary of project proposals
Process used to decide projects to be funded
Timeline
Process for MB and others in finding means for unfunded projects
Expectations for FY 16 and Ideas for Process Improvements

## Slide 3: FY 14 GIT Funding
Proposals Submitted
29 projects submitted
$1,296,100 value of projects submitted
Proposals Funded
17 projects awarded
$862,000 value awarded
Vehicles – three Inter-Agency Agreements, MdCBIG-CBT grant, Va CBRAP grant, ICPRB grant, one EPA contract

## Slide 4: FY 15 GIT Funding
Proposals Submitted
37 projects submitted
$2,208,000 value of projects submitted
Proposals Funded
12 projects awarded
$700,000 value awarded
$150,000 Cross-Program Coordinator
Vehicles – EPA Grant (CBT), Inter-Agency Personnel Agreement

## Slide 5: Process used to determine FY 15 projects to be funded
Spring 2015 Prompted GITs to begin thinking about needs in
Summer 2015 Issued background information, proposal form, criteria to consider and timeline
Summer 2015 GIT chairs added additional criteria and asked for a check on combining and reducing project costs
September 9 GITs submitted final prioritized lists
September 15 GIT Cdtrs/Staffers met to look for possible combinations and to rank the #2 priority group using – cross-outcome value, equity, and leverage
September 24 GIT chairs agree on cross-program Coordinator and accepted Cdtrs/Staffers recommendation for projects to be funded 9/24/15

## Slide 6: FY 15 Projects Timeline (Cont’d)
October 7 - Deadline for GITs to submit detailed specifications for projects selected for funding.
October 9 – The final priority GIT projects are submitted to CBT with detailed scope of work to begin their RFP and sub-award process. Technical leads are identified for each project.
October 30 – CBT notifies EPA of any projects that it proposes to complete in-house.
December (tentative) – CBT completes sub-awards.
January 2016 (tentative) – GIT technical leads meet with awardees to commence projects.

## Slide 7: Unfunded FY 15 Projects
What process can be undertaken to find resources for projects that were not funded?
What is the MB’s role?
What other CBP groups or outside groups can be engaged?

## Slide 8: FY 15 Unfunded Projects – Next Steps
Return list to GITs and ask them to :
  Reaffirm that projects are still needed
  Indicate any for which funding has been identified
Revised list and detailed descriptions sent to the MB; request ideas for near term or future funding
How can we communicate the needs among partners?
How can we engage funding networks?
How can we align with future budget cycles?
GIT 6 revisiting Budget and Finance Workgroup proposal

## Slide 9: FY 16 GIT Funding and Ideas for Improvement
Contingent on availability of funds
Based on GIT priorities or broader program priorities?
GIT Chair decision or other entity?
Start early and have a focus group review the Fy14/FY15 process and consider options for alternate approaches