## Slide 1
Management Strategy Timeline | 
March 16 | Release management strategies for public input
April 9 April 30 | MB meeting Public input period closes
May 1 - 22 May 14 May 22 May 27/28 | GITs/workgroups revise strategies based on comments MB meeting Strategies to MB for final review MB meeting
June 2 June 11 June 30 | PSC meeting MB meeting Final management strategies completed
July 9 July TBD | MB meeting Executive Council Meeting
Dec. 30 Jan 15 | First Biennial workplan due First Biennial workplan due