## Sheet1
Phase 6 Fatal Flaw Review Comments and Issues
Name of Commenter | Affiliation | Comment | Date Received | CBPO Contact | Lead Partnership Group | (Proposed) Resolution
Darold Burdick | Fairfax County | For Fairfax County’s rolled-up nutrient input numbers (i.e. “Lbs Applied), there appears to be an anomalous drop for 1987. It occurs in both TN & TP | 2017-04-25 | Gary Shenk | CBPO Modeling Staff | Error found in one of the input tables for CAST. This was corrected for the Draft Phase 6
Bill Keeling | VA DEQ | The second one is related to animal numbers and spatial location. This in my mind has 3 components: 1) numbers and spatial distribution through the calibration period, 2) numbers and distribution for annual progress runs, 3) numbers both contributing to a LA and WLA for an allocation. Numbers 1 and 2 on this item could use something less than permit maximums but the allocation for a 2025 condition must use permit maximums and locations at least for VA. I have concerns that what has been proposed/approved by the AMS/AgWG might work for 1 and 2 but appears inadequate for allocation purposes. The calibration data must be resolved before the August calibration. But on the heels of that will come the allocation or target development so we need resolution on a method that accounts for facilities in existence now and those that will be operational in 2025 at permit maximums so that portion of the Ag load is properly accounted for similar to wastewater facilities current discharge verses what they are allocated. | 2017-04-26 | Matt Johnston | AMS/AgWG
Bill Keeling | VA DEQ | VA high resolution LU QAQC statistics in Peters LU matrix. | 2017-04-26 | Peter Claggett | LUWG | WQGIT agreed fatal flaw
Alisha Mulkey | MDA | Soil P modeling. As I review the final soil P time series, I question the management implications where soil P is ~85-100 ppm over the calibration period. This range represents many of the MD land segment plots. At these concentrations the state would not likely limit P inputs thus minimizing my opportunity to create change in the subsequent EOSS loads. I would like to discuss the model mechanic options (building on the APLE work) for considering soil P annually as a source of nutrients for crop uptake not just sensitivity for loss. This would produce an annual change in concentration and may eliminate the need for projection scenario concerns. Bill Angstadt has initial thoughts on this formula that I will ask him to share. | 2017-06-13 | Gary Shenk | CBPO Modeling Staff / AgWG | In discussion 6/14
Alisha Mulkey | MDA | Benefits of NM. This overlaps a scenario request provided from Rich (emailed today) on behalf of the AgWG, but I wish to understand how core versus non-core NM acres act to cap the application to crops for manure-rich counties. Example, if I improve Somerset county to 100% core-NM but do not change the broiler population, what is the effect on my load? | 2017-06-13 | Matt Johnston | CBPO Modeling Staff | In discussion 6/14
Alisha Mulkey | MDA | Crop Uptake versus Removal. These are two distinct concepts and should not be used interchangeably within data sets. As I read section 3.7 of the documentation, I would ask to revisit the AgWG decision (details, date?) and rationale for using both within a data set. Mistakes also seem to exist on labeling within Tableau (e.g. descriptors are uptake, but values appear to be removal) and Table 3-34 where corn and soybean is labeled with "lbs N uptake/application unit" but the values again appear to be removal. | 2017-06-13 | Matt Johnston | CBPO Modeling Staff | In discussion 6/14
Greg Busch | MDE | Biosolids inputs do not match what was submitted by MD. | 2017-06-16 | Matt Johnston | CBPO Modeling Staff | Error found in CAST data. Error impacts biosolid nutrient applications, but does not significantly impact total nutrient applications as biosolids make up a very small percentage of overall applications. Staff can easily fix data if recalibration occurs.
Greg Busch | MDE | Enhanced Vegetative Index may not be appopriate for use the land-to-water factors. The modeling team did not test this as understood at the modeling workgoup | 2017-06-29 | Gary Shenk | CBPO Modeling Staff | This test will be part of the recalibration, as oritinally proposed
Greg Busch | MDE | streambank erosion and floodplain deposition does not capture localized factors | 2017-06-29 | Gary Shenk | CBPO Modeling Staff | in discussion
Greg Busch | MDE | land use true-up procedure creating additional impervious acres | 2017-06-29 | Gary Shenk | CBPO Modeling Staff | in discussion
Greg Busch | MDE | Phosphorus delivery factors above 1 are difficult to explain to stakeholders | 2017-06-29 | Gary Shenk | Modeling Workgroup | in discussion
James Davis-Martin | VA DEQ | Shoreline length and loads should be assigned by agency. It is not acceptable that 100%of shoreline is currently attributed to non-federal | 2017-07-05 | Gary Shenk | CBPO Modeling Staff | CBPO staff agrees. Unlikely to be objections. Will discuss at WQGIT
Dave Montali | WV DEP | I am requesting consideration of increasing the uncertainty associated with the AgriAnalysis observations in Berkeley County so that the soil history representation becomes more similar to Berkeley’s neighboring counties. | 2017-07-07 | Gary Shenk | CBPO Modeling Staff | CBPO staff agrees. Will take to the MWG
James Davis-Martin | VA DEQ | We should reconsider the uniform soil test P application across all ag LUs. Logic suggests that w/o manure LUs should have lower soil P than those acres receiving manure. Maybe it should follow the manure application rules, LUs receiving the most manure should have the highest soil P and those receiving none should have the lowest, rather than applying the countywide average to all LUs | 2017-07-07 | Matt Johnston | AMS | should go to workgroup
James Davis-Martin | VA DEQ | Clarke and Botetourt County, VA (and Botetourt) nutrient application rates for MSS4 turf and canopy over turf are different than all other VA counties by a slight amount | 2017-07-07 | Matt Johnston | CBPO Modeling Staff | They are actually the same in CAST. The Tableau system had a rounding error that made them look different
James Davis-Martin | VA DEQ | On the Plant Nutrient uptake tab 2005 CSS Construction nitrogen lbs applied spikes to over 350 lbs/ac/yr on a very small acreage. Clearly we do not intend to load this land use at that rate. It should not matter how tiny the acres, the application rates should be proportional. | 2017-07-07 | Matt Johnston | CBPO Modeling Staff | in discussion
James Davis-Martin | VA DEQ | Land Use through time in Northampton, Accomack, Albemarle and Page counties show declines in developed lands in some years. Seems unlikely. Should we have a rule in the LU hindcast/forecast that urban lands cannot be reduced through time (except through explicitly reported impervious surface reduction BMPs)? | 2017-07-07 | Matt Johnston | LUWG | should go to workgroup
James Davis-Martin | VA DEQ | Nutrient application rates (N and P) on turf is an order of magnitude different across the watershed, ranging from about 1/20th to ½ of the recommended fertilization rates. While I appreciate the desire to use the fertilizer salesdata, seeing it applied to the available acres producing the huge difference in application rates between the states is clearly not representative of reality and probably is not the best approach. USWG should be asked to reconsider decision rules in light of the observed impact. | 2017-07-07 | Matt Johnston | USWG | should go to workgroup
Alisha Mulkey | MDA | 5. Maryland’s soil P time series are largely reasonable with modest values across most counties and land uses. Remaining questions are: a. Many segments have soil P at 85-100 ppm over the calibration period. At these concentrations the state would not likely limit P inputs thus minimizing an opportunity to create change in the subsequent EOSS loads. I would like additional conversations with CBP and states on the potential management implications of this outcome. b. Creating the soil P time series relied on observed data sets from university and private labs where subsequent statistical methods were used to derive the time series. Please detail the robustness of the original observed data specifically used for “ag open space” and “specialty” land uses. c. Is there support, building on the APLE work, to consider soil P annually as a source of nutrients for crop uptake not just sensitivity for loss, i.e. mass balance option. This would produce an annual change in concentration and may eliminate the need for projection scenario concerns. | 2017-07-13 | Gary Shenk | CBPO / AgWG / AMS / MWG | conversations with CBP. Will ask for Andrew to work on 'B'
Alisha Mulkey | MDA | Section 2.5 of the P6 documentation states “An area of considerable uncertainty is the phosphorus losses in stream reaches that are not reservoirs. Ator and others, 2011, Noe and others 2015a and 2016b indicate that the losses in free-flowing streams and rivers are relatively small. The Phase 5.3.2 watershed model had a significant loss of 12.8 million pounds of P in these systems. Attempts to calibrate the Phase 6 model in beta versions using the assumption of no let loss were not successful. Several major river systems had more phosphorus measured at the output than was generated by all upstream sources. For this reason, the Phase 5.3.2 losses of 12.8 million pounds were used in the final version.” Does this statement suggest an additional 12.8 m lbs of legacy P exist in the stream network that have been unaccounted for in all inputs to the landscape? If yes, please confirm if the 12.8 million lbs P were then added to the calculation for estimating global targets and subsequently inferred to be primarily ag contributed given the global target methodology (i.e. crop ratio = 1.0)? | 2017-07-13 | Gary Shenk | CBPO Modeling Staff | Calibration method. GS will write a response and discuss with AgWG and MWG
Alisha Mulkey | MDA | Section 2.5 of the P6 documentation states “An area of considerable uncertainty is the phosphorus losses in stream reaches that are not reservoirs. Ator and others, 2011, Noe and others 2015a and 2016b indicate that the losses in free-flowing streams and rivers are relatively small. The Phase 5.3.2 watershed model had a significant loss of 12.8 million pounds of P in these systems. Attempts to calibrate the Phase 6 model in beta versions using the assumption of no let loss were not successful. Several major river systems had more phosphorus measured at the output than was generated by all upstream sources. For this reason, the Phase 5.3.2 losses of 12.8 million pounds were used in the final version.” Does this statement suggest an additional 12.8 m lbs of legacy P exist in the stream network that have been unaccounted for in all inputs to the landscape? If yes, please confirm if the 12.8 million lbs P were then added to the calculation for estimating global targets and subsequently inferred to be primarily ag contributed given the global target methodology (i.e. crop ratio = 1.0)? | 2017-07-13 | Gary Shenk | CBPO Modeling Staff | Calibration method. GS will write a response and discuss with AgWG and MWG
Alisha Mulkey | MDA | Global targets for crop have ranged from approximately 47 lbs N (Beta 2) to 30 lbs N (Beta 3) with the final proposed target as 38 lbs N. Variability in target ranges have also occurred for the pasture global land use, as well as P targets for both crop and pasture. However, P6 improved input estimations show significantly less absolute pounds of N and P throughout the calibration period (Figure 1, Jeff Sweeney 062917). Please provide the justification for selection of the global crop target given the decreased agricultural inputs, and in the context of STAC’s comment on the circular logic of the global target’s use (Draft report Nov. 2016). | 2017-07-13 | Gary Shenk | Modeling Workgroup | Decision of modeling workgroup. GS will write a response and discuss with AgWG and MWG
Alisha Mulkey | MDA | Global target estimations were made for above-RIM locations only to calculate a land use target rate. These target estimates were subsequently applied to below-RIM locations. Is this an appropriate assumption given the lack of observed data and hydrologic connectivity of areas below-RIM stations? | 2017-07-13 | Gary Shenk | Modeling Workgroup | Decision of modeling workgroup. GS will write a response and discuss with AgWG and MWG
Alisha Mulkey | MDA | Local land use targets were provided with the release of the P6 documentation((https://archive.chesapeakebay.net/modeling/Phase6/Draft_Phase_6/Documentation/10C%20Targets%20Draft%20Final.csv). Local targets are those loads reaching the EOSS that account for sensitivity to inputs; however, variability among all watershed segments is approximately +/- 2 lbs N and less than 1 lb P for most agricultural land uses. This suggests that inputs across the watershed (both nutrient inputs and soil P) are largely homogenous and variation in load delivery, beyond EOSS, is attributed to transport mechanisms (e.g. Stream-to-River factors). Please explain a jurisdiction’s ability to affect meaningful change in water quality if load delivery is primarily attributed to transport factors (e.g. percent catchment in Piedmont carbonate)? And secondly, do the local targets sufficiently represent states (such as Maryland) who have greater documented nutrient management adoption (extent and time) than other jurisdictions? | 2017-07-13 | Gary Shenk | Modeling Workgroup | Results of partnership decisions. GS will write a response and discuss with AgWG and MWG
Alisha Mulkey | MDA | 7. Crop uptake is a N sensitivity component with N specie fractions (NO3, NH3, and organic N). Why are sensitivity factors for NO3 uptake negative values, while NH3 uptake and organic N uptake are positive values according to the P6 documentation? | 2017-07-13 | Gary Shenk | Modeling Workgroup | Results of partnership decisions. GS will write a response and discuss with AgWG and MWG
Alisha Mulkey | MDA | 6. P6 is using a hybrid of crop uptake (minor crops) and crop removal (major crops), depending on the crop type. Pasture uptake values were also observed as much too low. Discussion of this decision and implications to loads were brought to the AMS 22 June. It is agreed absolute values may have minimal effect; however, the relative difference between land uses may be important in regions limited to major crops. Additionally, a consistent choice of uptake or removal should be used. | 2017-07-13 | Matt Johnston | AMS
Alisha Mulkey | MDA | 8. Livestock to pasture ratios (animal per acre pasture) are unexplainably high in Kent County, MD. A review of the 2012 Ag Census confirms the total number of livestock (8,743 cows) with approximately 50% being dairy livestock. Pasture acres in the county are minimal. However, MDA provided assumptions to CBP indicating that dairy are largely confined throughout the year rather than on pasture. Please confirm that the livestock animals in Kent County were properly distributed between pasture, barnyard, and riparian pasture | 2017-07-13 | Matt Johnston | CBPO Staff
Alisha Mulkey | MDA | 9. A scenario request was made to CBP to demonstrate the benefits of core NM. Staff presented prelim results to AgWG on 29 June (slide 8, http://www.chesapeakebay.net/channel_files/24799/amsupdateagworkgroup06292017.pdf) suggesting measurable results from increased NM acres. However, state efforts (Maryland & Delaware) have not been able to replicate these results in CAST. Maryland has found modest decreases in N and P (<1%) with an additional 10% BMP implementation. Additionally, N loads (and some P) have actually increased in some counties with additional NM BMP coverage. Please provide the raw scenario files as shown to AgWG, and explain the CAST outcomes where increasing BMP coverage results in greater nutrient loads? A similar effect has been found for increased Manure Transport. Maryland must be assured that manure-rich counties (e.g. Somerset) with increased NM and/or Manure Transport, but without changes to broiler populations, would see decreases in loads | 2017-07-13 | Matt Johnston | CBPO Staff
Alisha Mulkey | MDA | 10. Maryland full-season soybeans according to Tableau indicates an average of 130-140 lbs N applied annually, removal as 107-120 lbs N annually, and fixation rates similar to application rates. Additionally, previous discussions from Meissinger et al. cite ~ 45 lbs PAN contributed from the soil. Please explain the relationship between all legume parameters relative to potential losses of N? | 2017-07-13 | Matt Johnston | CBPO Staff
Alisha Mulkey | MDA | 11. A preliminary review of riparian pasture loads (N and P) look high. Staff is still conducting a review of BMP credit coverage, but may raise additional questions with CBP on the findings | 2017-07-13 | Matt Johnston | CBPO Staff
Alisha Mulkey | MDA | 12. During conversation with CBP, MDE, and MDA, it was explained that crop needs for 2012 were met using actual data and to establish a new crop need baseline for later years (without actuals). For example, if crop applications were 110% of need in 2012, the new baseline for crop need in 2013 was set to 110%. Please confirm if this is an accurate explanation of the model assumptions? If yes, please explain the rationale for setting a new crop need baseline that is counter to agronomic recommendation? | 2017-07-13 | Matt Johnston | CBPO Staff
Greg Busch | MDE | Mixed Open sediment loads unreasonably high | 2017-07-17 | Gary Shenk | CBPO Modeling Staff | CBPO Staff agrees. C factor used not consitent with documentation. Will be revised in final
Dave Montali | WV DEP | My evaluation of model land use indicates an overrepresentation of “turf” in contrast to “mixed open” across the WV Potomac watershed. For the West Virginia Potomac basin, mixed open constitutes only 25% of the combined area of mixed open, turf, and tree canopy over turf. The rate varies by county within the range of 12 to 53%. There are clearly classification issues, and more importantly, the overrepresentation of turf could have an adverse impact on the target process. There is no difference between NA and E3 for mixed open. For turf, E3 includes substantive application of forest buffers, grey infrastructure improvements, nutrient management, and stormwater runoff reduction | 2017-07-19 | Peter Claggett | LUWG | Not likely to be an easy fix. Would take 2 months after the 2025 projections are delivered.