## AGWG Panel Queue
Status of Agricultural BMP Expert Panels
Sector | BMP(s) to be Reviewed | BMP Status | Potential Resource Allocation | Status | Notes
Ag | Phase 5 Cover Crops |  | Tetra Tech | ü | Completed in 2014
Ag | Phase 5 Conservation Tillage |  | Tetra Tech | ü | Completed in 2014
Ag | Non-Urban Stream Restoration | E | TBD | ü | Agricultural stream restoration included in urban stream restoration report
Ag | Karst Sinkhole Grass Buffers | N | Tetra Tech | û | WV withdrew request
Ag | Phase 5 Nutrient Management |  | Tetra Tech | In progress | Expert Panel developing recommendations
Ag | Manure Treatment Technologies | N | Virginia Tech | In progress | Expert Panel developing recommendations
Version: 5/14/15 | Shoreline Erosion Control |  |  | In progress | Expert Panel developing recommendations (CWP)
Ag | Phase 6 Nutrient Management | E | Tetra Tech | In progress | Stakeholder meeting to be scheduled this summer
Ag | Phase 6 Conservation Tillage | E | Tetra Tech | In progress | Stakeholder meeting to be scheduled this summer
Ag | Phase 6 Cover Crops | E | Tetra Tech | In progress | Stakeholder meeting to be scheduled this summer
Ag | Manure Injection / Incorporation | I/N | Tetra Tech | In progress | Stakeholder meeting to be scheduled this summer
Ag | Animal Waste Storage Facilities / Poultry Heavy Use Area Concrete Pads | E/N | Virginia Tech | In progress | Stakeholder meeting to be scheduled in early 2016
Ag | Cropland Irrigation Management | I | Tetra Tech | Tier 2 | AgWG has approved panel charge and submitted member nominations. The AgWG will be asked to approve proposed panel membership in March, 2016.
Ag | Agricultural Stormwater Structures / Nursery and Greenhouse Runoff Capture and Reuse | N/I | Tetra Tech | Tier 2 | AgWG has approved panel charge and submitted member nominations. The AgWG will be asked to approve proposed panel membership in March, 2016.
Ag | Agricultural Ditch BMPs | N | TBD | Tier 3 | The AgWG gave approval to the proposed scope in February, 2016. The proposed panel membership will be put in front of the AgWG for approval in March, 2016.
Ag | Animal Mortalities Facilities-Freezerrs Interim BMP Efficiency | N | TBD | Tier 3 | The AgWG approved the proposal for the interim BMP efficiency during their February 2016 meeting.
| New requests for 2016 |  |  | Status | Notes
Ag | Vegetative Environmental Buffers | I | TBD | Potential Tier 3 | MD request
Ag | Nutrient Sorbing Materials in Agricultural Ditches / Bioreactors | N/I | TBD | Potential Tier 3 | MD request
| Non Poultry Mortality Composters |  |  | Potential Tier 3 | MD request
| Biofilters |  |  | Potential Tier 3 | MD request
| Poultry mortality management |  |  | Potential Tier 3 | DE request
Others?

## Panel Membership
BMP Panel Membership (2016)
Nutrient Management: | Frank Coale | UMD, Panel Chair
| Lindsey Gordon | CRC, Staff support
| Mark Dubin | UMD, Coordinator
| Matt Johnston | UMD, Modeling Team Representative
| Chris Brosch | DDA, WTWG Representative
| Jack Meisinger | USDA, ARS
| Deanna Osmond | North Carolina State University
| Doug Beegle | Penn State University
| Tom Fisher | UMCES
| Quirine Ketterings | Cornell
Manure Injection/Incorporation: | Curtis Dell | USDA ARS, Panel Chair
| Lindsey Gordon | CRC, Staff support
| Mark Dubin | UMD, Coordinator
| Chris Brosch | DDA, WTWG Representative
| Jeff Sweeney | CBP EPA, Modeling Team Representative
| Arthur Allen | UMD - Eastern Shore
| Dan Dostie | USDA NRCS
| Robb Meinen | Penn State University
| Rory Maguire | Virginia Tech
Cover Crops: | Ken Staver | UMD, Panel Chair
| Lindsey Gordon | CRC, Staff support
| Mark Dubin | UMD, Coordinator
| David Wood | CRC, Modeling Team representative
| Jason Keppler | MDA, WTWG Representative
| Charlie White | Penn State University
| Jack Meisinger | USDA ARS
| Paul Salon | USDA NRCS
| Wade Thomason | Virginia Tech
Conservation Tillage: | Wade Thomason | Virginia Tech, Panel Chair
| Lindsey Gordon | CRC, Staff support
| Mark Dubin | UMD, Coordinator
| Bill Keeling | VA DEQ, WTWG Representative
| Jeff Sweeney | CBP EPA, Modeling Team Representative
| Bill McCollum | DuPont Pioneer
| Kevin Ganoe | Cornell
| Dale Gates | USDA NRCS
| Mark Reiter | Virginia Tech
| Sjoerd Duiker | Penn State University
Animal Waste Management Systems: | Shawn Hawkins | U. of Tennessee, Panel Chair
| Jeremy Hanson | VT, Coordinator
| Jonathan Moyle | UMD
| Bill Brown | UD
| Peter Vanderstappen | PA NRCS
| Doug Hamilton | OK State
| Mark Risse | UGA