## Public Access Workplan
Outcome: Public Access Site Development
Goal: Public Access
Outcome: By 2025, add 300 new public access sites, with a strong emphasis on providing opportunities for boating, swimming and fishing, where feasible
Long term Target: 300 x by 2025
2 year Target: 95 by 2017
Management Approach 1: Track progress towards the 300 new sites goal: At the end of each calendar year partners will compile a list of all new public access sites opened in their jurisdiction during the year. These sites will be tallied and tracked by NPS and counted towards the 300 new sites by 2025 goal.
Key Action | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Report on new public access sites opened each year. | New public access sites opened in watershed with target of 20 per year. | All state and federal partners in Public Access Work Group. | Regional | Reports filed in January for the proceeding calendar year State agency partners have reported that their staffing and operational budgets have been greatly reduced and in one case operation funding beyond staff salary eliminated; thereby reducing ability to support this activity.
Total
Identify new potential public access sites each year that would fill in system gaps and contribute towards goal. |  | All state and federal partners in Public Access Work Group. | Regional | Reports filed in February for the proceeding calendar year State agency partners have reported that their staffing and operational budgets have been greatly reduced and in one case operation funding beyond staff salary eliminated; thereby reducing ability to support this activity.
Management Approach 2: Make funding for public access a priority: Sustain funding for development of new public access sites and maintenance of existing sites, including maintenance dredging of small channels. Relevant state and federal funding or matching grant programs should consider targeting or giving bonus points for projects that include new public access sites. For example, the National Park Service Chesapeake Office will continue to prioritize funding for public water access site development through its financial assistance awards.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Develop new public access sites by targeting financial assistance programs as appropriate. | Evidence of grant/financial award programs with application criteria supporting public access development. | State and federal partners who admininister appropriate financial assistance awards programs (This list includes VA DCR, VA DGIF, PA DCNR, MD DNR, NPS, USFWS, WV DNR, NY DEC, DE DPR and DC DOE | Regional | State agency partners have reported that their staffing, operational budgets, and state funds for local project assistance have seen significant reductions, thereby, reducing their ability to support this activity.
Total
Maintain and upgrad public access sites on DoD instalations. | Maintian public access sites on DoD instalations where site security allows. | DoD | DoD Instalations where appropriate.
Total
Management Approach 3: Establish a process that ensures public access is considered in the planning of all appropriate transportation projects: Many road projects across or adjacent to streams or rivers could provide public access opportunities. Where they do not yet exist, a state’s recreation and resources agencies and its department of transportation (DOT) should consider establishing an MOU or other appropriate
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Develop as needed MOU/agreements with state DOTS for public access development in conjunction with road projects. | A defined process, where one does not exist, for maximizing the development of new public access sites in harmony with road and bridge construction projects. | The state agnecies which have primary responsibility for their state's public access planning and develoment. (This includes VA DCR, VA DGIF, VDOT, MD DNR, MDOT, PA DCNR, PDOT, WV DNR, WV DOT, NY DEC, NY DOT, DE DPR and DE DOT) | Regional
Total
Total
Management Approach 4: Enhance Public Access for a Diverse Population: As the population of the watershed grows, it becomes increasingly diverse with a population containing a broad range of ethnic, language and cultural backgrounds. As the makeup of the population changes, so has the way in which the various groups utilize and access the resource. If we are to continue to build strong support for the care and conservation of the Bay, it is important that all segments of the population have reasonable access. Actions to accomplish this include looking at gaps in types of access and how it relates to the various user populations in our urban areas. It includes looking at underserved populations and determining what may be needed to enhance their access opportunities. To be successful the Bay Program partners need to honor the culture, history and social concerns of local populations and communities and include a wide range of people and diverse groups in our decision making processes. Enhancing public access for diverse populations may also involve informational and programmatic shifts that target minority and underserved populations. This is becoming particularly true as it relates to informational signage at public access sites. Increase the effectiveness of existing public access sites by better communicating their location through improved signage and online resources. Such signage, whenever possible, should use universal symbols and be in the languages of the primary user to develop a more diverse user population.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Improve access to and increase amount of open green space, with specific emphasis on currently underserved neighborhoods and communities | Identify new access sites to meet the needs of a diverse population (Focus areas include local and regional greenways, city parks, restored urban stream corridors and street trees and urban forests ) | Greater Baltimore Wilderness coalition equity work group | Greater Baltimore area | Demand for public access in urban centers
| Increase connectedness of existing access sites, making them more accessible to urban populations | Greater Baltimore Wilderness coalition equity work group | Greater Baltimore area
Total
Create a visual of current and proposed access sites and compare it to Environmental Justice Screen which is an EPA mapping tool with communities and environmental justice sites | Completion of visual evaluation tool to potentially show correlation of access to areas of potential need related to diverse communities. | This project would be acconplished through a cooperative effort involving NPS Chesapeake, Bay Program and EPA.
Total
Management Approach 5: Carry out and support more detailed assessments and project design for potential sites: Most of the over 400 potential new public access sites identified in the plan require more detailed assessments and construction designs prior to implementation. Pre-planning and design of public access sites is a key step in their future development. This is an area in which funding is needed. Agencies at all levels should provide, within resource capabilities, technical assistance and funding for site analysis and design.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Provide technical assistance in site assessment, pre-planning, project design, and compliance/permitting to local access site development partners | Within resource limitations, federal and state staff provide assistance to local partners when opportunities are identified. | All state and federal partners that are involved with the Public Access Working Group | Regional | State agency partners report that their staffing and operational budgets have been greatly reduced and in one case eliminated; therefore support for this activity has been significantly reduced.
Total
Total
Management Approach 6: Fill strategic gaps in access along water trails: NPS will work with partners to identify, prioritize and develop sites that fill public access gaps along the Captain John Smith Chesapeake National Historic Trail, Star-Spangled Banner National Historic Trail, Potomac Heritage National Scenic Trail and recognized water trails throughout the watershed. This will also include efforts to find and develop sites to support boat-in primitive camping along the trails.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Develop new public access sites that fill gaps and support boat-in primitive camping along the trails by targeting financial assistance programs as appropriate. | Evidence of grant/financial award programs with application criteria supporting public access development projects that fill gaps and support boat-in primitive camping along the trails. | State and federal partners who admininister appropriate financial assistance awards programs (This list includes VA DCR, VA DGIF, PA DCNR, MD DNR, NPS, USFWS, WV DNR, NY DEC, DE DPR and DC DOE) | Regional | Several state agency partners report that their state appropriated grant budgets have been zereod out; therefore there are greatly reduced funds in place to support financial assistance programs.
Total
Develop new public access sites that fill gaps and support boat-in primitive camping along the trails. Target Youth Conservation Corps to implement smaller projects as appropriate. | Evidence of appropriately directed YCC projects, within the overall program scope of work, that support public access development projects that fill gaps and support boat-in primitive camping along the trails. | State partners who admininister appropriate Youth Conservation Corps programs. | Regional | Funding by both federal and state agencies is dependent on approprations and subject to change yearly.
| Public access site development objectives are incorporated into CAJO Segment Implementation Plans as these plans are developed to assist in strategic public access development in devleopment of the trails. | NPS - Chesapeake | Regional
Total
Management Approach 7: Further examine urban public access issues and needs: Recognizing the complex factors associated with expanding access in urban communities, governments at the local, state and federal levels should support and pursue studies assessing specific urban access issues and needs.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Total
Total
Management Approach 8: Work with private sector funders to develop access: Many companies and foundations often have objectives that can be advanced through partnerships to develop public access sites and facilities. Public access managers and advocates should actively work with private sector funders on access projects.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Total
Total
Management Approach 9: Engage in hydropower relicensing processes to expand public access: Relicensing of existing hydropower projects provides significant opportunities for expanding access to the water. Local, state and federal agencies should participate in re-licensing processes to make the case for specific public access projects as a part of new license agreements.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
State agency partners will be involved in any major hydro project relicensing when they occur in their state. Specific actions can be identified in future plans as appropriate.
Total
Total
Management Approach 10: Explore options for resolving railroad crossing liability: Railroads along rivers—and associated liability concerns over track crossings—limit water access. Some states have indemnified railroads from liability at at-grade crossings for public access purposes, but it is suggested that federal action to limit liability may be needed to address the railroad companies’ concerns.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Total
Total
Management Approach 11: Explore potential for additional access on public lands: Management objectives and practices on public lands may not account for recent changes in access needs and opportunities. As circumstances permit, managers of public lands fronting streams and rivers should re-evaluate these lands’ public access potential. This can occur through regular master planning processes or as ad hoc assessments. When new opportunities are identified they should be included in the properties’ master plan and scheduled for development as soon as resources allow.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
As a part of on going planning and update cycles agency partners will evaluate the potential of additional public access opportunities on lands under their control. When site master plans or resource management plans are updated, the potential for additional public access will be evaluated and included in the new plans as appropriate. Federal and state agency partners in the water shed. Region Opportunities will be ongoing through 2017 within agencies's resource, funding and management constraints. Absorbed as part of agency operation costs. N/A Planning is contingent on scheduled review cycles as well as staff limitations and funding.
Total
Total
Management Approach 12: Managing land control for water access using various instruments: Gaining control of water access sites can be accomplished using several “land or site acquisition” techniques or instruments. Land control can be achieved through fee simple acquisition of the land, recreational easements, leases and cooperative agreements. Even when sites are purchased in fee simple caution must be exercised to be sure the property does not contain restrictions that could make it difficult to achieve its intended use. Easements, leases and agreements should clearly state the uses that will be allowed and provided for on the property. In addition, they must clearly state the terms of use.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Total
Total
Management Approach 13: Prevent loss of access on public rights-of-way: Over the course of many decades roads leading to the water’s edge for uses such as steamboat docks, ferrys or for other reasons have been abandoned as a part of the road system when newer facilitates/infrastructure was developed. Many of these rights-of-way over time have been taken over by neighboring property owners or simply abandoned. It is important that each jurisdiction maintain control of such roads and rights-of-way since they can provide public access. Where clear legal grounds exist, those that may have been lost to other uses should be reclaimed.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Total
Total
Management Approach 14: Incorporate identified proposed public access sites and actions in key plans: Elements of the Chesapeake Bay Watershed Public Access Plan, including potential new public access sites and key actions, should be incorporated as appropriate into major state and local outdoor recreation and open space planning documents, such as Statewide Comprehensive Outdoor Recreation Plans (SCORPs) and local land use plans. Local units of government are encouraged to incorporate potential new public access sites and policies in local comprehensive and capital improvement plans
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Total
Total
Management Approach 15: Climate Change: As we move toward achieving the Chesapeake Bay Public Access goal we must identify how planning and implementation can be adapted to address climate change and sea level rise projections
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Total
Total
Management Approach 16: Fully address accessibility at public access sites: Public access sites are subject to federal and state standards and guidelines for ensuring access by a population with diverse physical capabilities. Yet it is not always clear how some of these guidelines may apply, particularly to boating access sites. NPS should work with its partners to clarify approaches to addressing accessibility needs
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Establish as a condition of financial assistance awards, the development of new public access sites in compliance with accessibity standards and guidelines to ensure access by a population with diverse physical capabilities. | Evidence of grant/financial award programs with requirement of compliance with accessibity standards and guidelines to ensure access by a population with diverse physical capabilities. | NPS- Chesapeake and financial assistance recepient(s). | Regional
Total
Total
Management Approach 17: Build opportunities for citizen stewardship- Many public access sites are remote from regular maintenance staffs. Communities, user organizations, water trail managers and others should work to develop volunteer citizen stewardship programs to care for and maintain specific access sites.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Total
Total