## SAV
Outcome: Submerged Aquatic Vegetation
Goal: Sustain and increase the habitat benefits of SAV (underwater grasses) in the Chesapeake Bay.
Outcome: 130,000 acres of SAV by 2025
Long term Target: 185,000 acres of SAV Bay-wide
2 year Target: 90,000 acres of SAV by 2017
Management Approach 1: Restore Water Clarity in the Chesapeake Bay
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Determine cause of declining water clarity trends in Chesapeake Bay |  | Chuck Gallegos (SERC), Richard Zimmerman (ODU) | Chesapeake Bay
Totals
2. Achieve water clarity/SAV standards in areas designated for SAV use | WIP Phase II key initiatives | Bay States (DE, MD, NY, PA, VA, WV) | Chesapeake Bay | by 2025
| Develop WIP Phase III | Bay States (DE, MD, NY, PA, VA, WV) | Chesapeake Bay | 2018
Totals
3. Improve SAV component of shallow water model |  | Chuck Gallegos (SERC), Richard Zimmerman (ODU), Ken Moore, Nancy Rybicki, SAV Workgroup | Chesapeake Bay
Totals
4. Target oyster restoration in areas that have historically supported both oysters and SAV to maximize the synergistic effect of both on water clarity. | 147 acres of restored oyster reef in the Tred Avon River | USACE - Baltimore | Tred Avon River | 2018 | $11.4 Million | $11.4 Million
Totals
gap $0.00
Management Approach 2: Protect existing Submerged Aquatic Vegetation in the Chesapeake Bay
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1.Evaluate and enhance current statutes and regulations that protect existing SAV in the Chesapeake Bay. | 1) ASSEMBLE. Assemble all current statutes and regulations that protect existing SAV in the Chesapeake Bay from human activities that contribute to its direct loss. | SAV Workgroup | Chesapeake Bay | 3 mo post start date | $20,000 - $30,000 | 0 | not funded
| 2) REVIEW. Review current statutes and regulations for both strengths and weaknesses, with particular attention paid to consistency of protection between Bay states, loopholes, unintended detrimental consequences related to the prioritized protection of other Bay resources, and general inadequacies. |  |  | 6 mo post start date
| 3) COMPARE. Review and summarize regulations designed to protect SAV, and their efficacy, in other states, such as Florida and Washington. |  |  | 9 mo post start date
| 4) RECOMMEND. Make policy recommendations based on review of current Chesapeake Bay state regulations compared to other state regulations that may be more thorough and successful. |  |  | 1 year post start date
Totals
gap $20,000 - $30,000
2. Determine the extent to which watershed land-use impacts SAV survival and growth. | 1) Modeling component to identify watershed effect | SERC | Whole Bay | December 2016?
| 2) Field component to identify local effect | MD DNR (NOAA grant) | 24 sites throughout the Bay | December 2016 | 125000 | $125,000 (NOAA) | 0
Totals
gap $0.00
3. Determine the extent to which shoreline armoring influences existing SAV abundance and distribution | 1) Modeling component to identify watershed effect | SERC | Whole Bay | December 2016?
| 2)Field component to identify local effect | MD DNR | 24 sites throughout the Bay | December 2016 | 125000 | 125000 | 0
| 3) Field study to determine the effect of beneficial use/island restoration projects on SAV | MD DNR / FWS | Smith Island / Martin State Wildlife Refuge | 2017?
| 4) Field study to determine the effect of beneficial use/island restoration projects on SAV | MD DNR / FWS | Eastern Neck | 2017?
Totals
gap $0.00
4. Determine the extent to which dock construction and placement influences existing SAV survival and growth. | [6 empty] | Effects have been established/determined in other states. Need better regs. See #1.
Totals
5. Determine the extent to which living shorelines impact SAV abundance and distribution. |  | MD DNR | Chesapeake Bay | 2017 |  |  | proposals in place. Funding unknown.
Totals
6. Manage invasive species (both plant and animal) that are considered detrimental to existing SAV populations (ie. Water chestnut, Mute swan). | Control Mute Swans | MD DNR | MD | ongoing
| Control Mute Swans | FWS | MD | ongoing
| Control Mute Swans | NPS | MD/VA | ongoing
| Manage Trapa natans | MD DNR | MD | ongoing | 3000 | 3000
| Manage Trapa natans | DGIF | VA | ongoing
Totals
7. Continue Bay-wide annual SAV aerial monitoring to ensure up to date data regarding the extent and recovery of SAV in the Chesapeake bay and its tributaries. This data is essential to the protection of existing SAV. | Collect, process, and analyze aerial SAV imagergy data throughout Chesapeake Bay and it's tributaries; report results. | VIMS | DC, MD, VA | annual |  | 85464 | extensive and on-going funding crisis. Project may be discontinued if not resolved.
|  | EPA |  |  |  | 264306
|  | VA DEQ |  |  |  | 65455
|  | VA CZM |  |  |  | 48000
|  | NOAA |  |  |  | 16000
|  | MD DNR |  |  |  | 36000
Totals
gap: $150,000
8. Determine the economic value of SAV ecosystem services. Knowing the economic value of a resource is vital to its long-term protection. | TS III | Lisa Waigner (UMCES) | Chesapeake Bay |  | 5500 | 5500 | 0
| TS III | Chris Kennedy (GMU) | Chesapeake Bay |  | 5500 | 5500 | 0
| Evaluate total value of ecosystem services in MD | Elliott Campbell (MD DNR) | MD
Totals
9. Continue long-term monitoring of "sentinel" SAV sites throughout the Bay |  | MD DNR | MD, seven long term transect sites | annual
|  | VIMS | Virginia, eastern and western shores | annual
| monthly monitoring April - October | VIMS | York River | on-going
Totals
Management Approach 3: Restore Submerged Aquatic Vegetation in the Chesapeake Bay
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Plant, at minumum, 20 acres of Sav seeds and propagules in appropriate high water quality/clarity areas each year until goal is reached. | Collects seeds, store seeds, disperse seeds | MD DNR | Meso and Oligohaline portion of Bay | annual | ~$5000 |  | dependent on seed collection, storage, weather, etc.
| Collects seeds, store seeds, disperse seeds | VIMS | Polyhaline portion of Bay/mostly James | annual | ~$5000 |  | dependent on seed collection, storage, weather, etc.
Totals
2. Restore 1715 acres of remote island habitat at Poplar Island to create suitable conditions for SAV growth. | ? | USACE- Baltimore | Poplar Island, CB | 2020? Ask to specify for two year goals | 1.2 billion | 1.2 billion | they're all set
Totals
3. Identify the latest modeling techniques and use up to date scientific information to determine the most favorable locations for active SAV restoration. | develop lab test to test sediment and water quality for restoration site suitability | Steve Ailstock (AACC) | Magothy River; Chesapeake Bay | continuous work - no end date
Totals
Management Approach 4: Enhance Research, Citizen Involvement, and Education in the Chesapeake Bay watershed
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Increase the knowledge base regarding the biology and ecology of under-studied tidal fresh, oligohaline, and mesohaline SAV species. |  | UMCES - HPL (Kemp and Gurbisz) | Susquehanna Flats | Fall 2011 - Spring 2016 |  | funded by MD Sea Grant
VIMS (K. Moore)
AACC (Ailstock)
Totals
2. Increase understanding of SAV community dynamics and response to stressors. |  | SERC (Weller and Patrick)
|  | UMCES - HPL (Kemp and Gurbisz) | Susquehanna Flats | Fall 2011 - Spring 2016 |  | funded by MD Sea Grant
UMCES - CBL (Harris)
Totals
3. Determine the ideal size of restoration plots to maximize SAV bed persistence, further increasing the understanding of the role of smaller sub populations in SAV recovery. | [6 empty] | This work needs to be done…partner currently unidentified.
Totals
4. Determine whether success rate increases if a primary colonizing species is planted first, followed by a climax species. |  | AACC (Ailstock)
UMCES - HPL (Kemp and Murray)
Totals
5. Determine the conditions under which planting multiple species in the same location are likely to increase the chances of population survival. |  | AACC (Ailstock)
Totals
6. Identify and select species with characteristics that maximize ecological function. |  | UMD (Neel)
UMCES - AL (Engelhardt)
Totals
7. Determine the conditions under which planting multiple genotypes and locally adapted genotypes are likely to increase chances of population survival. |  | UMD (Neel)
UMCES - AL (Engelhardt)
Totals
9. Determine connectivity among source beds that act as a source of seed/genetic material over varying spatial scales. |  | UMD (Neel)
UMCES - AL (Engelhardt)
UMCES - CBL (Harris)
| boats as propagule vectors for gene flow/ genetic signature of pops surviving vs. not surviving | UVA (Bricker) | polyhaline/VA
Totals
10. Determine at what density and spatial arrangement SAV should be planted to maximize growth and survival. |  | UMD (Neel)
UMCES - AL (Engelhardt)
AACC (Ailstock/Norman)
MD DNR (Lewandowski)
Totals
12. SAV Modeling effort in the coastal lagoons of the Delmarva, with implications for restoration and climate issues in general. | Enhance Virtual Eelgrass Model, an individual-based model simulates population impacts of temperature, nutrients, light changes, and sediment on clonal growth of Zostera marina.Reproductive mechanisms to simulate seed germination and seedling growth will also be included. | Jessica Foley (MS at UMCES) and Lora Harris (UMCES-CBL) | Delmarva, with regional and national implications | 2016-02-01 | 250000 | 250000
Totals
13. Complete and publish the third Technical Synthesis of research regarding SAV in the Chesapeake Bay. This document will highlight everything that is known, to date, regarding SAV in the Chesapeake Bay. | 1. Identify chapters/topics necessary. 2. Assign chapter authors. 3. Draft and review. 4. Finalyze. 5. Publish as TS III. 6. Publish as individual articles. | SAV Workgroup | CB Watershed | June, 2016 | 100000 | 100000 | brain fatigue
14. Develop a communication strategy that enhances the public's knowledge of and appreciation for SAV in the Chesapeake Bay, similar to the models used to advance oyster and other wildlife restoration efforts. | (Market the importance of SAV through websites, informational signage at ramps, etc.) | SAV Workgroup | Bay-wide
| Annual CB Report Card | UMCES - IAN | Bay wide with individual segments scored
Totals
15. Continue, or reinstate, Bay Grasses in Classes and Bay Grasses for the Masses Programs where they are still active. | Continue…. | CBF (BGftM) | Virginia
| Re-instate… | MD DNR | MD portion of Bay
Totals
**Note: As a member of the Chesapeake Executive Council and a signatory to the Chesapeake Bay Watershed Agreement, the Chesapeake Bay Commission (CBC) functions as the legislative arm of the Chesapeake Bay Program working within Maryland, Pennsylvania and Virginia and at the federal level to identify specific Bay management concerns requiring intergovernmental coordination and cooperation. CBC makes recommendations to the federal, state and local governments on legislative and administrative actions necessary to effectuate coordinated and cooperative management for the Bay watershed. The Commission will work collaboratively with Bay Program partners to identify legislative, budgetary and policy needs to advance the key actions identified in this outcome and to anticipate those needed in the future. The CBC’s work is supported by the annual appropriations of its three member states totaling $675,000 and is, on occasion, supplemented by project-specific grants.
Note on G55: blandry: I'm not sure how to deal with this….
Note on F56: blandry: all without direct costs