## Sheet1
Toxic Contaminants Policy and Prevention Outcome Effective date: 1/1/2016-1/1/2018
Goal: Toxic Contaminants
Outcome: Policy and Prevention
Continually improve practices and controls that reduce and prevent the effects of toxic contaminants below levels that harm aquatic systems and humans. Build on existing programs to reduce the amount and efffects of PCBs in the Bay and watershed. Use research findings to evaluate the implementation of additional policies, programs and practices for other contaminants that need to be further reduced or eliminated.
2 year Target: Completion of performance targets related to key actions
Partner contributions to 2 year target: As-listed under performance targets
Management Approach 1: Regulatory Approaches
Key Action | Performance Target(s) | Partners
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible
Identify responsible partner for each step.
|  |  | Status (Updated: 9/14/16) | Status (updated 12/11/17)
1. Continue jurisdictional monitoring programs for PCB occurrence to assess need for new local TMDLs and progress related to reducing PCB loads. | Continue statewide fish tissue sampling for PCBs at 125 sites. Not all are in the Susquehanna Drainage. These are rotated to new locations every year. | PA DEP
| Estuarine probabilistic monitoring which includes a list of PCB congeners in sediment; | VA DEQ |  | 42 sites were sampledwithin minor tidal tributaries and embayments of the CB Watershed, 35 of which were probabalistic and 7 of which were targeted, cromprising a special study within the Potomac River embayments. 3 of the targeted sites weree within MD's Potomac River waters, off the mouth of VA embayments. An additional 11 probabalistic sites occured in coastal Delmarva waters, and 4 in the Back Bay and North Landing River waters of the Abermarle Sound drainage. Sediment chemistry, sediment toxicity, and benthic community samples were collected at all 57 sites. Weight of evidence measurements for aquatic life use will be conducted for all sites, based on the sediment quality triad.
| Monitor all main stem tributaries to Bay listed as impaired. Fish PCB monitoring used on an as needed basis to monitor status; |  | Fish samples were collected in the lower section of the non-tidal James River, the tidal James River, Elizabeth River and Rappahannock River (from Fredisckburg to the mouth). Results not yet available. | Sampling design plan under development. Some stations will be placed in the non-tidal portion of the James River.
| TMDL source investigation studies included where PCB TMDL being developed. Includes sediment monitoring and low level water column samples. |  | Sediment and water source investifation saples were collected in Mountain Run (tribuatary to the Rappahannock River) as part of the TMDL development (source ID and model development). 2016: a handful of PCB water samples were collected at the fall line in the James River for purposes of model development for the tidal James River TMDL. | A study plan is current;y under development for the non-tidal, middle and upper James River segments.
| Conduct a PCB monitoring survey on pre and post-ENR WWTPs in Maryland to determine if there is an increase in removal effciency from the ENR treatment technology. Conduct a second round of sampling on the two plants that are pre-ENR once the upgrade goes online. | MDE | Three sample collections (24 influent and effluent samples) have been conducted at four WWTPs in MD (Back River, Cox Creek, Mattawoman, and Elkton). A fourth sample collection will be conducted at Back River and Cox Creek WWTPs (8 influent and effluent samples) once the facilities' ENR processes come online, which is anticipated by the end of the year. Next Steps: The samples are being analyzed by Texas A&M using EPA method 1668. A final data report is expected Spring 2017. | The final round of sampleing remains on hold as the Back River and Cox Creek WWTPs ENR treatment processes have not been completed. The contract has been extended through December 2018.
| Continue annual PCB monitoring in support of PCB TMDL development. Monitoring includes collection of water column (non-tidal/tidal), sediment and fish tissue samples for PCB analysis to support the development of water quality models in establishing PCB TMDLs. |  | A monitoring survey has been completed in the Conowingo Pool to support development of a PCB TMDL. Sample collections have been completed and are currently being analyzed for PCBs by UMCES CBL. The monitoring survey included 48 sediment samples (bulk & porewater), 156 water column samples (surface and bottom water), 12 fish tissue composite samples, and 1 sediment core. A final data report is expected Spring 2017. A monitoring survey is currently underway in the non-tidal Potomac River to support development of a PCB TMDL. The monitoring survey includes 40 sediment samples, 112 water column samples, and 27 fish tissue composite samples. Next Steps: Sample collections will be completed by Spring 2017 and all samples will be analyzed for PCBs by UMCES CBL. A final data report is expected Fall 2017. | Tried to collaborate with other jurisdictions, but did not work out. The loweer Sus River TMDL will depend on what happens with the Conowingo Dam. Lower Sus is evereything below the dam. 2019--TMDL will be in place for PCBs for both lower Sus and Conowingo pool. Datasets that trigger changes in listings will be shared with the TCW. Have not seen a declining trend in Hg in young of the year but trends in Hg appar to be declining in Potomac main stem in older fish.
| Conduct toxic contaminant monitoring for the tidal waters of Aberdeen Proving Grounds (APG). |  | A toxic contaminant monitoring plan for APG is currently being developed. Next Steps: It is anticipated that monitoring will be conducted Spring – Fall 2017. The monitoring plan will include sediment and water column sampling which will be analyzed for metals, pesticides, SVOCs, mercury, and cyanide. Water column toxicity tests will be conducted using sheepshead minnows and water fleas. Sediment toxicity tests will conducted using amphipods. B-IBI analysis will also be conducted on sediment samples. The objective of this study is to identify specific toxic impairments within the system.
| Conduct an analysis of Bay-wide PCB concentration data to improve our understanding of PCB dynamics through-out the Bay mainstem and the influence of loadings from the Susquehanna River and C&D Canal. The project will also focus on approaches for developing a PCB TMDL to address the main stem segment listing in MD's portion of the Bay. | MDE and VIMS | MDE has contracted VIMS to conduct the analysis. The study is currently underway and will be completed by December 2017. | The study has been completed and a draft is currently undergoing review. It is anticipatd that the report will be available in March 2018
| Continue annual PCB fish tissue monitoring for MDE’s Fish Consumption Advisory Program to assign state-wide fish consumption advisories. The program also provides fish tissue data for MDE’s Environmental Assessments and Standards (EASP) and TMDL Programs to support Integrated Report listing assessment and TMDL development. | MDE | Fish tissue sampling was conducted in 2016 at 18 stations (72 composites) to support the consumption advisory program, IR assessment and TMDL development needs. Fish composite samples are being analyzed by UMBC for PCBs, Hg, and chlordane. Several species of fish were collected including white perch, channel catfish, and largemouth bass. It is anticipated the data results will be available Winter 2017 | Toxics data for fish tissue collected on 2016 is available for early 2018. fish tissue sampling was conducted in 2017 at 25 stations (56 composites) to support the consumption advisory program, IR assessment, and TMDL development needs. Fish composite samples are being analyzed by UMBC and UMCES for PCBs, Hg, and chlordane. It is anticipated that the data results will be available in winter 2018.
| Conduct fish tissue study. | DOEE (WQD-ESA). |  | Fish tissue study was initiated July 2017. Expected completion in July 2018.
Complete toxics monitoring on sediments in the Anacostia.
| Approximately every five years, West Virginia performs a statewide fish tissue assessment to inform both fish consumption advisory and 303(d) listing processes. Mercury and PCBs will be analyzed. | WV DEP
| Develop a QAPP to describe objectives, monitoring procedures and laboratory methods to be used to characterize toxics in the Delaware portion of the Chesapeake Bay drainage. | DE DNREC
Compile existing toxics data within the Delaware portion of the Chesapeake Bay drainage.
Collect up-to-date toxics data on surface water, surface sediment and biota within the Delaware portion of the Chesapeake Bay drainage.
Collect deep sediment cores from a depositional area in the tidal Nanticoke River. Radio-date and analyze for contaminants to provide pollution history.
Create priority list for sources in need of clean-up and restoration.
2. Continue local TMDL implementation utilizing to the extent possible the outputs of this strategy including data compilations, results of enhanced monitoring, guidance documents and local-level input | Potomac River PCB implementation - includes point sources and MS4s. Point sources that exceed WLAs will submit PMPs. | VA DEQ |  | PCB samples have been collected and analyzed from point sources that have been assigned WLA's in the Potomac PCB TMDL. A detrmination for the need for Pollutant Minimization Plans (PMPs) is forthcoming. Several MS4s are in the process of or have submitted PCB TMDL action plans which are under review within DEQ.
| Tidal James/Elizabeth Rivers – point sources that have not screened effluents using the low level method will be required to do so. Facilities that have screened their effluents and exceed their WLA will be required to submit PMPs. | VA DEQ |  | For the tidal James/Elizabeth River TMDL, a list of point sources has been developed for inclusion in the TMDL. For facilities that have not monitored as part of TMDL development, the initial step post TMDL development will be for them to collect as prescribed number of sample results to compated with the assigned WLAs. The list of davilitis includes municipalities, Inductrial Individual Permits, and Industrial Stormwater General Permits. Facility ffluents with existing loads that exceed WLAs will be asked to develop PMPs.
| Phase 1 MS4’s which have been assigned a WLA within a PCB TMDL requiring a PCB load reduction are required to develop a PCB Implementation Plan within one year of an approved TMDL. | MD MS4’s | MD SHA has submitted a PCB stormwater implementation plan to address their MS4 WLA in all currently approved PCB TMDLs. The plan is currently undergoing MDE review. SHA MS4 WLAs have been assigned in various PCB TMDLs including Back River, Baltimore Harbor, and Anacostia River. | Phase 1 MS4 Implementation Plans have been developed by Anne Arundel County for the Baltimore Harbor, Baltimoree County for the Bird/Gunpowder River, and Harford County for the Bush River in 2015-2017. Counties that havee submitted plans are currently developing monitoring programs to support PCB TMDL implementation.
| Finalize the District Consolidated TMDL Implementation Plan, and incorporate elements into District’s next MS4 Permit. | DOEE, DDOT, DGS, and Federal Landholders |  | The TMDL IP was finalized in August 2016; 5 year milestones from the IP have been used to inform the performance metrics in each draft of the District's next MS4 permit, which is expected to be finalized in early 2018.
| Implement stormwater BMPs and green infrastructure to meet TMDL IP’s first set of 5-year milestones. |  |  | Ongoing. DOEE is actively working to compile finalized collection of BMPs.
3. Develop guidance on integration of the various programs addressing toxics to reduce inconsistencies in analytical methods, target thresholds, and investigation and remediation approaches (e.g. extent to which risk assessment requirements under contaminated site regulations evaluate potential carcinogenic effects from fish consumption by comparing ambient surface water concentrations of PCBs with human health criterion used in site cleanups). | Make a recommendation that STAC (or other partner such as the Interstate Technology and Regulatory Council or ASTSWMO) assemble a workshop of experts to discuss the integration of analytical methods, target thresholds and investigation/remediation approaches to achieve consistency. | TCW | TCW will contact EPA Headquarters to see if similar analysis has been performed in the past. | TCW may have put in a proposal for a workshop, but if so it was not selected--no progress as of December 2017. Will consider inclusion and feasibility for completion in next round of MS and workplan.
| Develop a “white paper” based upon the outcome of the workshop (e.g. formation of an expert panel). | STAC/Other Partner
| Determine status of efforts to coordinate these processes at a national level and stay informed of/participate in those conversations. | TCW
4. Determine consistent implementation measures to use throughout the Bay watershed for tracking local TMDL development and implementation progress. | Develop maps to track locations where PCB TMDLs are active, under development, and needed. | CBP GIS team and Bay watershed jurisdiction GIS leads | Completed: http://arcg.is/1MxTvgm | 1/14/16; 3/9/16; 6/15/16;
Will reach out to jurs partners on TMDL and impairment status to assess whether information should be updated.
| Assess available information on identified management action implementation and determine next steps (e.g. status of npdes permits with regards to inclusion of PMP; MS4 action plans to ID potential IDDE connections to PMPs) | TCW and Bay watershed jurisdictions’ TMDL programs | TCW is working with EPA WPD to pilot an approach that would use the DMR database to identify whether permits are being updated to be consistent with established PCB TMDLs. Depending upon the permit cycle, permits should be updated within 5 years of TMDL establishment. | NPDES Permits and PMPs: Outcome was a memo on incorporating PMP approaches but not numeric effluent limitations. Follow up is needed to examine memo. Unsure if any progress made on ID of potential IDDE connection to PMPs. Will consider inclusion as a separate item for next workplan.
5. Determine whether the jurisdictions compile existing PCB outfall monitoring data for NPDES dischargers and assist with development of systems to compile all available information from governmental and academic organizations. This inventory will help determine whether there is a need for additional monitoring requirements to support TMDL development and implementation. | Reasonable potential analysis during permit reviews includes PCBs | PA
| Virginia has an Access Database used to store PCB data obtained from a wide array of matrices (sediment, water, effluent, etc.). The database structure, obtained from DRBC, was designed specific to storing data analyzed and reported using method 1668 including 209 PCB congeners (aka DRBC protocol). | VA |  | All PCB data generated uding method 1668 ar stired in this database; this includes results from sedument samples, ambient water samples and point source samples. These data are used for purposed of tracking point source PCB results (existing conditions and follow up results when implementing the PMP, provides site specific information that can be used for "fingrprinting" prospective sources when using available data.
| Compile an issue paper to describe the current state of monitoring and outline the roadblocks to enhancing those monitoring programs. | STAR and TCW |  | No progress on issue paper.
6. EPA conducts an on-going National-scale Air Toxics Assessments (NATA). The 2011 NATA will be reviewed upon release to identify the sources of and exposures to air toxics, including PCBs, within the Chesapeake Bay watershed. | Conduct a thorough review of the 2011 NATA report. | TCW | Report was reviewed and summary slides produced in March 2016. Summary was never presented to the TCW.
| Determine additional activities that could be helpful in determining where more atmospheric source data is needed. |  |  | TCW put forward a proposal for Goal Tema funding that did not go through UMBC is conducting monitoring and analysis of air deposition data for PCBs. Could have companion work item over next couple of years on Iding gaps and locating resources to fill gaps.
7. Assess the information that is available and forthcoming (e.g., the characterization of Anacostia river sediments by DC Department of Energy and Environment) that describes the most highly contaminated in-stream sediments in the watershed to engage the jurisdictions and federal regulators to explore the feasibility of additional remedial actions such as capping and/or dredging. | Develop a final Remedial Investigation Report (RI Report) based on the 700 samples already collected along the 9-mile tidal portion of Anacostia River between FY14 and end of FY15. | DOEE and federal partners |  | DOEE has completed all field activities for the Anacostia River sediment monitoring project. DOEE contractor has submitted a draft RI report to the Agency and is currently under review. Release of the RI report for public comment will be in early 2018. DOEE has held multiple meting engaging the public on the project, and providing updated during 2017.
| Study brown bullhead tumors in tidal Potomac River and Anacostia River between 2014-2016, establish trends, if any, and to determine whether or not any established trends are local or regional; ). | DOEE and FWS |  | FWS has completed the brown bullhead catfish studt and DOEE is awaiting a draft to the final report for this 3rd round of data collection.
| Install gauging and sampling stations in NW Branch, NE Branch and Lower Beaver dam Creek. Sampling storms by collecting sediment samples using innovative USGS tested methods to calculate loads for six episodes. | DOEE and USGS |  | Answer incorporated below:
| Collect data to identify sources and characterize contributions from those sources, including CSOs, MS4 outfalls, streams, and upstream contributions. | DOEE and USGS |  | DOEE in contract with USGS continues to collect water-quality samples for both lowflow and stormflow samples at NE Branch, NW Branch, Beaverdam Creek (BDC), Hickey Run, and Watts Branch; and 4 smaller non-gaged tributaries that flow through Washington, D.C. -- Nash Run, Ft. DuPont, Pope’s Branch, and Ft. Stanton;
8. The EPA Region 3 HSCD Site Assessment program will continue to track sites that are being evaluated in the Chesapeake Bay Watershed. Additionally, a GIS desktop tool is being developed to assist HSCD in identifying potential land sources of contamination in the watershed. This project is not limited to PCBs, but any type of contamination that could be migrating from CERCLA sites and affecting the watershed. The GIS tool will help to identify potential CERCLA sites and their proximity to environmentally sensitive areas and receptors to better focus on priority site evaluations. The use of EJ SCREEN will be evaluated to identify the location of such sites in areas with diverse populations. | Ongoing tracking in SEMS of work in Ches. Bay Watershed Site assessment decision forms have been updated to include checkbox on whether site is in Ches. Bay Watershed, and/or priority areas (Baltimore Harbor, Anacostia, Elizabeth River) | EPA HSCD | Tracking is ongoing in the CB watershed. HSCD is still in the process of developing GIS desktop tool.
| Meet with CBO GIS team to go over available data layers that might be of use to site discovery effort - Site Assessment Mapper (SAM) GIS tool is completed and ready for use – EJscreen is a data layer in SAM | EPA HSCD, TCW | HSCD will meet with the CBP GIS team in the coming months to review available data ;ayes to assist in the site discovery effort.
| Provide information to TCW for potential GIS mapping on CERCLA NPL sites in the watershed that may be undergoing PCB remediation. | EPA HSCD | Current NPL sites are mapped. Next step is to search for sites that are undergoing PCB remediation.
9. The HSCD Site Assessment Program will conduct work share meetings with our State counterparts once per year to determine who will be the lead agency for further investigation of any potential PCBs sites that are on the active sites list. | During yearly workshare meeting, TCW workplan will be a discussion point at the meetings and will use the initiative in the prioritization of sites to be evaluated in the CA | HSCD, State Site Assessment Counterparts | Workshare meetings are performed on a regular basis and PCB sites are discussed. If a PCB source discovery effort is launched and a list of active sites is developed, a focus of those workshare meetings would be that discovery effort.
| Also, other sites identified in #10 below or by other methods in trackdown studies, etc. may be better addressed under State VCP or other State programs. This will also be discussed at workshare meetings. |  | Pending source discovery effort
10. HSCD and TCW will continue to evaluate sites to identify industries or processes that used PCBs. Once this list is generated, the CERCLA, Brownfields, and RCRA programs can better focus resources on identifying and investigating these types of sites. As significant sources of PCBs, or other contaminants that are migrating into the watershed from contaminated land sources are discovered, HSCD will share this information as part of the progress monitoring of this strategy. Additionally, if there are potential land sources that other programs have found, HSCD can investigate those potential sources through coordination with the appropriate authority. | Identification and mapping of potential industries that historically used PCBs in the watershed | HSCD, TCW, TSCA
Discuss potential PCB sources with TCW and TSCA (e.g., power plants, railroad maintenance yards, etc.)
| Identify locations of industries within the watershed that may be potential PCB sources | HSCD
| Obtain information on PCB hotspot areas within the watershed and try to correlate CERCLA sites or other sites identified from above with those hotspots. | HSCD, TCW
Use information and data generated from above to pre-screen and prioritize sites to determine whether further assessment is needed and by whom.
11. The EPA R3 NPDES Permits Branch will continue to address PCBs through the CWA framework. Where waters have been identified as impaired and a local TMDL has been established creating WLA for point sources, the NPDES Permitting program will ensure that permits are consistent with the TMDL. The NPDES Permitting Program will draft and review permits with a focus on ensuring that PCB WLAs are clear and enforceable. The NPDES Enforcement Program, through state oversight and its independent compliance monitoring and enforcement authorities, will ensure that permit requirements are met. If a permittee is in non-compliance with its compliance obligations, EPA will take timely and appropriate action, including exercising its enforcement authority, to ensure that the permittee returns to compliance in an expeditious manner. | The NPDES Permitting Program will draft permits with a focus on ensuring that PCB WLAs are clear and enforceable and consistent with the TMDL. | EPA R3 NPDES Permits Branch | Ongoing
| The NPDES Permitting Program will review permits developed by the jurisdictions with a focus on ensuring that PCB WLAs are clear and enforceable and consistent with the TMDL. | EPA R3 NPDES Permits Branch | Ongoing
| The NPDES Enforcement Program, through state oversight and its independent compliance monitoring and enforcement authorities, will ensure that permit requirements are met. If a permittee is in non-compliance with its compliance obligations, EPA will take timely and appropriate action, including exercising its enforcement authority, to ensure that the permittee returns to compliance in an expeditious manner. | EPA R3 NPDES Permits Branch | Ongoing | Ongoing; will be carried over to next workplan
12. The EPA R3 Land and Chemicals (LCD) Toxics Program Branch will continue to ensure compliance with PCB TSCA regulations through its PCB inspection and enforcement program. Inspections will be targeted based on potential for releases, cumulative burden on EJ communities, or permitting. The R3 Toxics Program Branch will also responds to on tips/complaints that involve potential for illegal disposal and significant risk. | In 2016 and 2017, the EPA R3 LCD Toxics Program will perform inspections at facilities within the R3 states based on potential for PCB releases, cumulative burden on EJ communities, or permitting. The R3 Toxics Program Branch will also responds to on tips/complaints that involve potential for illegal disposal and significant risk. | EPA Region 3 | EPA LCD Toxics Branch has conducted 3 inspections in 2016 on facilitied within the CB watershed and has one remaining. OECEJ has performed 1 inspection in the CB watershed has 2 left to perform in 2016. There are at least 3 inspections planned within the CB watershed in FY17. Most enforcement actions that deal with PCB violations are associated with “management of PCB” issues such as labeling, manifesting and inspecting as opposed to illegal spills or disposal. Facilities are targeted based upon whether they have registered in-use PCB transformers or capacitors, or any other known PCB items. Disposal facilities that have current or interim Commercial Storage Permits for storage of PCB waste are also targeted as well as entities that submit self-implementing PCB cleanup plans. Also, RRC or NRC notifications that deal with PCB spills may be subject to an inspection and the ICIS database is surveyed to look for former violators. | Ongoing; will be carried over to next workplan
|  | Land and Chemicals Division |  | There were 2 inspections at Aberdeen and Delmarva stations in 2016-2017, and more planned for 2018
13. The EPA R3 LCD Office of Materials Management will continue to partner with the Maryland Department of Environment to oversee the PCB clean up at the Lockheed Martin plant located in Middle River, Maryland. The Middle River facility, which is located on Cowpen Creek, is considered to be a major contributor to PCBs in the Bay. Phase 2 of the clean-up is commencing. | Overall performance target is completion of remedial actions specified in the Feasibility Study approved by MDE and EPA Region III. Incremental steps include permit applications, approvals, mobilization, sediment removal, confirmatory sampling, in situ treatment amendment application, post-closure bioaccumulation monitoring, and a 5-year review submittal | Lockheed Martin is performing the remediation under an Administrative Consent order with the MDE. The project will require EPA approval of a Risk Based Disposal Approval Application (RBDAA) to manage the PCB remediation waste, and a separate conditional RBDAA approval for the application and monitoring of in situ amendments to reduce the bioavailability of residual PCBs within Dark Head Cove. | Ongoing | Upal Ghosh and UMBC were involved in carbon ammendment work for use in remedation activities. Tech decisions for remediation may be usefule as case studies to inform other remediation activities (e.g. Anacostia)
Permits to perform the remedial work will have to be secured from various entities of the MDE, U.S. Army Corps of Engineers (USACE), Baltimore County, etc.
14. The Chesapeake Bay Commission will work collaboratively with the Bay Program partners to identify legislative, budgetary and policy needs to advance the goals of the Chesapeake Watershed Agreement. | CBC will, in turn, pursue action within our member state General Assemblies and the United States Congress. See CBC Resolution #14-1 for additional information on the CBC’s participation in the management strategies. | Chesapeake Bay Commission |  | No updates
15. EPA will publish the April 7, 2010 Advanced Notice of Proposed Rulemaking (ANPRM) in the Federal Register for Public Comment. The Proposed Rulemaking is to reassess the ongoing authorized uses of PCBs to determine whether certain use authorizations should be ended or phased out because they can no longer be justified under section 6(e) of the Toxic Substances Control Act, which requires that the authorized use will not present an unreasonable risk of injury to health and the environment. | Publish the Advanced Notice of Proposed Rulemaking (ANPRM: April 7, 2010) in the Federal Register for Public Comment. | EPA Office of Chemical Safety and Pollution Prevention, Office of Pollution Prevention and Toxics |  | Not anticipated to move forward as a proposed rule. Will consider striking in next workplan.
Management Approach 2: Education and Awareness
Key Action | Performance Target(s) | Partners
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible
Identify responsible partner for each step.
1. Develop PMP guidance document for the control and reduction of PCBs in NPDES regulated stormwater and wastewater including an inventory of stormwater BMP options. This document would provide guidance to all Bay jurisdictions in implementing PCB load reductions established for dischargers through local TMDL development while recognizing the need for flexibility in PMP design. Develop guidance for unregulated sources of PCBs for use in developing implementation plans under TMDLs. | Contingent upon completion of VA DEQ’s work to evaluate and assess cross-jurisdiction applicability | VA DEQ (The document will be Virginia Specific, but can serve as a prototype for a larger effort) |  | Still important to pursue, working to free up staff resources to keep developing materials for draft PMP guidance.
2. Working with local government and non-profit organizations, the TCW will inform the public regarding risks from consuming contaminated fish by developing communications materials and corresponding procedures for their dissemination throughout the targeted communities. | Secure GIT Project funding. | Diversity Action Team | GIT Project funding was awarded in early 2016 | Ongoing. Release of first phas (poster/infographic) expected early 2018
| Inventory existing approaches to issuing fish consumption advisories and study effectiveness of and compliance with those advisories in order to develop enhanced tools | Project award recipient in coordination with DAT and TCW
| Test the new tools and work on optimization | Project award recipient in coordination with DAT and TCW
| Implement and disseminate new tools in order to explore the extent to which diverse populations are located in areas where fish advisories are being issued, using EPA’s EJSCREEN tool. | Bay Program partners
3. Compile education materials regarding existing procedures and best practices for containment and prevention of release of PCBs. | Identify potential resources | TCW
TCW has discussed the development of a PCB resource center. Resources have not yet been identified to support the development and maintenance of the site.
| Compile education materials |  |  | FCA infographic poster in final stages of development. Will be published and distributed through the watershed in 2018.
Management Approach 3: Voluntary Programs
Key Action | Performance Target(s) | Partners
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible
Identify responsible partner for each step.
1. Coordinate a voluntary action program to reduce transformers and other PCB containing equipment (e.g., fluorescent light ballasts). Include those classified as PCB free (less than 50 ppm) Provide to program participants information on remediating PCB contamination on-site from historical releases of these transformers and use EPA’s EJ SCREEN tool to help identify where such equipment is located in areas with diverse populations. | Identify a project lead | TCW |  | Have RFP out for GIT funded project to do a feasibility study. After awards are given, work will begin and project will be completed by end of calendar year 2018.
| Estimate location and volume of PCB-containing equipment | Contingent upon available resources
| Estimate costs of replacing PCB-containing equipment | Contingent upon available resources
| Identify potential incentives and present summary of cost information to land owners | Contingent upon available resources
| Obtain commitment from land owners to voluntarily replace PCB containing equipment with consideration to include activities in areas with diverse populations | Contingent upon available resources
Management Approach 4: Science
Key Action | Performance Target(s) | Partners
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible
Identify responsible partner for each step.
1. Support research on cost-effective tools for track-down studies and provide a mechanism for municipalities to share information on lessons learned from PMP development and implementation strategies and methods for documenting and sharing the information. | Apply for GIT project funding, or secure other resources. | TCW | Funds were provided to Tetra Tech to conduct a literature review and produce a draft set of track down study guidance. | Further work on trackdown study ongoing. Possibility of a PCB consortium on trackdown and resources in fall 2018 in coordination with Balitmore Urban Waters Partnership
| Conduct interviews, literature reviews and hold a technical workshop to gather information on best practices. | Contingent upon resources | Tetra Tech performed a literature review and drafted a set of track down study guidance. The guidance document is undergoing review and edits by a small working group under the TCW. | Further work on trackdown study ongoing. Possibility of a PCB consortium on trackdown and resources in fall 2018 in coordination with Balitmore Urban Waters Partnership
| Develop a guidance document on best practices for effective implementation of PCB track down studies in the TMDL context | Contingent upon resources |  | Further work on trackdown study ongoing. Possibility of a PCB consortium on trackdown and resources in fall 2018 in coordination with Balitmore Urban Waters Partnership
2. Identify barriers and opportunities related to more frequent use of EPA 1668 for contaminated sites, wastewater and regulated and unregulated stormwater dischargers as a screening tool (as is underway in VA) or for a targeted subset of permittees. This effort could also be targeted to industrial stormwater permittees with SIC classifications that indicate the facility has the potential for PCB contamination on site from historical use or current operation or disposal of PCB containing materials. | Apply for a STAC workshop or identify additional potential resources | TCW
VA DEQ
3. Encourage use of the high-sensitivity congener-based methods to analyze PCBs to ensure that PCB sources are being characterized accurately when such characterization can help with source identification | Apply for a STAC workshop of identify an alternative funding source to achieve this item. | TCW
VA DEQ
4. A project was completed to determine the relative amount of PCB reduction that might occur across the range of BMPs implemented for the Chesapeake Bay nutrient and sediment TMDL. The BMPs will be cross-correlated with contaminant pathways and their association with land use and industrial sources (e.g., urban stormwater, agriculture, landfills, dredged material disposal facilities, hazardous waste sites, and industrial operations). The study assessed and explained the most beneficial management actions that could leverage current local TMDLs and watershed implementation plans (WIPs) to achieve multiple benefits for nutrient, sediment, and toxic contaminant reductions. | Estimate the potential toxic contaminant reduction associated with the implementation of BMPs for sediment and nutrient reduction under the Chesapeake Bay TMDL. | Chesapeake Stormwater Network and TCW | Scores (-5 to 5) have been developed to rate the relative effectiveness of nutrient and sediment BMPs in terms of their ability to reduce toxic contaminant loads to the Chesapeake Bay. More science is needed in order to develop reduction efficiency estimates. | Exploratory work being done to incorporate qualitative scoring tools into BMP implementation scenarios in Phase 6 CAST.
Provide water resource managers with better BMP data to develop more effective local TMDLs to control toxic pollutants in the watershed.
| Recommend specific stormwater treatment and pollution prevention practices that could maximize removal of toxic contaminants in the Bay watershed |  |  | Exploratory work being done to incorporate qualitative scoring tools into BMP implementation scenarios in Phase 6 CAST.
5. Review the 2015 NATA report to determine the need for further investigation of atmospheric sources of PCBs, characterization of PCB concentrations in atmospheric deposition to the watershed and Bay, and determine the significance of these sources for bioaccumulation in fish. Homolog distribution profiles for PCBs in atmospheric deposition could be evaluated to determine whether mid-weight congeners are present at levels that significantly contribute to bioaccumulation in fish. | Review NATA report | TCW | The 2015 NATA report is the same as the 2011 NATA report, but which was updated in December 2015.
Review atmospheric deposition study based in Delaware estuary
Analyze need for next steps
Definitions:
EPA | U.S. Environmental Protection Agency
DE DNREC | Delaware Department of Natutral Resources and Environmental Control
DOEE | District of Columbia Department of Energy and Environment
MDE | Maryland Department of the Environment
MD DNR | Maryland Department of Natural Resources
NYS DEC | New York State Department of Environmental Control
PA DEP | Pennsylvania Department of Environmental Protection
VA DEQ | Virginia Department of Environmental Quality
WV DEP | West Virginia Department of Environmental Protection
USGS | U.S. Geological Survey
FWS | U.S. Fish and Wildlife Service
UMCES | University of Maryland Center for Environmental Science
UMBC | University of Maryland Baltimore County
NOAA | National Oceanic and Atmospheric Administration
USDA | U.S. Department of Agriculture
NRCS | National Resource Conservation Service
DoD | U.S. Department of Defense
USACE | U.S. Army Corps of Engineers
DOT | Department of Transportation
SRBC | Susquehanna River Basin Commission
CBP | Chesapeake Bay Program Partnership
CBPO | Chesaoeake Bay Program Office
WQGIT | Water Quality Goal Implementation Team
STAC | Scientifical and Technical Advisory Committee
MB | Chesapeake Bay Program's Management Board
PSC | Chesapeake Bay Program's Principles' Staff Committee
WIP | Watershed Implementation Plan
TMDL | Total Maximum Daily Load
NATA | National Air Toxics Assessment
DAT | Chesapeake Bay Program Diversity Action Team
HSCD | EPA Hazardous Site Cleanup Division
TSCA | Toxic Substance Control Act
PMP | Pollution Minimization Plan
ASTSWMO | Association of State and Territorial Solid Waste Management Officials
CSN | Chesapeake Stormwater Network