## Sheet1
Toxic Contaminants Research Outcome Effective dates: 2016-2017
Goal: Toxic Contaminants
Outcome: Research
Long term Target: Develop a research agenda and further characterize the occurrence, concentrations, sources and effects of toxic contaminants of emerging and widespread concern.
2 year Target: Completion of performance targets related to key actions
Partner contributions to 2 year target: As-listed under performance targets
Management Approach 1: Supply information to make fish and shellfish safe for human consumption |  |  | Status | Meetings Addressed
Key Action | Performance Target(s) | Partners
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible
Identify responsible partner for each step.
1. Use existing information to provide overviews of the effects of multiple toxic contaminants on shellfish and fisheries. | NOAA is preparing a National Bioeffects report that will contain a chapter on Chesapeake Bay. NOAA will present the Chesapeake summary to the TCW. | NOAA | New NOAA links available: https://www.coastalscience.noaa.gov/publications/detail.aspx?resource=CD49zJOmle8QZs7m2e5xkN70bQyiHUCD//IBANGJf5I https://www.coastalscience.noaa.gov/publications/detail.aspx?resource=4EDHhMwZ8mKFyE3FvsVk6tourxJXmpjHTZYKMzs8wro= https://www.coastalscience.noaa.gov/publications/detail.aspx?resource=UXYJZBaDEjUU5fZP0w40KePNX8GV55W6QA6MsO00DV4= https://www.coastalscience.noaa.gov/publications/detail.aspx?resource=s9rQDs9By9FKckWVejYTpFWevrvfFj9ivvIuoDhO8FA= https://www.coastalscience.noaa.gov/publications/detail.aspx?resource=ODebTy8c7p2BVplVnKQR4Q== https://www.coastalscience.noaa.gov/publications/detail.aspx?resource=OY1w/4qioCfyiJJzy372gu37gZUJQwc3Pt3jRqxg1gw= https://www.coastalscience.noaa.gov/publications/detail.aspx?resource=mog5MXjGBQBJcfXMqNU4fQ== | 6/15/16;
Other existing NOAA reports include:http://ccma.nos.noaa.gov/publications/NCCOSTM47.pdf)
http://www.ccma.nos.noaa.gov/publications/nccoschesapeakebay.pdf
2. Generate further information on mercury, focused on determining whether further Chesapeake Strategies are needed to supplement national efforts to reduce its impact on fish and associated consumption advisories. | Establish a Mercury Subgroup that would begin to summarize information to be considered by TCW to minimize effects of mercury. | TCW
|  | UMCES, SERC, NOAA-ARL, ERM, Inc., MDE, DNR-PPRP |  | 6/15/16;
| Conduct sampling of mercury in young of the year fish. Results will eventually be used to assess trends. | MDE and MD DNR
| Review and obtain information documented during the establishment of Maryland’s proposed Mercury TMDL. | MDE | This action is on hold as MDE is awaiting information from an air deposition model in order to support MD’s mercury TMDL. It is anticipated that this information will not be available till the end of 2017.
3. Generate further information on selected pesticides to help TCW consider a future management strategy | Interact with MD Pesticide network and associated research WG (see Management Approach 4) | MD Pesticide Network
4. Consider the development of a PCB mass balance model for the Chesapeake Bay. | Discuss utility, feasibility and practicality of developing a mass-balance model for PCBs. | TCW and science partners
5. Monitor levels of PCBs in fish and shellfish and move contaminated sites towards cleanup. | (Please see the Toxic Contaminants Policy and Prevention Workplan- Management Approach 1, Key Action 1) | (See Toxic Contaminants Policy and Prevention Workplan)
6. Better delineate PCB sources from diffuse sources of land, release from deposits in stormwater pipes, and atmospheric deposition. | (Please see the Toxic Contaminants Policy and Prevention Workplan- Management Approach 1, Key Actions 6 and 10; Management Approach 4, Key Actions 1 and 5) | (See Toxic Contaminants Policy and Prevention Workplan)
Management Approach 2: Understanding the influence of contaminants in degrading the health, and contributing to mortality, of fish and wildlife
Key Action | Performance Target(s) | Partners
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible
Identify responsible partner for each step.
1.Assess the effects of contaminants on fish and shell fish in tidal waters | Continue studies of tumors found in Bullheads catfish | FWS
| Evaluate findings from condition of Yellow Perch in urban areas. | FWS
MD DNR
USGS
2.Generate information to document fish health conditions in the Bay watershed. | Conduct studies to understand the influence of contaminants and other factors degrading the health, and contributing to mortality of fish. Products include summary of fish health conditions (including intersex) over the last 10 years in the watershed. Studies have partners in several states (see below) | USGS | A data series of the fish health and indicators of exposure to estrogenic contaminants for adult bass (smallmouth and largemouth) will be released in 2017. The data compiled from the chemical data series, the biological (wild fish health, estrogen equivalents in water) and landscape analyses will be used for a synthesis report (2017) of the contributing factors to degraded health of bass within the Chesapeake watershed. Final publication: 2018 | 8/10/16;
| Better understand the influence of endocrine-disrupting compounds (EDCs) and their effects on fish conditions. Focus on agricultural areas in 2016-17 with urban areas addressed in 2018-19. (in collaboration with project listed above) | USGS | Adult smallmouth and YOY were collected from these 6 sites as well as other sites throughout the study area and assessed histologically. In 2017, we will complete assessments of factors affecting fish health at the integrator sites (2013-2017) representing potential effects of EDCs in agricultural areas. Targeted sampling will occur in 2017 to fill data gaps at 4 of the 6 sites. In late summer once the geospatial work is complete we will start outlining a plan for urban areas which will run from 2018-2019.
| Continue monitoring of fish conditions in areas of concern within jurisdictions (most in cooperation with USGS projects listed above) | PA DEP
MD DNR
WV DEP
| Continue studies on the relationship between the amount of impervious surface and the impact on fish conditions | MD DNR
| Continue stream IBI studies as part of the Maryland biological stream survey to evaluate health of fish communities and identify potential linkages to toxic contaminants. | MD DNR and MDE
3.Assess the effects of toxic contaminants on wildlife by summarizing existing studies and considering additional research activities. Information will be used to TCW on implications for relative risk (see management approach 4) | Complete and present review of EDC found in wildlife within the Chesapeake watershed. Based on results consider additional studies. | USGS | Wildlife Review: The review was completed and presented in 2016. The study lead is currently working on a manuscript to be published in 2017. | 1/13/16; 2/10/16; 8/10/16
| Publish results from the recently published Chesapeake Bay osprey food study. Assess if results from the Delaware-based osprey food study are applicable. | USGS
Management Approach 3: Document the occurrence, concentrations, and sources of contaminants causing fish and wildlife degradation
Key Action | Performance Target(s) | Partners
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible
Identify responsible partner for each step.
1. Better define the sources and occurrence of EDCs and other contaminant groups that are affecting the health of fish and wildlife in the watershed. | Conduct projects to identify the sources and occurrence of toxic contaminants contributing to degraded fish health. Prepare initial summary of the occurrence and sources of contaminants based on information collected by USGS over the last 10 years in the Bay watershed. Assess the potential association with nutrients. Studies have partners in several states (see below). | USGS | A synthesis of historic chemical data (including grab water, passive sampler and sediment) will be released as two data releases. A database of estrogenic activity (estrogen equivalents) for sites within the Chesapeake watershed will be completed and released in 2017 as a USGS data release. | 7/13/2016, 9/14/16
| Continue study of sources and occurrence of EDCs in agricultural watersheds (same locations as USGS fish health studies). Collect samples for Gather information for GIS analysis of sources and occurrence of EDCs in the watershed. Begin planning for study of urban watersheds, focusing on impact of BMPs on EDCs in the environment. | USGS | Ongoing Sampling: Water samples were collected from 6 sites in 2016 from Feb-Nov at six sites. Samples were collected monthly from Feb-March and Aug-Nov and twice a month from April-July. Water was analyzed for over 200 compounds at USGS labs and estrogenicity. Bed sediment was collected from the 6 sites two times in 2016 and will be collected twice from the 4 sites in 2017. Sampling in the agricultural watersheds will be completed in July 2017.
In 2017, planning will begin for our study on urban watersheds with a focus on BMP implementation. A pilot study was conducted in 2016 to evaluate the upstream and downstream impacts from nutrient control, agriculture management, stormwater management and wastewater treatment strategies on estrogenicity in surface waters. Approximately 12 sites were sampled bimonthly for 1 year including a rain event.
| Continue Pennsylvania studies on pesticides and hormones. | PA DEP
| Continue studies on the impacts of algal toxins on fish kills in West Virginia and identify potential links to toxic contaminants. | WV DEP (working with USGS)
| Evaluate outcomes from Anacostia River sediment investigation to improve understanding of contaminants other than PCBs. | DOEE
2. Better define sources and occurrence contaminant groups occurring in tidal waters | -use new Chesapeake bio-effects summary and Utilize information from existing NOAA documents http://ccma.nos.noaa.gov/publications/NCCOSTM47.pdf | NOAA
Management Approach 4: Assess the relative risk of contaminants, and options for mitigation, to inform policy and prevention
Key Action | Performance Target(s) | Partners
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible
Identify responsible partner for each step.
1. Develop approaches to assess the relative risk of contaminants to help inform policy and prevention strategies. | Develop approaches to assess relative risk to help inform policy and prevention strategies. | EPA Office of Water, Office of Science and Technology
| Begin to develop methods for summarizing existing information on Hg, pesticides, PAHs, for future consideration within the Policy and Prevention Management Strategy. | TCW
2. Share approaches for assessing relative risk with the TCW so that they can consider options for mitigating impacts of toxic contaminants. | Develop a lessons learned document based on the results from the Anacostia River study. | DOEE
TCW
| Begin a risk assessment study of EDCs compounds with occurrence of intersex and other fish health conditions | USGS | In 2016 a population dynamic model for smallmouth bass was developed and validated using data from PA. In 2017 abiotic and chemical data will be incorporated into the developed simulation to assess long-term risk of contaminants to smallmouth bass populations. Individual based models will be developed again using smallmouth bass as a case study beginning in 2017. A journal article on the population model will be completed in 2017 as well as a data visualization tool.
| Conduct GIS analysis to identify toxic contaminant “hotspots” based on land use. Relate to areas of nutrient loading | USGS | Geospatial data within the entire Chesapeake Bay Watershed was acquired in 2016 on the NHD+ scale including AFOs, pesticide use, CSOs, basic land-use information, WWTPs, etc. Landscape variables identified by Young et al. (2104) as having strong correlations with estrogenic activity will be collected and mapped at the Chesapeake Bay Watershed-scale. In 2017, additional data will be collected to better represent non-agricultural areas, including existing and proposed BMP implementations, potential point and non-point EDC sources, and other relevant landscape and watershed-scale variables. Locations of historic and ongoing EDC research efforts and relevant species distributions within the Bay will be cataloged and assembled along with the contaminant, BMP, and landscape data in a GIS. Correlation and Principal Component Analyses will be used to identify landscape gradients and clusters, and regressions will be used where historic biologic and chemistry data documenting estrogenic activity is available to determine any correlations with the landscape-scale data as per methods described in Young et al. (2014). Proximity and overlay analyses will be used to identify locations where key habitat and species assemblages coincide with indicator variables identified from the regression analyses to flag areas exhibiting potential EDC, nutrient, and sediment loading risks. A data release including all sources of EDCs will be summarized by NHD+ catchment will be released in 2017. Another product will be a series of maps visualizing the spatial distribution of various EDC sources throughout the Bay watershed.
| Evaluate outcomes from the literature review on the potential toxic contaminant reductions provided by traditional stormwater BMPs, and conduct outreach efforts to share those results. | CSN
TCW
| Have MD Pesticides share methodology for prioritizing pesticides. Work with them to assess use for TCW | MD Pesticide Network (research workgroup)
3. The Chesapeake Bay Commission will work collaboratively with the Bay Program partners to identify legislative, budgetary and policy needs to advance the goals of the Chesapeake Watershed Agreement. | CBC will, in turn, pursue action within our member state General Assemblies and the United States Congress. See CBC Resolution #14-1 for additional information on the CBC’s participation in the management strategies. | Chesapeake Bay Commission
Management Approach 5: Gather information on issues of emerging concern
Key Action | Performance Target(s) | Partners
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible
Identify responsible partner for each step.
1. Better delineate potential impacts of UOG activities. | Conduct research on impacts of UOG activities (part of wider studies of UOGs) | USGS with partners
Definitions:
EPA | U.S. Environmental Protection Agency
DE DNREC | Delaware Department of Natutral Resources and Environmental Control
DOEE | District of Columbia Department of Energy and Environment
MDE | Maryland Department of the Environment
MD DNR | Maryland Department of Natural Resources
NYS DEC | New York State Department of Environmental Control
PA DEP | Pennsylvania Department of Environmental Protection
VA DEQ | Virginia Department of Environmental Quality
WV DEP | West Virginia Department of Environmental Protection
USGS | U.S. Geological Survey
FWS | U.S. Fish and Wildlife Service
UMCES | University of Maryland Center for Environmental Science
UMBC | University of Maryland Baltimore County
NOAA | National Oceanic and Atmospheric Administration
USDA | U.S. Department of Agriculture
NRCS | National Resource Conservation Service
DoD | U.S. Department of Defense
USACE | U.S. Army Corps of Engineers
DOT | Department of Transportation
SRBC | Susquehanna River Basin Commission
CBP | Chesapeake Bay Program Partnership
CBPO | Chesaoeake Bay Program Office
WQGIT | Water Quality Goal Implementation Team
STAC | Scientifical and Technical Advisory Committee
MB | Chesapeake Bay Program's Management Board
PSC | Chesapeake Bay Program's Principles' Staff Committee
WIP | Watershed Implementation Plan
TMDL | Total Maximum Daily Load
NATA | National Air Toxics Assessment
DAT | Chesapeake Bay Program Diversity Action Team
HSCD | EPA Hazardous Site Cleanup Division
TSCA | Toxic Substance Control Act
PMP | Pollution Minimization Plan
ASTSWMO | Association of State and Territorial Solid Waste Management Officials
CSN | Chesapeake Stormwater Network