## Table 1
Biennial Strategy Review System: Logic Table and Work Plan
Instructions: The following Logic Table should be used to articulate, document, and examine the reasoning behind your work toward an Outcome. Your reasoning—or logic—should be based on the Partnership’s adaptive management decision framework. This table allows you to indicate the status of your management actions and denote which actions have or will play the biggest role in making progress.
Some Management Strategies and Work Plans will not immediately or easily fit into this analytical format. However, all GITs should complete columns one through four to bring consistency to and heighten the utility of these guiding documents. The remaining columns are recommended for those who are able to complete them. If you have any questions as you are completing this table, please contact SRS Team Coordinator Laura Free (free.laura@epa.gov).
The instructions below should be used to complete the table. An example table is available on the GIT 6 webpage under “Projects and Resources”.
1. For the first round of strategic review (2017-2018): Use your existing Work Plan actions to complete the Work Plan Actions section first. Make sure to number each of the actions under a high-level Management Approach, as these numbers will provide a link between the work plan and the logic table above it. Use color to indicate the status of your actions: a green row indicates an action has been completed or is moving forward as planned; a yellow row indicates an action has encountered minor obstacles; and a red row indicates an action has not been taken or has encountered a serious barrier. 2. Required: In the column labeled Factor, list the significant factors (both positive and negative) that will or could affect your progress toward an Outcome. The most effective method to ensure logic flow is to list all your factors and then complete each row for each factor. Consult our Guide to Influencing Factors (Appendix B of the Quarterly Progress Meeting Guide on the GIT 6 webpage under “Projects and Resources”) to ensure your list is reasonably comprehensive and has considered human and natural systems. Include any factors that were not mentioned in your original Management Strategy or Work Plan but should be addressed in any revised course of action. If an unmanageable factor significantly impacts your outcome (e.g., climate change), you might choose to list it here and describe how you are tracking (but not managing) that factor. 3. Required: In the column labeled Current Efforts, use keywords to describe existing programs or current efforts that other organizations are taking that happen to support your work to manage an influencing factor but would take place even without the influence or coordination of the Chesapeake Bay Program. You may also include current efforts by the Chesapeake Bay Program. Many of these current efforts may already be identified in your Management Strategy; you may choose to link the keywords used in this table to your Management Strategy document for additional context. You may also choose to include some of these efforts as actions in your work plan; if you do, please include the action’s number and hyperlink. 4. Required: In the column labeled Gap, list any existing gap(s) left by those programs that may already be in place to address an influencing factor. These gaps should help determine the actions that should be taken by the Chesapeake Bay Program through the collective efforts of Goal Implementation Teams, Workgroups, and internal support teams like STAR, or the actions that should be taken by individual partners to support our collective work (e.g., a presentation of scientific findings by a federal agency to a Chesapeake Bay Program workgroup). These gaps may already be listed in your Management Strategy. 5. Required: In the column labeled Actions, list the number that corresponds to the action(s) you are taking to fill identified gaps in managing influencing factors. Include on a separate line those approaches and/or actions that may not be linked to an influencing factor. To help identify the action number, you may also include a few key words. Emphasize critical actions in bold. 6. Optional: In the column labeled Metric, describe any metric(s) or observation(s) that will be used to determine whether your management actions have achieved the intended result. 7. Optional: In the column labeled Expected Response and Application, briefly describe the expected effects and future application of your management actions. Include the timing and magnitude of any expected changes, whether these changes have occurred, and how these changes will influence your next steps 8. Optional: In the column labeled Learn/Adapt, describe what you learned from taking an action and how this lesson will impact your work plan or Management Strategy going forward.
Toxics Contaminants Research Logic Table and Work Plan
Primary Users: Goal Implementation Teams, Workgroups, and Management Board ¦ Secondary Audience: Interested Internal or External Parties Primary Purpose: To assist partners in thinking through the relationships between their actions and specific factors, existing programs and gaps (either new or identified in their Management Strategies) and to help workgroups and Goal Implementation Teams prepare to present significant findings related to these actions and/or factors, existing programs and gaps to the Management Board. ¦ Secondary Purpose: To enable those who are not familiar with a workgroup to understand and trace the logic driving its actions. Reminder: As you complete the table below, keep in mind that removing actions, adapting actions, or adding new actions may require you to adjust the high-level Management Approaches outlined in your Management Strategy (to ensure these approaches continue to represent the collection of actions below them). Long-term Target: Develop a research agenda and further characterize the occurrence, concentrations, sources and effects of toxic contaminants of emerging and widespread concern. Two-year Target: Completion of performance targets related to key actions
KEY: Use the following colors to indicate whether a Metric and Expected Response have been identified.
Metric |  | Specific metrics have not been identified
Metrics have been identified
Expected Response |  | No timeline for progress for this action has been specified
Timeline has been specified
Factor |  |  | Current Efforts |  | Gap | Actions (critical in bold) |  | Metrics | Expected Response and Application |  | Learn/Adapt
What is impacting our ability to |  |  | What current |  | What further efforts or | What actions are |  | Optional: Do | Optional: What |  | Optional: What did
achieve our outcome? |  |  | efforts are |  | information are needed | essential to achieve |  | we have a | effects do we expect |  | we learn from
|  |  | addressing this |  | to fully address this | our outcome? |  | measure of | to see as a result of |  | taking this action?
|  |  | factor? |  | factor? |  |  | progress? | this action, when, |  | How will this lesson
[8 empty] | How do we | and what is the |  | impact our work?
[8 empty] | know if we | anticipated
[8 empty] | have achieved | application of these
[8 empty] | the intended | changes?
result?
Communicating the potential |  |  | Tracking of impairments, which lead to fish consumption advisories based on jurisdictional reporting of PCB impairments. |  |  | Interaction between jurisdictions to ensure there is consistent efforts to reduce contaminants, which contribute to fish consumption advisories.
impacts of consuming
contaminated fish and
addressing their causes. The
jurisdictions have different
assumptions about human
exposure through fish
consumption, which can limit
comparability across the
watershed
Multiple factors affecting |  |  | Studies addressing the multiple causes of factors affecting fish and shellfish, including EDCs and fish health; surveys of toxic contaminants and oysters. Limited information on wildlife; |  | Evolving towards a more geographic approach to focus in areas where fish health issues are most prevalent. Greater emphasis on linkage between factors affecting fish habitat and health, including toxic contaminants | More integrated studies to address the topic. Increase collaboration with academic institutions conducting research. Working with partners to plan potential studies to address selected topics.
health and mortality of fish
and wildlife. There are
multiple contaminants and
additional factors are causing
the degradation (and
mortality) of fish so trying to
identify specific causes is
extremely difficult.
Lack of data on the |  |  | Jurisdictions have |  | Longer-term, and | Better utilize
occurrence and trends of toxic |  |  | monitoring |  | comparable monitoring | jurisdictions
contaminants. There is no |  |  | programs for selected toxic |  | for selected toxic contaminants through | monitoring that is used for biannual
Factor |  |  | Current Efforts |  | Gap | Actions (critical in bold) |  | Metrics | Expected Response and Application |  | Learn/Adapt
What is impacting our ability to achieve our outcome? |  |  | What current efforts are addressing this factor? |  | What further efforts or information are needed to fully address this factor? | What actions are essential to achieve our outcome? |  | Optional: Do we have a measure of progress? How do we know if we have achieved the intended result? | Optional: What effects do we expect to see as a result of this action, when, and what is the anticipated application of these changes? |  | Optional: What did we learn from taking this action? How will this lesson impact our work?
watershed-wide monitoring program on the condition of fish and wildlife that is integrated with water and sediment sampling. |  |  | contaminants, but mostly not adequate for trends. |  | design of an integrated monitoring network. Data synthesis to improve current understanding of sources, status and trends of toxic contaminants, and their relation to nutrients and sediment. | integrated reports; Design an integrated monitoring network to improve long-term information
Limited information of the practices to mitigate contaminants, and their potential co-benefits with nutrients and sediment reductions |  |  | Some academic partners looking at contaminant mitigation from selected BMPs. Fact sheets on potential co- benefits between toxic contaminants, nutrients, and sediment. Developed reports on ag and urban contaminants. |  | Increased interaction with WQ GIT to develop and promote joint approaches to reduce toxic contaminants, nutrients, and sediment. | Focused source- sector approach with emphasis on agricultural and urban settings; Generate more information on potential co-benefits and explore use of CBP decision tools (such as CAST).
Resource constraints. The constraints include (1) minimal capacity within |  |  | Coordination of efforts between members of the |  | Expand capacity through increased coordination with ongoing academic research, state, and | Invite more partners to the TCW. Have more focused interaction between
Factor |  |  | Current Efforts |  | Gap | Actions (critical in bold) |  | Metrics | Expected Response and Application |  | Learn/Adapt
What is impacting our ability to |  |  | What current |  | What further efforts or | What actions are |  | Optional: Do | Optional: What |  | Optional: What did
achieve our outcome? |  |  | efforts are |  | information are needed | essential to achieve |  | we have a | effects do we expect |  | we learn from
|  |  | addressing this |  | to fully address this | our outcome? |  | measure of | to see as a result of |  | taking this action?
|  |  | factor? |  | factor? |  |  | progress? | this action, when, |  | How will this lesson
[8 empty] | How do we | and what is the |  | impact our work?
[8 empty] | know if we | anticipated
[8 empty] | have achieved | application of these
[8 empty] | the intended | changes?
result?
the CBP to address |  |  | Toxic Contaminant |  | federal efforts. Increase | researchers and
contaminants; (2) an |  |  | WG. |  | emphasis on toxic | stakeholders such as
emphasis on nutrients and sediment that limits the opportunity for increased CBP focus on toxic |  |  |  |  | contaminants within CBP monitoring and modeling teams. More focus on co- benefits. | through workshops (such as STAC, ChesRMS) and GIT WGs.
contaminants; and (3)
minimal funding
opportunities to conduct
additional studies.
Synthesis. This is a new |  |  | Very little current |  | Summarize existing | USGS is considering
factor which recognizes the findings from technical articles and reports need to |  |  | effort |  | information and provide implications for better management of contaminants | more resources towards synthesis. TCW needs to consider other
be summarized and | [5 empty] | possibilities (such GIT
communicated to be used | [5 empty] | funding, etc.).
effectively by resource
managers
WORK PLAN ACTIONS | [11 empty] | 2020 SRS REVIEW: STATUS OF WORKPLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [11 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  |  | Geographic Location | Expected Timeline | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
Management Approach 1: Supply information to make fish and shellfish safe for human consumption | [11 empty] | Management Approach 1: Supply information to make fish nd shellfish safe for human consumption
1.1 | Generate further information on mercury, focused on determining whether further Chesapeake Strategies are needed to supplement national efforts to reduce its impact on fish and associated consumption advisories. |  |  | Summarize existing impairments in the watershed through the creation of a story map for mercury. Jurisdictions supply information and the CBP GIS team and Monitoring team integrate into a story map. |  |  | TCW; MDE, PA DEP, VA DEQ, DOEE, WV DEP, DNREC. CBP GIS team and monitoring team. |  |  |  | 2018-19 | Draft story map was created but text needs to be updated. Outline of available information was created | Incomplete and needs for work: Need to revise text on story map, create supporting documentation. POCs: H. Swartwell and S. Phillips
|  |  |  | Inventory available mercury monitoring data (water, sediment, fish tissue) to inform status or trends. Have CBP Monitoring team lead the inventory and assessment of data. |  |  | TCW; MDE, PA DEP, VA DEQ, DOEE, WV DEP, DNREC. CBP monitoring team. |  |  |  | 2018-19 | Do not believe CBP monitoring team conducted this inventory. However, was included as part of USGS effort to inventory selected toxic contaminants | If part of USGS effort, completed w/ additional follow-up. USGS has inventoried mercury, PCBs, and pesticides as part of their Chesapeake status and trends topic. POC: Emily Majcher, USGS
|  |  |  | Communicate information from ongoing study of mercury and fish consumption advisories in the watershed. |  |  | USGS and partner states |  |  |  | 2019-2020 | Presentation provided to TCW; paper will be published | Completed w/additional follow up. Once paper is published, should be communicated with TCW and other CBP groups by USGS. POC: Colin Eagle-Smith, USGS
|  |  |  | Conduct sampling of mercury in young of the year fish. Results will eventually be used to assess trends. Reported annually. |  |  | MDE and MD DNR |  |  |  | Ongoing; annual sampling and reporting | Young of year sampling continued into 2019. Final report was released in September 2019. Studies remain to establish a downward statistical trend in Hg concentrations. | Ongoing with activities planned
|  |  |  | Review and obtain information documented during the establishment of Maryland’s proposed Mercury TMDL. Additional fish tissue collections are planned in 2018 to determine if the remaining waters listed for mercury are impaired. Hg TMDL development will be delayed in Maryland until listing reassessment is completed. |  |  | MDE |  |  |  | MDE information will not be available until early 2019. | Additional fish tissue collections conducted in 2018 and 2019. Data is currently being analyzed to determine if Hg impairments can be delisted. One listing was removed in the 2018 IR. Additional fish collection may be required for reassessment in Fall 2020 if data analysis demonstrates existing data is insufficient for delisting decisions. Hg TMDL development will be delayed until listing reassessment is completed. | Ongoing with activities planned
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [11 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  |  | Geographic Location | Expected Timeline | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
1.2 | Inventory any ongoing progress of regional PCB models within the Chesapeake Bay. |  |  | Stay informed on progress of models in James River, Anacostia, upper Potomac, any others as they may inform adaptive management decisions/areas of focus for others in the watershed. Assess if information could be used to inform co-benefits and CBP tools (such as CAST), (see Management Approach 4). |  |  | TCW partners constructing models and USGS. |  |  |  | 2018-2020 | States has been contacted about existing modeling efforts. Not all have responded. | Incomplete and needs more work. Responses needed from all states. Results would be shared at one of the TCW calls. POC: Emily Majcher
1.3 | Science to support PCB Policy and Prevention Refine and improve understanding of PCB sources to inform the Conceptual Model of fate in the environment |  |  | Complete information gathering and develop a guidance document on best practices for effective implementation of PCB track down studies in the TMDL context |  |  | TCW |  |  | Further work on trackdown study ongoing. Possibility of a GIT funded effort to complete |  |  | Ongoing, importance of trackdown highlighted in STAC workshop report, USGS supported lessons learned document | Ongoing with activities planned (GIT funding proposal for trackdown guidance)
|  |  |  | Communicate results of completed research study investigating the PCB content of WW biosolids and effluent in an urban WWTP. Ongoing studies of fat-oil-grease deposits as potential sources of PCBs in aging infrastructure |  |  | UMBC USGS |  |  | 2018 briefing of completed WWTP study, ongoing study will be briefed in 2021 |  |  | Ongoing, additional briefing anticipated FY21, Tetra Tech document captured here? | Ongoing with activities planned;
1.3 | (Please see the Toxic Contaminants Policy and Prevention Strategy and Workplan for further details). |  |  | -Improve understanding of sources and fate of PCBs in the environment to inform mitigation options [includes summarizing best practices for PCB track down studies, informing stakeholders of results of atmospheric deposition studies, WWTP biosolids and effluent loads as well as reporting of other potential sources such as demolition/construction, dredged sediments], -Status and change in environment through the more prevalent use of the 1668 congener based analytical method, communicate lessons learned from innovative monitoring approaches, and gather data from TMDL implementation plan progress to assess changes over time, and -BMP effectiveness for removal of PCBs, including co-benefits from nutrient and sediment BMPs and explore use in CBP decision tools (such as CAST). (Please see the Toxic Contaminants Policy and Prevention Strategy and Workplan for further details). |  |  | (See Toxic Contaminants Policy and Prevention Workplan) |  |  |  | (See Toxic Contaminants Policy and Prevention Workplan) | REFER TO OTHER AP FILE
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [11 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  |  | Geographic Location | Expected Timeline | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
Management Approach 2: Understanding the influence of contaminants in degrading the health, and contributing to mortality, of fish and wildlife | [11 empty] | Management Approach 2: Understanding the influence of contaminants in degrading the health, and contributing to mortality, of fish and wildlife
2.1 | Assess the effects of contaminants on fish and shell fish in tidal waters |  |  | Inform presence of select UV filters, hormones, and antibiotics in eastern oysters and hooked mussels in urban streams and the Chesapeake Bay mainstem. |  |  | UMBC, USDA FS |  |  |  | 2018-2020 | Presentation provided at STAC workshop on contaminants of concern | Completed w/ additional follow up. Study by UMBC is ongoing so more results will be available in the future. POC: Lee Blainey, UMBC
|  |  |  | Inform presence of select CECs in bivalves in the estuarine waters investigated as part of NOAA Oxford study. |  |  | NOAA Oxford |  |  |  | 2018-2020
|  |  |  | Communicate results of Bullhead catfish tumor study, which showed a dramatic decrease in the tumor prevalence in the Anacostia River. |  |  | FWS |  |  |  | 2019 | Presentation provided to TCW and at STAC workshop on contaminants of concern | Completed and can be removed??. Should check if any more study results will be available. POC: Fred Pinckney, USFWS
|  |  |  | Continue study and evaluate findings from condition of Yellow Perch in urban areas. Specifically, FWS and UMD conducted yellow perch sampling in Fall 2017- Winter 2018 in the Severn, Choptank, and Mattawoman. The sampling will be repeated in Fall 2018-Winter 2019. The goal is to determine whether the findings of abnormal yolk and abnormal chorion about ten years ago in the Severn are still apparent. FWS will update those findings with new data, with additional molecular analysis, analyzing lesions and movement over time. |  |  | FWS, MD DNR, USGS |  |  |  | 2018-2020
2.2 | Generate information to document fish health conditions in the Bay watershed. |  |  | Report and communicate results of study to understand the influence of contaminants and other factors degrading the health, and contributing to mortality of fish. The final publication on the retrospective analysis of the relationships between |  |  | USGS |  |  |  | 2019 | Summary is still under development | Incomplete and needs more work. Report expected to be completed in 2020; POC: Vicki Blazer, USGS
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [11 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  |  | Geographic Location | Expected Timeline | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
fish health, estrogenicity and land-use will be completed. Final outcomes will be communicated to the TCW.
|  |  |  | Report and communicate results of study examining the influence of endocrine-disrupting compounds (EDCs) and their effects on fish conditions. The data collected at the integrator sites (2013-2017) is being compiled, analyzed and published as a series of journal articles. The first is compiling long term, integrative indicators at the South Branch Potomac site, which could be a template for subsequent information. This information will be summarized with other data collected by the USGS into a series of synthesis powerpoint presentations. |  |  | USGS |  |  |  | 2019 | Several summary articles are under development. | Incomplete and needs more work. Report expected to be completed in 2020; POC: Kelly Smalling, USGS
|  |  |  | Continue monitoring of and communicating results of fish conditions in areas of concern within jurisdictions. Specifically, USGS is working with PA, MD and WV. One summary paper on disease issues and potential immunosuppression was published in 2018. In addition, WV and PA are collaborating with USGS to assess the immune response of wild smallmouth bass. |  |  | PA DEP, MD DNR, WV DEP |  |  |  | 2018-2020 | Collaborative papers being reviewed with USGS | ongoing with activities planned
|  |  |  | Communicate results of risk assessment study of EDCs compounds with occurrence of intersex and other fish health conditions. Young of the year fish data and model results from PA are being used in |  |  | USGS |  |  |  | 2019 | Several summary articles are under development. | Incomplete and needs more work. Report expected to be completed in 2020; POC: Kelly Smalling, USGS
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [11 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  |  | Geographic Location | Expected Timeline | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
this investigation, as well as long-term historical trend data.
|  |  |  | Continue studies and evaluate the relationship between the amount of impervious surface and the impact on fish conditions. During 2014 – 2018 the MBSS is re-sampling streams that were sampled 20 and 14 years ago. The data will be used to examine for potential change over time in stream biological, physical habitat, and chemical conditions. |  |  | MD DNR |  |  |  | 2018-2020
|  |  |  | Continue stream IBI studies as part of the Maryland biological stream survey to evaluate health of fish communities in 2019-2020. |  |  | MD DNR |  |  |  | 2019
2.3 | Assess the effects of toxic contaminants on wildlife |  |  | Publish results of study examining EDCs found in wildlife within the Chesapeake watershed. |  |  | USGS |  |  |  | 2019 | Presentation provided but results not published | Incomplete? Need to see if an article will be published or if presentation is final product. POC: Kelly Smalling
|  |  |  | Interact with state federal wildlife service agencies to assess priority needs related to contaminant effects on wildlife |  |  | TCW; DE, MD, PA, VA, WVA, working with Habitat Goal Team. |  |  |  | 2019-2020
Management Approach 3: Document the occurrence, concentrations, and sources of contaminants in different landscape settings | [11 empty] | Management Approach 3: Document the occurrence, concentration, and sources of contaminants in different landscape settings
3.1 | Better define the sources and occurrence of EDCs and other toxic contaminant groups in different landscape settings |  |  | Communicate results of study to identify the sources and occurrence of toxic contaminants contributing to degraded fish health. Chemistry data collected at the integrator site is being compiled into a data release. These data will be summarized is at least |  |  | USGS |  |  |  | 2019 | Several summary articles are under development. | Incomplete and needs more work. Report expected to be completed in 2020; POC: Kelly Smalling and Vicki Blazer, USGS
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [11 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  |  | Geographic Location | Expected Timeline | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
one journal article and will be added to the synthesis efforts.
|  |  |  | Communicate results of study of sources and occurrence of EDCs in agricultural watersheds (same locations as USGS fish health studies). Initiate planning for study of urban watersheds, focusing on impact of BMPs on EDCs in the environment. |  |  | USGS |  |  |  | 2018-2020 | Summary article is under development. | Incomplete and needs more work. Report expected to be completed in 2020; POC: Kelly Smalling, USGS
|  |  |  | Communicate GIS analysis to identify toxic contaminant “hotspots” based on land use. Vulnerability metrics are being detailed and will be communicated in the synthesis reporting. |  |  | USGS |  |  |  | 2019 | Initial presentation provided but final is needed. | Incomplete and needs more work. Report expected to be completed in 2020; POC: Kelly Smalling, USGS
|  |  |  | Continue Pennsylvania studies on occurrence of pesticides and hormones and other toxic contaminants in surface water. |  |  | PA DEP USGS |  |  |  | 2018-2020 | Summary paper is under development. Continued sampling focuses on impacted areas and "core" sites (not all in Chesapeake Bay watershed). | Ongoing with activities planned; incomplete and needs more work (reports forthcoming).
|  |  |  | Inform presence of select CECs in sediment, water, and bivalves. |  |  | NOAA Oxford |  |  |  | 2018-2020
|  |  |  | Inform presence of select UV filters, hormones, and antibiotics in eastern oysters and hooked mussels in urban streams and the Chesapeake Bay mainstem near both agricultural and urban landscapes. |  |  | UMBC, USDA FS |  |  |  | 2018-2020
|  |  |  | Inventory jurisdiction toxic contaminant monitoring efforts by individual groups |  |  | TCW and states, DOEE |  |  |  | 2018-2020 | Ongoing as part of USGS inventory | Incomplete and needs work. I don't know if we are sharing with external partners?? POC - Emily Majcher
|  |  |  | Evaluate outcomes from Anacostia River sediment investigation to improve understanding of contaminants other than PCBs in urban environments. |  |  | TCW, DOEE, USGS, UMBC, FWS |  |  |  | 2018-2020 | Ongoing, some studies presented as part of STAC workshop, publication to include lessons learned from Anacostia and other projects in the remedial investigation and clean up field to be written in 2021 | Incomplete and needs more work. Report expected to be completed in 2021.POC - Emily Majcher
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [11 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  |  | Geographic Location | Expected Timeline | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
3.2 | Examine the co-occurrence of toxic contaminants with nutrients and sediments to inform co-benefit analysis (see MA 4) |  |  | Inventory co-located data, spatially analyze to evaluate possible contaminant associations and source, and use results to inform co-benefit understanding (also see MA4) |  |  | TCW; USGS, MDE, VA DEQ, DOEE, DNREC, PA |  |  |  | 2018-2020 | No formal effort underway for inventory co-located concentration data for contaminants, nutrients/sediment | Incomplete and needs more work. Could we use the GIS risk analysis being done by USGS to address relation of contaminant and nutrient/sediment sources? Probably beyond scope of TCW to look at relation between contaminants and nutrient/sediment concentration data. POC for risk analysis: Kelly Smalling and Dan James, USGS
3.3 | Loading rates of toxic contaminants for use in CBP models |  |  | Interact with CBP Modeling group to assess data needs required to inform loading rates of toxic contaminants in various landscape settings |  |  | TCW |  |  |  | 2018-2020 | Preliminary meeting of CBP Modeling/BMP and TCW leadership | Incomplete and needs more work. No clear directions of next steps. POC??
Management Approach 4: Science to help prioritize options for mitigation to inform policy and prevention | [11 empty] | Management Approach 4: Science to help prioritize options for mitigation to inform policy and prevention
4.1 | Summarize further information about direct and co-benefits for mitigation of toxic contaminants, and nutrient and sediment reductions. (also see Science portion of the Policy and Prevention Strategy and Work Plan) |  |  | Inventory case studies where innovative remediation of sediments/water have occurred in the watershed and evaluate how they could be adapted or implemented for TMDL compliance. |  |  | USGS, working with academic and state partners |  |  |  | 2018-2020 | Ongoing, initiated as part of STAC workshop, inventory of papers/projects ongoing. Green IF WE CONSIDER STAC WORKSHOP ADDRESSED THIS | Complete with additional efforts or Incomplete and needs more work?. Depends if we want to do more beyond the STAC workshop
|  |  |  | Investigate the impact of Stormwater Best Management Practices (BMPs) on PCB loadings to waterways. |  |  | MDE funded study. |  |  |  | 2018-2020 | See Policy and Prevention Workplan | Ongoing with activities planned
|  |  |  | Further evaluate findings from the CSN literature review on the potential toxic contaminant reductions provided by traditional stormwater BMPs and Ag BMPs. Decide on most appropriate findings for additional outreach from these and CBP fact sheets. |  |  | TCW partners, USGS |  |  |  | 2018-2020 | Sharing results of STAC workshop with Ag and Urban stormwater WGs and Water-Quality Goal Team. | Completed with additional activities. Once we decide on most important findings and follow-up, will be working with UMCES IAN to develop fact sheet. POC: Scott Phillips
4.2 | Monitor/survey efficiency of BMPs to remove toxic contaminants (mostly PCBs) (also see Science portion of the |  |  | Bioretention efficacy and optimization for removal of toxic contaminants |  |  | UMCP |  |  |  | 2018-2020 | Results briefed at STAC workshop and included in STAC report, ongoing research | Completed with additional activities POC - Birthe Kjellerup
|  |  |  | Design/testing of enhanced media in stormwater control structures for degradation of toxic contaminants |  |  | UMCP |  |  |  | 2018-2020 | Ongoing, study design briefed at STAC workshop additional findings will be briefed at a later time | Incomplete, study ongoing will have additional results to brief ongoing POC Birthe Kjellerup
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [11 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  |  | Geographic Location | Expected Timeline | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
| Policy and Prevention Strategy and Work Plan) |  |  | Riparian forest buffer removal of toxic contaminants |  |  | PSU |  |  |  | 2018-2020 | PSU presented at Toxic Contaminant session of the Chesapeake Research Symposium. However, no follow-up has occurred. | Ongiong with future activities needed. Did PSU determine efficiency of riparian forest buffers in removing toxic contaminants? Need to input from Heather at PSU. Suggestion: PSU to present to TCW- should this be a joint meeting with the forestry WG?
4.3 | Explore use of CBP decision tools to include selected contaminants |  |  | Prepare a matrix of information needed for inclusion of selected contaminants (begin with PCBs) in CAST, and assess availability of information. |  |  | EPA and TCW |  |  |  | 2018-19 | Initial discussions help with CAST and modeling team but no additional progress | Inadequate progress and revise planned activities. POC???
4.4 | Interact with source teams to communicate and apply findings on the co-benefits for mitigation of nutrients, sediment, and toxic contaminants |  |  | Communicate with agricultural, stormwater, and wastewater source teams to identify synergies with nutrient/sediment and toxic contaminant mitigation options |  |  | TCW chairs with selected investigators. |  |  |  | 2018-2020 | Sharing results of STAC workshop with Ag and Urban stormwater WGs and Water-Quality Goal Team. | Completed and additional activities to be planned! Ongoing dialog to determine cooperative efforts related to co-benefits. POC: Scott Phillips and Emily Majcher
4.5 | The Chesapeake Bay Commission will work collaboratively with the Bay Program partners to identify legislative, budgetary and policy needs to advance the goals of the Chesapeake Watershed Agreement. |  |  | CBC will, in turn, pursue action within our member state General Assemblies and the United States Congress. See CBC Resolution #14-1 for additional information on the CBC’s participation in the management strategies. |  |  | CBC |  |  |  | 2018-2020
Management Approach 5: Gather information on issues of emerging concern. | [11 empty] | Management Approach 5: Gather information on issues of emerging concerns
5.1 | Continue to investigate previously identified issues of emerging concern including contaminant toxicity to pollinators, microplastics and UOG. |  |  | Attend, summarize microplastics workshop |  |  | STAC, TCW |  |  |  | 2018-2020 | USGS attended workshop. | Complete with additional activities. Shawn Fisher will be USGS representative on Plastics Action Team
|  |  |  | Track progress USGS NE region microplastics study and identify relevance to CB. |  |  | USGS, TCW |  |  |  | 2018-2020 | USGS provided briefing to workgroup and STAC workshop on topic | Complete with additional activities. Shawn Fisher will be USGS representative on Plastics Action Team
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [11 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  |  | Geographic Location | Expected Timeline | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
5.2 | Prioritize new issues of emerging concern and identify tasks to complete |  |  | Track research progress by USGS and NOAA on the toxins that are produced from algal blooms |  |  | USGS, NOAA, TCW |  |  |  | 2018-2020 | Briefing provided to TCW. However we are not tracking efforts | Completed with new activities. Determine which emerging contaminants to retain and expand activities POCs- Peter Tango, NOAA?
|  |  |  | Aggregate and analyze recent regulations and management approaches related to UV filters, hormones, and antibiotics in other states to help outline possible strategies for CB |  |  | UMBC, TCW |  |  |  | 2018-2020 | Briefing provided to STAC workshop. However we are not tracking efforts
|  |  |  | Determine the nature and extent PFAS data in CB watershed, track progress fish consumption advisories neighboring watersheds (DRB) to help outline possible strategies for CB |  |  | USGS, TCW |  |  |  | 2018-2020 | Briefing provided to TCW. However we are not tracking efforts | Completed with new activities. Determine which emerging contaminants to retain and expand activities POC - Michelle Lorah
|  |  |  | Provide technology Transfer from MD, VA, and DC to other jurisdictions on successful efforts to reduce chloride impacts due to road salt application while maintaining public safety. |  |  | MDE, TCW |  |  |  | 2018-2020 | Briefing provided to TCW. However we are not tracking efforts | Completed with new activities. Determine which emerging contaminants to retain and expand activities POC - Len Schugam, Mark Richards, Greg Onyullo
|  |  |  | Provide technology transfer from MD to other jurisdictions on successful efforts to find beneficial reuse of fly ash produced from coal combustion and minimize disposal in CCR facilities. |  |  | MD DNR, TCW |  |  |  | 2018-2020 | Briefing provided to TCW. However we are not tracking efforts | Completed with new activities. Determine which emerging contaminants to retain and expand activities POC - DNR